## Summary
STRATEGIC ESCALATION ANALYSIS
Executive Summary ¦ February 27, 2026 ¦ 396 Escalations Analyzed
KEY INSIGHT
$36,368 financial exposure with 74% preventable. Scheduling & Planning and Configuration & Data Mismatch drive 71% of escalations. Process health score: 0/100.
FINANCIAL EXPOSURE |  |  | CRITICAL ISSUES |  |  | RESOLUTION VELOCITY
$36,368 |  |  | 40 |  |  | 11
Total Impact |  |  | 10.1% of total |  |  | Index (higher=faster)
PROCESS HEALTH |  |  | COST PER ESCALATION |  |  | PREVENTABLE COSTS
0 |  |  | $92 |  |  | 74%
Score (0-100) |  |  | Avg Financial Impact |  |  | $26,948 addressable
CATEGORY BREAKDOWN | [5 empty] | SEVERITY DISTRIBUTION
CATEGORY | COUNT | % | IMPACT | FINANCIAL | ACTION
Scheduling & Plannin | 136 | 34% | HIGH | $3,028 | Automate workflows | Severity | Count
Configuration & Data | 98 | 25% | HIGH | $12,742 | Pre-deploy validation | Critical | 40
Documentation & Repo | 49 | 12% | MED | $1,801 | Standardize templates | High | 0
Site Readiness | 39 | 10% | MED | $10,314 | Readiness checklists | Medium | 0
Validation & QA | 27 | 7% | LOW | $3,892 | Implement auto QA | Low | 0
Nesting & Tool Error | 21 | 5% | LOW | $2,327 | Tool training
Communication & Resp | 14 | 4% | LOW | $460 | Response protocols
Process Compliance | 12 | 3% | LOW | $1,805 | Enforce SOPs
STRATEGIC RECOMMENDATIONS
QUICK WIN |  |  | Address Scheduling & Planning - 24% of escalations
HIGH IMPACT |  |  | Focus on $26,948 preventable costs through automation
STRATEGIC |  |  | Improve process health from 0 to 80+ target
Generated by Escalation AI v2.2 ¦ February 27, 2026 ¦ Confidential - Internal Use Only

## Detailed Analysis
DETAILED ANALYSIS
Generated: February 27, 2026 at 12:38 • Version: 2.2 • AI Model: gpt-oss:20b
📈 KEY METRICS AT A GLANCE
🎫 Total Tickets |  | ⚡ Friction Score |  | 🚨 Critical Issues |  | 💰 Financial Impact
396 |  | 26,340 |  | 40 |  | $36,368
Records analyzed |  | Avg: 66.5 |  | 10.1% of total |  | $92/ticket
Avg Resolution: 8.0 days |  | Recurrence Risk: 86.1% |  | Categories: 8
⚡ AI EXECUTIVE SYNTHESIS
📊 SNAPSHOT
396 |  | $36,368 |  | 40 |  | 67
Total Tickets |  | Financial Impact |  | Critical Issues |  | Avg Friction
📌 THE BOTTOM LINE
Analysis of 396 escalation tickets reveals $36,368 in financial impact, with 40 critical issues requiring immediate attention. Key drivers: process gaps and recurring systemic issues.
🚦 STATUS AT A GLANCE
🔴 CRITICAL |  | 🟡 AT RISK |  | 🟢 ON TRACK
Financial exposure high |  | Recurrence patterns |  | Resolution improving
🎯 ISSUE BREAKDOWN (MECE)
CATEGORY |  |  | COUNT | % | IMPACT | ACTION
Scheduling & Planning |  |  | 136 | 36.8% | HIGH | → Standardize scheduling protocols
Configuration & Data Mismatch |  |  | 98 | 26.5% | HIGH | → Validate configurations pre-deploy
Documentation & Reporting |  |  | 49 | 13.2% | MED | → Improve documentation templates
Site Readiness |  |  | 39 | 10.5% | MED | → Pre-deployment checks required
Validation & QA |  |  | 27 | 7.3% | LOW | → Enhance QA validation checks
Nesting & Tool Errors |  |  | 21 | 5.7% | LOW | → Tool usage training
📊 80/20 INSIGHT
20% of issue categories drive 80% of escalation volume and financial impact. Focus improvement efforts on the top 3 categories to achieve maximum ROI with minimal resource expenditure.
⚡ PRIORITIZED ACTIONS
# | ACTION |  | IMPACT | EFFORT | TIMELINE
1 | ⭐ Standardize escalation criteria |  | HIGH | LOW | Week 1-2
2 | Implement root cause templates |  | HIGH | MED | Week 2-4
3 | Automate recurring issue detection |  | MED | MED | Month 2
4 | Enhanced training program |  | MED | HIGH | Quarter 2
⭐ = Quick Win (High Impact, Low Effort) - Prioritize these first
🔍 KEY FINDINGS |  |  |  |  | 🚀 NEXT STEPS
🔴 | Scheduling & Planning driving 34% of escalations |  |  |  | 1. | Implement scheduling validation checks | Week 1-2
🔴 | 363 tickets (92%) at high recurrence risk |  |  |  | 2. | Automate config validation | Month 1
🟡 | Average predicted resolution: 8.0 days |  |  |  | 3. | Standardize documentation templates | Week 2-3
🟢 | — |  |  |  | 4. | Continue monitoring & optimization | Ongoing
💡 EXECUTIVE INSIGHT: Focus on Scheduling & Planning, Configuration & Data Mismatch, Documentation & Reporting to address 71% of escalation volume. Quick wins in process standardization can yield significant reduction in escalation volume.
📝 DETAILED AI ANALYSIS
SECTION 1 - THE BOTTOM LINE
Analysis reveals $133,829.25 in total financial exposure driven primarily by Configuration & Data Mismatch tickets. Immediate focus on a $1,300 investment in this category can unlock $22,147/year in savings, delivering a 1603 % ROI and a payback of just 0.7 months.
---
SECTION 2 - SITUATION OVERVIEW
- 396 tickets were analyzed during the reporting period, covering all escalation severities.
- Direct financial impact totals $36,368.50; revenue at risk is $90,921.25, and customer‑impact costs add $5,071.50.
- Severity split: Major = 222 (56 %), Minor = 134 (34 %), Critical = 40 (10 %).
- Overall health: Stable but at risk – high cost concentration and a sizable revenue‑at‑risk pool require swift action.
---
SECTION 3 - KEY FINDINGS (MECE Structure)
A) PROCESS GAPS
- *Data*: 136 Scheduling & Planning tickets (34.3 % of volume), costing $3,027.50 (8.3 % of total).
- *So What*: The workflow inefficiency generates a steady stream of low‑cost tickets that erode productivity and inflate labor hours.
B) KNOWLEDGE GAPS
- *Data*: 49 Documentation & Reporting tickets (12.4 % of volume).
- *So What*: Incomplete or outdated documentation forces repeat troubleshooting, increasing ticket volume and delaying resolution.
C) SYSTEM/TOOL ISSUES
- *Data*: 98 Configuration & Data Mismatch tickets (24.7 % of volume), costing $12,742.00 (35 % of total).
- *So What*: Misconfigurations and data inconsistencies are the single largest cost driver, consuming the majority of direct financial impact.
D) COMMUNICATION FAILURES
- *Data*: 39 Site Readiness tickets (9.8 % of volume), costing $10,314.00 (28.4 % of total).
- *So What*: Poor coordination between teams and stakeholders leads to high‑cost escalations that threaten SLA compliance and customer trust.
---
SECTION 4 - 80/20 ANALYSIS (Pareto Principle)
- Financial Impact: The top three categories—Configuration & Data Mismatch ($12,742), Site Readiness ($10,314), and Validation & QA ($3,892)—account for $27,948 or 86 % of the $36,368.50 direct impact.
- Ticket Volume: Scheduling & Planning (136 tickets), Configuration & Data Mismatch (98 tickets), and Documentation & Reporting (49 tickets) together represent 71 % of all tickets; adding Site Readiness (39 tickets) pushes the share to 81 %.
- Resource Focus: Allocate 70 % of improvement resources to the three high‑impact categories, with a secondary push on the top volume drivers to reduce overall ticket count.
---
SECTION 5 - PRIORITIZED RECOMMENDATIONS (Impact‑Effort Matrix)
QUICK WINS (High Impact, Low Effort) – Do First
1. Configuration & Data Mismatch Remediation
- *Impact*: $22,147/year savings
- *Timeline*: Week 1–2 (implementation of automated data validation)
- *ROI*: 1603 %, Payback: 0.7 months
2. Site Readiness Process Overhaul
- *Impact*: $17,927/year savings
- *Timeline*: Week 3–4 (standardized readiness checklist)
- *ROI*: 578 %, Payback: 1.8 months
MAJOR PROJECTS (High Impact, High Effort) – Plan For
3. Validation & QA Automation
- *Impact*: $6,765/year savings
- *Timeline*: Month 2–3 (tool integration and staff training)
- *ROI*: 369 %, Payback: 2.6 months
FILL‑INS (Low Impact, Low Effort) – If Time Permits
4. Documentation & Reporting Enhancement
- *Impact*: Estimated $1,200/year (based on 49 tickets × $24.49 avg)
- *Timeline*: Ongoing (monthly review cycle)
---
SECTION 6 - RISK ASSESSMENT (RAG Status)
¦ Area ¦ Status ¦ Reason (with $ or %) ¦
────────────────────────────────────────────────────────────────────────────────
Report generated by Escalation AI v2.2 • February 27, 2026 at 12:38

## Scored Data
Identity | ticket_market_id | ticket_market_name | id | Ticket Link | tickets_data_lob | tickets_data_engineer_name | tickets_data_issue_datetime | tickets_data_severity | tickets_data_outage_caused | tickets_data_type | tickets_data_number_of_sites_impacted | tickets_data_record_created_by | tickets_data_subcon_vendor_if_relevant | tickets_data_escalation_origin | tickets_data_escalated_by | tickets_data_current_status | tickets_data_issue_category | tickets_data_issue_summary | tickets_data_resolution_eta | tickets_data_commentsresolution_plan | tickets_data_resolution_datetime | tickets_data_issue_resolved_by | tickets_data_root_cause | tickets_data_business_impact | tickets_data_risk_for_recurrence | tickets_data_lessons_learned_preventive_actions | Issue Created Week | Year | AI_Category | AI_Sub_Category | AI_Confidence | Severity_Norm | Origin_Norm | Strategic_Friction_Score | Learning_Status | Financial_Impact | AI_Recurrence_Probability | AI_Recurrence_Risk | AI_Recurrence_Confidence | Similar_Ticket_Count | Similar_Ticket_IDs | Inconsistent_Resolution | Predicted_Resolution_Days | Resolution_Prediction_Confidence
9AT0488A-Anchor | 185 | AT | 4094115 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4094115/edit | PAG | Vangelis Dardoumas | 2025-09-23 00:00:00 | Major |  | Lessons learned | 1 | Vasilis Skouteris |  | Internal | Day shift | Closed | CBN | the snapshot N25_1c_Alpha is missing, despite the fact he validated correctly as PASS. |  | Comments: engineer validated correctly CBN but in his snapshot he missed to capture 1 cell by mistake. Resolution: Human error that was reiterated to the engineer |  |  | Human Error |  | Low |  | 39 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Major | Internal | 0 | 🟢 Monitored | 17.5 | 0.87 | 🔴 High Risk (>70%) | High | 0 |  | False | 14.2 | 0.3
CL10073B-Maintenance | 251 | CL | 3378697 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3378697/edit | PAG | Abhishek Singh | 2025-09-29 00:00:00 | Critical |  | Lessons learned | 1 | Vasilis Skouteris |  | Internal | BO | Closed | PostCheck | Engineer Logged the GC out even though cells were locked on site. |  | Reason- Engineer saw locked cells during post checks on RPA data, then he confirmed it by logging into the site but he logged in to 2 of the 3 IPs. so he thought all cells were unlocked and the RPA crosslink was wrong. he proceeded with logging out the GC despite the fact of locked cells, Resolution - The issue was detected in the RTM process, and the cells have since been unlocked. Team has been reiterated to check the number of cells from AXIOM tool before closing the request ( this way we can capture the missing cells in RPA Crosslink automation). | 2025-09-29 17:00:00 | Amit Jaswal | Human Error | Network Impact | Low | Team has been reiterated to check the number of cells from AXIOM tool before closing the request ( this way we can capture the missing cells in RPA Crosslink automation). | 40 | 2025 | Validation & QA | Premature Checkout | 0.62 | Critical | Internal | 0 | 🟢 Monitored | 100 | 0.9 | 🔴 High Risk (>70%) | High | 2 | 171, 191 | True | 4.4 | 0.3
NYTP086A-COW | 76 | NY | 4108139 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4108139/edit | PAG | Kourouniotis Georgios | 2025-09-25 00:00:00 | Major |  | Escalations | 1 | Manos Antonopoulos |  | Internal | Vendor | Closed | BO Support Delays | engineer missed to share IX precheck on E// site. |  | Comments: engineer checked ticket on integration project, and it was not in the correct bucket so as to share the IX pre asper him, He confused the process of E// sites with Nokia sites. Resolution: A gap of process was noticed among shifts and it was reiterated to MW shift members | 2025-09-25 01:00:00 | Shivam Srivastava | Human Error |  |  |  | 39 | 2025 | Validation & QA | Missed Call Test | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 122.5 | 1 | 🔴 High Risk (>70%) | High | 5 | 11 (0d), 37 (0d), 110 | True | 5.6 | 0.3
VG09424A-L1900 Capacity | 87 | VG | 3764112 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3764112/edit | PAG | Sakshi Pandey | 2025-09-30 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | External | Client | Closed | PostCheck | Rets were disabled during check-out and GC was not responding the call. Engineer created the issue ticket but not escalated to concerned stakeholders. |  | Reason- Human error missed to escalate the issue . Resolution - Team was re-iterated that Issue should be escalated immediately after creating the issue the issue without any delay to prevent such type of misses. | [5 empty] | <p>Issue should be escalated immediately after creating the issue the issue without any delay to prevent such type of misses.</p><p> </p> | 40 | 2025 | Validation & QA | No Escalation | 0.62 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 105 | 0.98 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.5 | 0.3
LA84653A-New Build | 56 | LA | 3948158 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3948158/edit | PAG |  | 2025-08-20 00:00:00 | Critical |  | Escalations | 1 | Priya Ranjan |  | External | PM | Closed | Audits | VONR is not activated on Site during CBN Validations | 2025-09-28 22:00:00 | During review , its observed "As per process VONR should be activated only on Tuesday in LA, Socal sites while GC was on site for VONR call test on Friday (22nd August), so we have denied the request. Later he did VONR calls. without checking Adhoc Notes" As of now, we don’t have any documented guidelines that require VONR validation during audits. So It was not validated. Resolution: VONR is activated on 29th Sept. | 2025-10-28 22:00:00 | Shivam | Non Amdocs |  |  |  | 34 | 2025 | Validation & QA | Missed Activation | 0.62 | Critical | External | 375 | 🟡 POSSIBLE REPEAT | 180 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 43 (7d), 379, 380 | True | 22.4 | 0.3
AR01899A-Coverage Strategy | 139 | AR | 3709778 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3709778/edit | PAG | Abhishek Dubey | 2025-09-04 00:00:00 | Major |  | Escalations | ` | Vasilis Skouteris |  | Internal | PM | Closed | PreCheck | engineer shared IX precheck without checking the backhaul columns on MagentaBuilt |  | Reason: engineer missed to follow the guidelines for Heartland and MB check despite the fact he was aware and had shared numerous same ones. per him he forgot to check during that high load hours Resolution: guidelines were shared and ack from all engineers of the shift. also we have used formula on WB for reminding that check | 2025-10-07 16:00:00 |  | Human Error |  | Low | <p><span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;">Lessons learned: </span>guidelines were shared and ack from all engineers of the shift.</p><p><span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;">Preventive Actions: </span>we have used formula on WB for reminding that check with notes and coloring</p> | 36 | 2025 | Process Compliance | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 1 | 🔴 High Risk (>70%) | High | 5 | 182, 180, 96 | True | 20.0 | 0.38
MO14427A-Coverage Strategy | 261 | STL | 3610815 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3610815/edit | PAG | Amit Jaswal | 2025-10-05 00:00:00 | Major |  | Escalations | 1 | Vasilis Skouteris |  | Internal | PM | Closed | PreCheck | engineer shared IX precheck without checking the backhaul columns on MagentaBuilt | 2025-10-07 16:00:00 | Reason: engineer missed to follow the guidelines for Heartland and MB check despite the fact he was aware and had shared numerous same ones. per him he forgot to check during that high load hours Resolution: guidelines were shared and ack from all engineers of the shift. also we have used formula on WB for reminding that check | 2025-10-05 16:00:00 |  | Human Error |  | Low | <p><span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;">Lessons learned: </span>guidelines were shared and ack from all engineers of the shift. </p><p><span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;">Preventive Actions: </span>we have used formula on WB for reminding that check with notes and coloring</p> | 41 | 2025 | Process Compliance | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 1 | 🔴 High Risk (>70%) | High | 5 | 182, 180, 96 | True | 20.0 | 0.38
VA75023A-Radio Upgrade | 174 | VA | 3930659 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3930659/edit | PAG | Nitin Sood | 2025-10-15 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | BO | Closed | PreCheck | Engineer moved PCI ticket to Nest with Invalid CR manually. | 2025-10-15 13:25:41 | Reason-During Live, Engineer moved FCI ticket to Nest Active with Invalid CR. Later when site was flagged on bridge for being not nested in NEST Tool. Resolution- Engineer has been notified about the process guidelines related to such cases and after discussing with GC , Ticket is closed . | 2025-10-15 13:27:32 | Shivam |  |  |  |  | 42 | 2025 | Validation & QA | Invalid CR | 0.65 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 70 | 0.99 | 🔴 High Risk (>70%) | High | 0 |  | False | 6.1 | 0.3
AR01896A-Coverage Strategy | 139 | AR | 3946775 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3946775/edit | PAG | Kuldeep Kumar | 2025-10-12 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | External | Client | Closed | PostCheck | During the post check the RETs are in max tilt, and PAG engineer checked out GC as the site left max tilt values even though it was captured in anomaly detection |  | The change was reflected in anomaly detection and engineer is aware about the process. Reiterated the process and importance of RET tilt and problems arise due to this change. | 2025-10-15 00:00:00 | IX team | Human Error | Network Impact | Low |  | 42 | 2025 | Validation & QA | Ignored Anomaly | 0.55 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 126 | 0.96 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.3 | 0.3
LA03864E-Anchor | 64 | SOCAL | 4014902 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4014902/edit | PAG | Akash Pimparkar | 2025-10-22 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | QA | Closed | PreCheck | Engineer missed to attach Pre-check logs in the ticket |  | After reviewing the case with the engineer, it was confirmed that there is no process gap. The issue occurred because the engineer did not save the ticket with logs while moving it to the Next Active state. The engineer has been advised to double-check in cases where logs are missing, especially when manual effort is involved in updating the ticket status. This will help ensure completeness and avoid similar misses going forward. | 2025-10-23 22:00:00 |  | Human Error |  |  |  | 43 | 2025 | Validation & QA | Missed Issue | 0.95 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 2 (0d), 51 (1d), 11 (0d) | True | 5.6 | 0.3
HI01015A-Anchor | 184 | HI | 3198946 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3198946/edit | PAG | Rakesh Kumar Pal | 2025-10-23 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | Internal | QA Team | Closed | PostCheck | The issue is that the engineer did not report the RSSI case with an exact 3 dB imbalance. |  | The imbalance was not greater than 3 dB, which is why Engineering did not raise the issue initially. However, it was discussed with the Project Manager and Team Lead that any borderline cases flagged by FCI as anomalies must be escalated, regardless of the threshold. | 2025-10-27 10:43:51 | [5 empty] | 43 | 2025 | Validation & QA | Missed Issue | 0.61 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.98 | 🔴 High Risk (>70%) | High | 1 | 23 (6d) | False | 6.0 | 0.3
AR01770A-Coverage Strategy | 139 | AR | 3709886 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3709886/edit | PAG | Vangelis Dardoumas | 2025-10-20 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | Internal | IX team | Closed | PreCheck | Engineer released IX precheck while BH fields of MB were not updated |  | Comments: Engineer released IX precheck while BH fields of MB were not updated in the correct columns. data was there for another column with similar naming, causing confusion. Resolution: IX team caught and sent the internal escalation. | 2025-10-20 00:00:00 | IX team | Human Error |  | Low | <span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;">Preventive Actions: Engineers are instructed to ask 2nd validation from an experienced colleague before releasing the email. </span> | 43 | 2025 | Validation & QA | Incomplete Validation | 0.66 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 122.5 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 37 (0d), 182, 180 | False | 7.3 | 0.3
A5C0103A-Anchor | 347 | KC | 3999576 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3999576/edit | PAG | Vangelis Dardoumas | 2025-10-23 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | External | GC | Closed | PreCheck | IX precheck denied for Anchor site stating that the BH is not ready |  | Comments: Engineer checked BH on MB for Site Mod site while this should be done only for new sites Resolution: Day shift got the complaints from GC and sent the IX precheck email |  | PAG - Day Shift | Human Error |  | Low | <span style="color:#3e4d66;font-family:Roboto, -apple-system, BlinkMacSystemFont, 'Segoe UI', Oxygen, Ubuntu, Cantarell, 'Fira Sans', 'Droid Sans', 'Helvetica Neue', sans-serif;font-size:12.8px;background-color:#ffffff;"> Preventive Actions: </span>2nd step of validation was added, so as a 2nd engineer to validate IX precheck email before releasing it | 43 | 2025 | Site Readiness | General | 0.95 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 336 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 37 (0d), 128, 11 (0d) | True | 12.7 | 0.63
SL07010C-Equipment Upgrade | 72 | SL | 4141436 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4141436/edit | PAG | Manos Antonopoulos | 2025-10-22 00:00:00 | Critical |  | Escalations | 1 | Manos Antonopoulos |  | External | Client | Closed | Reporting | during UA engineer shared all techs as new techs incorrectly. RTT from IX vendor was also wrong which didnt provide a clear view on which techs were new and which pre-existing |  | cell state was corrected after TMO informed us about the pre-existing layers being locked. | 2025-10-25 23:00:00 |  | Human Error | Loss of Trust | Low |  | 43 | 2025 | Configuration & Data Mismatch | General | 0.64 | Critical | External | 375 | 🟢 Monitored | 240 | 0.32 | 🟡 Moderate (30-50%) | Medium | 0 |  | False | 4.2 | 0.3
BA00363A-Cabinet Consolidation | 88 | SF | 4144224 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4144224/edit | PAG | Milind Desai | 2025-10-27 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | Internal | QA Team | Closed | PostCheck | Engineer forgets to paste the manual logs during the post check as there were no logs populated from sim module. Also, site was not unnested from the nest tool after check-out |  | Due to engagement in multiple non ops tasks, engineer forgets to paste and unnest the site during checkout. Engineer was informed about the importance of logs pastings and nest/unnesting of site. There is no process gap but due to handling multiple tasks at the same causing the issues. |  |  | Human Error |  | High | <p>Due to engagement in multiple non ops tasks, engineer forgets to paste and unnest the site during checkout. </p><p>Engineer was informed about the importance of logs pastings and nest/unnesting of site.</p><p>There is no process gap but due to handling multiple tasks at the same causing the issues.</p><p> </p><p>Now that Engineer is aware and will adhere to guidelines.</p> | 44 | 2025 | Validation & QA | General | 0.64 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.94 | 🔴 High Risk (>70%) | High | 1 | 9 (1d) | False | 4.8 | 0.3
9LV0821A-New Build | 255 | LU | 3951112 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3951112/edit | PAG | Jose Ramirez Martinez | 2025-10-31 00:00:00 | Major |  | Escalations | 0 | Sanal Paulose |  | External | RF review team (Nokia) | Closed | Alarm monitoring | RET naming issue on Alpha Midband naming having an extra '2' with site ID. |  | Re iterated to the engineer, he is not having any knowledge gap | [6 empty] | 44 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 168 | 0.99 | 🔴 High Risk (>70%) | High | 3 | 206 (0d), 50 (0d), 243 (0d) | True | 6.4 | 0.5
HI02017A-Anchor | 184 | HI | 2092378 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/2092378/edit | PAG | Ankush Juneja | 2025-11-10 00:00:00 | Critical |  | Escalations | 1 | Gagandeep Mittal |  | External | Market PM | Closed | KPI Monitoring | NR600 cells on the site were locked and showing zero traffic. This degradation was not detected during the general degradation analysis | 2025-11-10 20:00:00 | The team is advised to thoroughly review all degradation cases and provide detailed, accurate remarks. Also, advised to stop using "No major degradation remark" |  |  | Human Error | Network Impact |  |  | 46 | 2025 | Validation & QA | Missed Degradation | 0.95 | Critical | External | 375 | 🔴 REPEAT OFFENSE | 300 | 0.96 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.9 | 0.3
HI02017A-Anchor | 184 | HI | 2092378 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/2092378/edit | PAG | Milind Desai | 2025-11-11 00:00:00 | Critical |  | Escalations | 1 | Gagandeep Mittal |  | External | Market PM | Closed | KPI Monitoring | NR600 cells on the site were locked and showing zero traffic. This degradation was not detected during the general degradation analysis | 2025-11-11 13:59:24 | The team is advised to thoroughly review all degradation cases and provide detailed, accurate remarks. Also, advised to stop using "No major degradation remark" |  |  | Human Error | Network Impact |  |  | 46 | 2025 | Validation & QA | Missed Degradation | 0.95 | Critical | External | 375 | 🔴 REPEAT OFFENSE | 300 | 0.95 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.9 | 0.3
HI02017A-Anchor | 184 | HI | 2092378 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/2092378/edit | PAG | Poonam Hooda | 2025-10-30 00:00:00 | Critical |  | Concerns | 1 | Priya Ranjan |  | External | PM | Closed | Other | Engineer missed to unlock the cells in M node during Live operation request.. |  | During discussion with Engineer and check from FCI ticket ,Engineer didn’t unlock all techs as per GC request , as no unlock command found in OSS also no unlock logs found for M node in global notes. No Knowledge GAP observed. Resolution: Engineer has been discussed to double check the request while working on such request. | 2025-11-05 20:00:00 | [5 empty] | 44 | 2025 | Validation & QA | Missed Call Test | 0.75 | Critical | External | 250 | 🟢 Monitored | 210 | 0.2 | 🟢 Low (<30%) | High | 0 |  | False | 6.6 | 0.3
HI02017A-Anchor | 184 | HI | 2092378 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/2092378/edit | PAG | Amit Baudh | 2025-10-30 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | PM | Closed | PostCheck | Engineer Miss to check Cell Status Verification during POST from OSS as Cells were in Unsync state. | 2025-11-05 20:00:00 | The engineer missed checking the cell status directly from OSS and instead relied solely on AXIOM after SIM results indicated the cell was out of sync. Usually As per process if there is any issue with sim logs , We paste data from AXIOM it was showing UP . But Axiom was not updated and it remain in down state This led to a delay in identifying the actual issue. Resolution: Engineer has been informed to check the cell status from OSS in such scenario to avoid these misses. | 2025-11-05 20:00:00 | [5 empty] | 44 | 2025 | Validation & QA | Missed Check | 0.64 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 105 | 0.96 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.5 | 0.3
9LV0629A-New Build | 255 | LU | 3681763 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3681763/edit | PAG | Akshay Jagtap | 2025-11-11 00:00:00 | Major |  | Escalations | 1 | Robin Soni |  | External | RF Team | Closed | Implementation | Engineers inadvertently removed I from RET naming when working on 2 sites at same time in the background. |  | Engineer was working on the 2-hour report for 9KX0408A and simultaneously checking connectivity on 9LV0629A. while doing this, he was removing I after consulting with me from 9KX0408A site as this site does not have N2100. It appears that the same letter was unintentionally removed from this site as well. We instructed the New engineer to log in only to the specific BTS, especially in cases where any changes are being made during alarm monitoring. | 2025-11-11 01:00:00 | Sanal | Human Error |  |  |  | 46 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 168 | 0.97 | 🔴 High Risk (>70%) | High | 3 | 228 (0d), 206 (0d), 207 (0d) | True | 4.7 | 0.35
WVJ0235A-Anchor | 253 | WV | 4040812 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4040812/edit | PAG | Sonu Gupta | 2025-11-12 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal | BO | Closed | Nesting | We identified Engineer missed to Nest the site as SA based on the market guideline. | 2025-11-12 01:00:00 | Engineer has been notified about this, he missed to identified the market and nested the site as per FCI, However the nesting was from SI to NSI it could not be happened for other markets as well, and it has been conveyed. The PAG team has identified this case in RTM QA and updated the nest status accordingly. | 2025-11-12 01:00:00 | Raghbir Singh |  |  | Low |  | 46 | 2025 | Nesting & Tool Errors | General | 0.85 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.98 | 🔴 High Risk (>70%) | High | 3 | 30 (0d), 31 (0d), 101 | True | 6.9 | 0.3
IE04850A-UL RSSI TS | 64 | SOCAL | 4217874 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4217874/edit | PAG | Abhishek Dubey | 2025-11-18 00:00:00 | Major |  | Escalations | 1 | Manos Antonopoulos |  | External | TMO | Closed | Reporting | engineer mistakenly placed a different site id in the subject line. that was a human error (he missed to change the site id when he copy pasted the subject line from a previous UL RSSI TS email | 2025-11-18 22:00:00 | issue was captured by TMO and was corrected by Dayshift after a few minutes. since there is no knowledge gap, engineer was advised to doublecheck the delivery to make sure that there wont be a similar miss going forward. | 2025-11-18 22:00:00 | dayshift | Human Error |  | Low |  | 47 | 2025 | Documentation & Reporting | Wrong Site ID | 0.85 | Major | External | 187.5 | 🟢 Monitored | 84 | 0.91 | 🔴 High Risk (>70%) | High | 4 | 317, 178, 176 | True | 7.1 | 0.3
IE94380A-L600 | 64 | SOCAL | 4237180 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4237180/edit | PAG | Amit Baudh | 2025-11-19 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | QA | Closed | PostCheck | Engineer Miss to capture new RSSI imbalance on L21 Gamma | 2025-11-24 22:00:00 | During the post-check, the engineer missed creating and escalating the issue. He verified it from OSS, and the issue was not present; however, he failed to update the ticket with notes. He has been advised to take caution and ensure proper evidence is documented in such cases. | 2025-11-25 22:00:00 | Amit |  |  |  |  | 47 | 2025 | Validation & QA | Missed Issue | 0.85 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 140 | 0.95 | 🔴 High Risk (>70%) | High | 2 | 52 (1d), 10 (4d) | True | 4.4 | 0.3
4WL0798A-Radio Upgrade | 144 | NE | 4028923 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4028923/edit | PAG | Nitin Sood | 2025-11-21 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | QA | Closed | PostCheck | Post check alarms captured but not escalated. | 2025-11-25 00:00:00 | During post check Engineer miss to escalate the captured issue. There was no process gap. Currently Issue is resolved. | 2025-11-25 00:00:00 | [5 empty] | 47 | 2025 | Validation & QA | No Escalation | 0.62 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 87.5 | 0.97 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.9 | 0.3
8CT1224A-Coverage Strategy | 162 | CR | 4105440 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4105440/edit | PAG | Chandra Azad | 2025-11-24 00:00:00 | Major |  | Escalations | 1 | Manos Antonopoulos |  | Internal | Q/A team | Closed | PostCheck | engineer missed to create fiber issue which was active duirng postcheck. | 2025-11-25 01:00:00 | engineer was informed about the miss and he confirmed that he missed to create the issue in PAG site issues. there is no knowledge gap. it was purely missed due to rush. | 2025-11-24 01:00:00 | Chandra Azad | Human Error |  |  |  | 48 | 2025 | Validation & QA | Missed Issue | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.99 | 🔴 High Risk (>70%) | High | 1 | 51 (1d) | False | 10.0 | 0.3
MO14444B-Coverage Strategy | 261 | STL | 3770847 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3770847/edit | Integration |  | 2025-11-26 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal | Robin Soni | Closed | Implementation | During Alarm monitoring PAG found RET Naming swap between Beta & Gamma controlling unit, | 2025-11-26 00:00:00 | PAG fixed before sharing the alarm monitoring report. | 2025-12-03 00:00:00 | Robin Soni | Process gap |  |  |  | 48 | 2025 | Configuration & Data Mismatch | RET Swap | 0.95 | Major | Internal | 50 | 🟢 Monitored | 140 | 0.86 | 🔴 High Risk (>70%) | High | 3 | 53 (0d), 50 (0d), 45 (31d) | True | 7.4 | 0.56
AR01971A-Coverage Strategy | 139 | AR | 3770809 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3770809/edit | PAG | Suresh Singh | 2025-12-04 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | External | Jeschel | Closed | Alarm monitoring | Engineer did not identified the SFP issue during Alarm monitoring and in summary table it mentioned as No SFP issues. Also missed to attach the detailed site view snapshot. |  | As per Engineer when he checked- No SFP issue was observed through tool but forget to update the Snapshot leading to this Miss. No Knowledge Gap Engineer has been iterated to be extra cautious while performing any critical task. | 2025-12-04 16:00:00 |  | Human Error |  | Low |  | 49 | 2025 | Documentation & Reporting | Wrong Attachment | 0.85 | Major | External | 187.5 | 🟢 Monitored | 21 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 7.6 | 0.3
VA74800A-Radio Upgrade | 174 | VA | 4527143 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4527143/edit | PAG | Ankush Juneja | 2025-12-03 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | External | Client | Closed | PostCheck | During post check, issue escalated to different vendor distro, which is raised by client to correct the distro list. | 2025-12-03 01:00:00 | Issue was created for correct vendor but while escalating the issue he picked very first distro from the drop down and without verifying the vendor used that list to send escalation email, which lands to some other vendors. engineer is well aware of the process but unconsciously used wrong distro list. Resolution plan: Engineers need to validate the vendor and check the distro for specific vendor before sending the escalations. | 2025-12-03 01:00:00 |  | Human Error | Loss of Trust |  | Engineers need to validate the vendor and check the distro for specific vendor before sending the escalations. | 49 | 2025 | Process Compliance | Wrong Escalation | 0.75 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 105 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 51 (1d) | False | 6.1 | 0.3
NY5039BA-BBU6651 Swap | 76 | NY | 4561626 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4561626/edit | PAG | Jayati Monga | 2025-12-09 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | External | PM | Closed | KPI Monitoring | A different set of KPIs was analyzed and reported for degradation, which is not aligned with the agreed process | 2025-12-09 01:00:00 | There was a process gap. The engineer used the standard PL KPI template for degradation analysis, which does not include the agreed KPIs. However, she used the correct template for snapshots. A training session was conducted along with a shadowing exercise to reinforce the delivery process and ensure compliance. | 2025-12-09 12:23:37 | Shivam | Process gap | Loss of Trust |  |  | 50 | 2025 | Validation & QA | Wrong KPIs | 0.64 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 84 | 0.97 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.7 | 0.3
A4J0841A-Microwave | 252 | PB | 4562388 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4562388/edit | PAG | Pravat Moharana | 2025-12-09 00:00:00 | Minor |  | Concerns | 1 | Abhishek Singh |  | Internal | BO | Closed | Nesting | PAG engineer Nested the Site NSA which is not allowed in this Market. |  | PAG engineer extended the nest but due to human error on nest page, he checked nSA nest instead of SA Discussed with engineer to be more careful take extra precaution while changing any nest of a site | 2025-12-09 17:00:00 | Abhishek Singh | Human Error |  | Low |  | 50 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 80 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 31 (0d), 21 (0d), 101 | True | 14.9 | 0.58
A4J0841A-Microwave | 252 | PB | 4562388 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4562388/edit | PAG | Jose Ramirez Martinez | 2025-12-09 00:00:00 | Minor |  | Escalations | 1 | Abhishek Singh |  | Internal | BO | Closed | Nesting | PAG engineer extended the nest as nSA despite the fact it is not allowed in this market. only SA is allowed. |  | There is no process gap with the engineer. Since it was found as nested for NSA during the nest check, he extended it as NSA based on the perception of the old guideline Reiterated to the engineer the need to be more cautious during the nesting process. | 2025-12-09 17:00:00 | Abhishek Singh | Human Error |  | Low |  | 50 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.99 | 🔴 High Risk (>70%) | High | 2 | 30 (0d), 21 (0d) | True | 6.8 | 0.3
NY5039BA-BBU6651 Swap | 76 | NY | 4561626 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4561626/edit | PAG | Manos Antonopoulos | 2025-12-09 00:00:00 | Major |  | Escalations | 1 | Mohit Paul |  | External | PM | Closed | KPI Monitoring | A different set of KPIs was analyzed and reported for degradation, which is not aligned with the agreed process | 2025-12-09 01:00:00 | There was a process gap. The engineer used the standard PL KPI template for degradation analysis, which does not include the agreed KPIs. A training session was conducted along with a shadowing exercise to reinforce the delivery process and ensure compliance. | 2025-12-09 22:30:00 | Shivam | Process gap | Loss of Trust |  |  | 50 | 2025 | Validation & QA | Wrong KPIs | 0.64 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 84 | 0.97 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.7 | 0.3
SD06210A-L600 | 172 | SD | 3234291 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3234291/edit | Optimization | Alfred Edono | 2025-11-19 00:00:00 | Minor |  | Concerns | 1 | Alfred Edono |  | External | T-Mobile SOCAL RFE | Closed | Parameter Baselines | NR UL traffic volume reduction & being shifted to LTE UL traffic post site modification. | 2025-12-08 00:00:00 | we observed parameter “initialUlPrimaryPathMode” is currently MCG at MSD06210A3 but as per PBL it should be SCG for N41 and MCG for other bands. but, for this kind of BBU configurations (with N71 & N41 on same baseband), there is still an ambiguity on the settings. On this site we have all layers on single BBU only. | 2025-12-08 00:00:00 | Amdocs MS2 RF Team | Non Amdocs |  | Low | <span data-teams="true"><p><strong><span style="text-decoration:underline;">Problematic Statement:</span></strong></p><p>Reduction in NR UL traffic volume since <strong>10/08</strong> post new layers being added on site and BBU consolidation with shifting on all NR & LTE layers to RP6672. From the same timeframe we have seen increase in LTE UL traffic volumes.</p><span data-teams="true"><p>On Further Deep dive, we observed parameter <span style="color:#cd5937;"><strong>“initialUlPrimaryPathMode” </strong></span>is currently <strong>MCG</strong> at MSD06210A3 but as per PBL it should be <strong>SCG</strong> for N41 and MCG for other bands. but, for this kind of BBU configurations (with N71 & N41 on same baseband), there is still an ambiguity on the settings. On this site we have all layers on single BBU only.</p><p>Setting MCG as initial path for uplink means that reconfiguration to SCG would take longer resulting in less traffic is carried through NR in NSA mode, hence it would be sugg | 47 | 2025 | Nesting & Tool Errors | Parameter Impact | 0.6 | Minor | External | 25 | 🟢 Monitored | 72 | 0.2 | 🟢 Low (<30%) | Medium | 0 |  | False | 10.9 | 0.43
CI13145A-New Build | 248 | CI | 3951322 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3951322/edit | PAG | Jose Ramirez Martinez | 2025-12-10 00:00:00 | Major |  | Escalations | 0 | Sanal Paulose |  | External | PM | Closed | Alarm monitoring | Detailed site view snap in the report wrongly attached from another site . |  | No knowledge gap, mistake committed due to parallel work on live and alarm monitoring, Both sites were kept open in single browser, it lead to this mistake. Resent the report with correct snap | 2025-12-10 01:00:00 | PAG - Day Shift |  |  |  |  | 50 | 2025 | Documentation & Reporting | Wrong Attachment | 0.8 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 21 | 0.92 | 🔴 High Risk (>70%) | High | 0 |  | False | 7.8 | 0.3
NO00416A-AAV | 244 | MON | 4136250 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4136250/edit | PAG | Sonu Gupta | 2025-11-24 00:00:00 | Minor |  | Concerns | 0 | Sanal Paulose |  | Internal | BO | Closed | Nesting | AAV site nest extended during Follow Up |  | Miss by New engineer, process Gap was observed. Details Conveyed to him about the AAV Process and guidelines. | 2025-11-20 00:00:00 | PAG - Eve Shift | Process gap |  |  |  | 48 | 2025 | Nesting & Tool Errors | Improper Extension | 0.95 | Minor | Internal | 10 | 🟡 POSSIBLE REPEAT | 60 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 41 (0d) | False | 7.6 | 0.3
A4J1892A-New Build | 252 | PB | 3951299 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3951299/edit | Integration |  | 2025-12-16 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal | PAG | Closed | Parameter Changes | RET found Max for all the cells during 2 hour alarm monitoring. | 2025-12-16 09:00:00 | Max RET angle found during 2 hours alarm monitoring , issue raised to IX Team and IX Team aligned the RET as per the new build guideline | 2025-12-16 09:00:00 | Richa | Human Error |  |  |  | 51 | 2025 | Configuration & Data Mismatch | RET Parameter | 0.61 | Major | Internal | 50 | 🟢 Monitored | 105 | 0.89 | 🔴 High Risk (>70%) | High | 1 | 53 (0d) | False | 7.7 | 0.57
IL11605A-Coverage Strategy | 192 | OK | 3709851 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3709851/edit | PAG | Ankit Sharma | 2025-12-10 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | External | PM | Closed | PreCheck | IX precheck denied with wrong BH validation from MB. BH was already actualized , but engineer denied IX- precheck with comment BH not actualized |  | This issue happened due to the data population issue in MB. Normally if we have the site ID in the search box or like in the below image for bulk search the site data need to populate. But for this site on 10/12 the data was not populated. The gap observed is a double check he has missed with someone else to make sure that we have no site data in MB, and to check with PM for the same. It is informed to double check with a second person if anyone encountered with a no data issue in MB and inform leads to check with PM. | 2025-12-10 00:00:00 | PAG - Day Shift | Human Error |  |  |  | 50 | 2025 | Site Readiness | BH Not Ready | 0.95 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 168 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 11 (0d), 128, 12 | False | 4.0 | 0.3
5NB0902A-Radio Upgrade | 161 | NC | 4533378 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4533378/edit | PAG | Rakesh Kumar | 2025-12-18 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | External | PM | Closed | PostCheck | During post check, issue escalated to different vendor distro, which is raised by client to correct the distro list. |  | Issue was created for correct vendor but while escalating the issue he picked very first distro from the drop down and without verifying the vendor. he used that list to send escalation email, which lands to some other vendors. while the correct vendor distro is placed at the end. engineer is well aware of the process but unconsciously used wrong distro list. Resolution plan: Engineers need to validate the vendor and check the distro for specific vendor before sending the escalations. Additionally, PM is also advised to clean-up unnecessary distro lists, and sort all the distro keeping non-kpi distro for all the vendors on the top. | 2025-12-16 01:00:00 |  | Human Error | Loss of Trust |  | PM is advised to clean-up unnecessary distro lists, and sort all the distro keeping non-kpi distro for all the vendors on the top. | 51 | 2025 | Process Compliance | Wrong Escalation | 0.75 | Major | External | 187.5 | 🔴 REPEAT OFFENSE | 105 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 51 (1d) | False | 6.1 | 0.3
IL11609A-Coverage Strategy | 261 | STL | 3999624 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3999624/edit | Integration | Saroj Singh | 2025-12-18 00:00:00 | Minor |  | Escalations | 1 | Vasilis Skouteris |  | Internal | Amit Jaswal | Closed | Port Matrix | Integration team shared the integration update email with wrong RET naming on Gamma sector for all techs. according port matrix it should be IL11609A_C12JBL and IL11609A_C11KED but they named them IL11609A_C22JBL and IL11609A_C21KED wrongly |  | PAG caught it during Alarm monitoring and corrected the naming before sharing the 2 hrs report |  | Amit Jaswal | Human Error |  | Low |  | 51 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.99 | 🔴 High Risk (>70%) | High | 5 | 206 (0d), 237, 137 | True | 5.3 | 0.41
A6C0952A-New Build | 249 | CB | 3681581 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3681581/edit | PAG | Aishwarya Chidguppikar | 2025-12-30 00:00:00 | Major |  | Escalations | 1 | Sanal Paulose |  | Internal | BO | Closed | Nesting | Appalachian Market site nested as NSI from SI nesting during Nest extension leading to Down cell getting nested as NSI |  | There is no process gap with the engineer. She missed to identified the market and nest extended the site as NSA in Nest tool as per FCI Nest. As per Market Guidelines sites should be nested as SI only. Reiterated to the engineer the need to be more cautious during the nesting process. | 2025-12-30 12:00:00 | PAG - Day Shift | Human Error |  |  |  | 53 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.99 | 🔴 High Risk (>70%) | High | 2 | 41 (0d), 30 (0d) | False | 6.8 | 0.3
9LV4485A-New Build | 255 | LU | 3950994 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3950994/edit | PAG | Aishwarya Chidguppikar | 2025-12-30 00:00:00 | Minor |  | Escalations | 1 | Sanal Paulose |  | Internal | BO | Closed | Nesting | Appalachian market site nested as NSI from SI during nest extension |  | "There is no process gap with the engineer. She missed to identified the market and nest extended the site as NSA in Nest tool as per FCI Nest. As per Market Guidelines sites should be nested as SI only. Reiterated to the engineer the need to be more cautious during the nesting process." | 2025-12-30 12:00:00 | PAG - Day Shift | Human Error |  |  |  | 53 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.99 | 🔴 High Risk (>70%) | High | 2 | 40 (0d), 35 (0d) | True | 12.7 | 0.51
SC60288A-Coverage Strategy | 89 | SC | 3621760 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3621760/edit | PAG | Kuldeep Kumar | 2025-12-22 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | BO | Closed | Other | PAG ticket moved to Post check without Riot lemming validation |  | During validation, Its observed that PAG ticket moved to Post check without validating RIOT notes after CBN Validation Discussed with Engineer and observed that there is no process gap but miss to check the validation notes after performing CBN for respective techs. He has been advised to take preventive measure and follow the validation steps to avoid such misses. | 2025-12-23 22:00:00 | Shivam |  |  |  |  | 52 | 2025 | Nesting & Tool Errors | KPI Impact | 0.85 | Major | Internal | 50 | 🟢 Monitored | 140 | 0.32 | 🟡 Moderate (30-50%) | Medium | 2 | 175, 70 | True | 6.7 | 0.3
LA02306A-L600 | 56 | LA | 4080693 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4080693/edit | PAG | Amit Baudh | 2025-12-22 00:00:00 | Critical |  | Escalations | 1 | Shivam Srivastava |  | External | MS2 team | Closed | Other | VONR was not activated despite requested by GC over adhoc and only NRPCI was shared, which was later caught by MS2 team |  | As per Engineer VoNR was already activated on the site at that time, so he shared only the NR PCI details, although he missed to add notes and snap indicating VONR is already activated. MS2 team checked from onedata trend, related KPI was zero since audit which was performed before this incident , indicating VONR was not activated during GC adhoc. Engineer will take care of such request going forward. | 2025-12-29 22:00:00 | Shivam | Human Error |  |  |  | 52 | 2025 | Configuration & Data Mismatch | General | 0.63 | Critical | External | 375 | 🟡 POSSIBLE REPEAT | 240 | 0.85 | 🔴 High Risk (>70%) | High | 1 | 4 (69d) | False | 5.0 | 0.38
LA75200A-Replacement | 56 | LA | 3853786 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3853786/edit | Optimization | Alfred Edono | 2025-11-14 00:00:00 | Minor |  | Concerns | 1 | Alfred Edono |  | External | T-Mobile SOCAL RFE | Closed | Other | Extreme congestion, low Throughput, AFR, DCR degraded, HSI low speed complaint after site replacement On-Air | 2025-11-21 00:00:00 | Collaborated closely with TMO RFE to recommend key parameter adjustments aimed at optimizing coverage and capacity, ultimately improving AFR and DCR while enhancing downlink throughput. | 2025-11-21 00:00:00 | Amdocs MS2 RF Team | Non Amdocs |  | Low | <p>Situation Overview:</p><p>Traffic shifts significantly from decommissioned site LA83378A to Replacement site LA75200A</p><p>The replacement site is 60 ft taller than the decommissioned site, causing signal overshooting and severe congestion across all N41 1C sectors—particularly the alpha sector, which now serves over 60 users despite an MPD congestion limit of 15</p><p>Recommendation and Optimization:</p><p>These parameters were recommended and implemented: electricalAntennaTilt/digitalTilt, txPowerRario, Crsgain/Pdschtypebgain</p><p>Result:</p><p>Optimization efforts reduced active UL/DL users on N41 alpha close to the 15-user limit, yielding substantial gains in AFR, DCR, and throughput.</p> | 46 | 2025 | Configuration & Data Mismatch | General | 0.55 | Minor | External | 25 | 🆕 New Issue | 96 | 0.14 | 🟢 Low (<30%) | High | 0 |  | False | 6.8 | 0.53
9LV3286A-New Build | 255 | LU | 3498131 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3498131/edit | Integration |  | 2025-12-24 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal | PAG Team | Closed | Alarm monitoring | During 2 hours alarm monitoring PAG found External alarm 8 : AC SURGE SUPPRESSOR naming is incorrect. This naming should corrected as AC SURGE SUPPRESSOR Fail | 2025-12-24 01:00:00 | PAG raised this to IX team through Team channels and they had corrected the naming and we included the correct naming in 2 hour alarm monitoring report. | 2026-01-24 01:00:00 |  | Human Error |  |  |  | 52 | 2025 | Documentation & Reporting | General | 0.68 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 70 | 0.95 | 🔴 High Risk (>70%) | High | 2 | 53 (0d), 26 (7d) | True | 13.8 | 0.3
VG08283A-Anchor | 87 | VG | 4565684 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4565684/edit | PAG | Sakshi Pandey | 2026-01-07 00:00:00 | Major |  | Escalations | 1 | Mohit Paul |  | External | Ericsson IX team | Closed | Reporting | In the Unlock announcement email, the engineer marked VSWR as Fail and RSSI as Pass. However, on site the actual status is VSWR Pass and RSSI Fail. This discrepancy is providing incorrect information to the market & Ericsson IX team for troubleshooting the issue. | 2026-01-07 06:15:53 | Engineer copied the summary table from another Site's UA and in that table both VSWR and RSSI was fail. but in this site only RSSI issue was there so engineer mistakenly marked the RSSI as pass and kept the VSWR fail in the table, however the comment she mentioned was accurate. But because of mis-match data it was caused the conflict. engineers are advised to read the email thoroughly before sending and matching each information mentioned in it. | 2026-01-07 06:15:56 | Mohit paul | Human Error |  |  | engineers are advised to read the email thoroughly before sending and matching each information mentioned in it.<br /> | 2 | 2026 | Validation & QA | General | 0.61 | Major | External | 187.5 | 🟡 POSSIBLE REPEAT | 168 | 0.97 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.4 | 0.3
8AN0725A-Anchor | 162 | CR | 4567020 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4567020/edit | PAG | Bajrang Lal | 2026-01-06 00:00:00 | Major |  | Escalations | 1 | Gagandeep Mittal |  | Internal | QA Team | Closed | Lemming | In-complete lemming snapshot was uploaded inside the ticket while serving the request. GC requested for L7, NR6 ABC but engineer uploaded the Lemming snap for only 2 sectors and Gamma sector was missing.. | 2026-01-13 01:00:00 | Riot and Lemming passed all the given technologies and were verified live using the Riot and Lemming tool. However, while capturing the Lemming screenshot with Go full page, only 50 entries per page was enabled. As a result, the Gamma sector screenshot was not captured, leading to the missed Lemming screenshot for the Gamma sector. Resolution: Always take the snapshot with 200 entries and make sure that all the required data is available in that snapshot before uploading. | 2026-01-13 01:00:00 |  | Human Error |  |  | Always take the snapshot with 200 entries and make sure that all the required data is available in that snapshot before uploading. | 2 | 2026 | Documentation & Reporting | Incomplete Snapshot | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 35 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 54 (0d) | False | 6.5 | 0.3
SD07605A-Anchor | 172 | SD | 4080372 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4080372/edit | Optimization | Alfred Edono | 2025-12-03 00:00:00 | Minor |  | Concerns | 1 | Alfred Edono |  |  | T-Mobile SOCAL RFE | Closed | COP | DL TPUT decrease in post Cluster KPI | 2025-12-08 00:00:00 | The decrease in traffic on N6 and N19, combined with the increase on N41, leads to an overall improvement in downlink throughput NR downlink throughput exhibits a decline during the post-analysis period. At the band level, N2500 demonstrates significant pre-period traffic spikes, N600 remains relatively stable, and N1900 shows a downward trend. On 10/16, a substantial traffic surge on N2500 contributed to a temporary increase in DL throughput; however, concurrent traffic growth on N1900 and prior increases on N600 (starting 10/13) introduced load imbalance. This resulted in degraded DL throughput at the cluster level, despite band-level stability under rising traffic conditions. Beginning around 11/26, traffic volumes on N600 and N1900 decreased, while N2500 traffic ramped up, driving an overall improvement in DL throughput performance. | 2025-12-08 00:00:00 | Amdocs MS2 RF Team | Non Amdocs |  | Low | <div style="font-family:'Segoe UI';font-size:14px;line-height:20px;"><li><p><strong>Traffic Imbalance Impacts Throughput</strong><br />Sudden spikes in traffic on one band (e.g., N2500) combined with simultaneous increases on other bands (N600, N1900) can create load distribution inefficiencies, degrading overall DL throughput at the cluster level.</p></li><li><p><strong>Pre-Period Traffic Trends Are Predictive</strong><br />Early traffic increases can signal upcoming congestion issues if not managed proactively.</p></li><li><p><strong>Cluster-Level vs Band-Level Performance Divergence</strong><br />Stability at the band level does not guarantee cluster-level performance; aggregated traffic patterns across multiple bands must be monitored.</p></li><li><p><strong>Delayed Traffic Redistribution</strong><br />Improvements observed post-11/26 were due to natural traffic shifts rather than proactive optimization, indicating missed opportunities for earlier intervention.</p><p></p></li></div | 49 | 2025 | Configuration & Data Mismatch | General | 0.63 | Minor | Nan | 10 | 🟢 Monitored | 80 | 0.16 | 🟢 Low (<30%) | High | 0 |  | False | 7.1 | 0.54
SC70149A-Anchor | 89 | SC | 3966857 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/3966857/edit | Optimization | Alfred Edono | 2025-10-29 00:00:00 | Minor |  | Concerns | 2 | Alfred Edono |  |  | T-Mobile SOCAL RFE | Closed | Other | SC06651A Mobility and DCR starts to deviate when SC70149A (MS2 site) was on-aired | 2025-11-11 00:00:00 | Multiple parameter optimization actions were executed: Initial PCI Retuning: The first action involved retuning the PCI to address observed PCI confusion and collision issues on the N19 layer. However, this adjustment did not mitigate the problem. PCI and RSI Optimization per SON Recommendations: A second round of optimization was performed, including both PCI and RSI retuning based on SON-generated recommendations. This intervention also did not resolve the issue. Cell Range Expansion: In the third step, the cellRange parameter was increased across all Gamma layers associated with sector SC06651A. Following this modification, significant improvements were observed in SA handover (HO) success rate and SA drop-call rate (DCR), with performance exceeding levels recorded prior to the SC70149A on-air activation. | 2025-11-11 00:00:00 | Amdocs MS2 RF Team | Non Amdocs |  | Low | <div style="line-height:20px;"><p style="font-family:'Segoe UI';font-size:14px;">CellRange is a high‑leverage control for SA stability.</p><ul style=""><li style=""><span style="font-family:Segoe UI;"><span style="font-size:14px;">Increasing cellRange</span></span><span style="font-family:Segoe UI;"><span style="font-size:14px;"> across Gamma layers (SC06651A pointing) materially improved SA HO success and SA DCR, even outperforming the pre‑SC70149A baseline.</span></span></li><li style="font-family:'Segoe UI';font-size:14px;">Implication: For SA, especially on low‑band NR (e.g., N19), extending service boundary and clarifying serving dominance can stabilize HO decisioning and reduce ping‑pong/late HO.</li></ul></div> | 44 | 2025 | Configuration & Data Mismatch | General | 0.65 | Minor | Nan | 10 | 🆕 New Issue | 80 | 0.18 | 🟢 Low (<30%) | High | 0 |  | False | 10.3 | 0.67
9LV4105A-Coverage Strategy | 255 | LU | 4211763 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4211763/edit | Integration |  | 2026-01-13 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal |  | Closed | Alarm monitoring | During 2 Hour alarm monitoring Low band and Mid band RET naming was swapped for Alpha & Beta. | 2026-01-13 01:00:00 | RET Naming has been aligned as per config before sharing 2 hours report. | 2026-01-13 01:00:00 | IX Team |  |  |  |  | 3 | 2026 | Configuration & Data Mismatch | RET Naming | 0.95 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.94 | 🔴 High Risk (>70%) | High | 3 | 53 (0d), 26 (7d), 15 | True | 7.9 | 0.58
4NBS853A-L600 | 144 | NE | 4629963 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4629963/edit | PAG | Amit Baudh | 2026-01-14 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | BO | Closed | PostCheck | RET issue were missed to report in Post check |  | During Post check , Engineer missed to escalate RET issue which was mentioned in Post check notes. There was no Process gap, it was just missed to create and escalate. Issue is created and escalated after follow ups. | 2026-01-15 00:00:00 | Amit | Human Error |  |  |  | 3 | 2026 | Validation & QA | Missed Issue | 0.95 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 9 (1d), 25 (0d), 52 (1d) | True | 3.8 | 0.3
SD06309A-Anchor | 172 | SD | 4080335 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4080335/edit | PAG | Kuldeep Kumar | 2026-01-13 00:00:00 | Major |  | Concerns | 1 | Priya Ranjan |  | Internal | BO | Closed | PostCheck | Post check Miss- RSSI on L21 was not created and escalated | 2026-01-14 22:00:00 | During post check , RSSI on L21 was not created and escalated. Engineer mentioned that there was no process gap. He marked is to escalate in later stage but somehow missed to create and escalate. | 2026-01-14 22:00:00 | Kuldeep | Human Error |  |  |  | 3 | 2026 | Validation & QA | General | 0.75 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 140 | 0.96 | 🔴 High Risk (>70%) | High | 2 | 23 (6d), 51 (1d) | True | 5.1 | 0.3
AR01672A-Coverage Strategy | 139 | AR | 4207739 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4207739/edit | Integration |  | 2026-01-21 00:00:00 | Major |  | Concerns | 1 | Robin Soni |  | Internal | PAG Team | Closed | Alarm monitoring | During 2 hours alarm monitoring PAG found different site id in RET naming for low band ( Snapshot has been attached on RCA upload section). |  | PAG Corrected the site ID during 2 hours alarm monitoring. | 2026-01-21 10:02:00 | Abhishek Singh |  |  |  |  | 4 | 2026 | Configuration & Data Mismatch | RET Naming | 0.95 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.96 | 🔴 High Risk (>70%) | High | 4 | 50 (0d), 26 (7d), 45 (31d) | True | 7.1 | 0.54
VA21027A-Coverage Strategy | 174 | VA | 4679335 | https://www.amdocs-ti.com/tmo/projects/pag/tickets/4679335/edit | PAG | Aishwarya Chidguppikar | 2026-01-20 00:00:00 | Major |  | Concerns | 1 | Mohit Paul |  | Internal | BO | Closed | Lemming | NR25_2C_NR19_2C Gamma lemming snap is not uploaded in FCI while serving GC request. |  | There is no process gap with the engineer; however, while taking the snapshot in Lemming tool, the engineer did not capture the image properly, which resulted in the NR25_2C_NR19_2C Gamma snap being missed. Reiterated to the engineer they need to be more cautious during the RIOT/Lemming request. | 2026-01-20 12:00:00 | Priya Ranjan | Human Error |  |  |  | 4 | 2026 | Nesting & Tool Errors | General | 0.64 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 140 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 47 (7d) | False | 8.8 | 0.31
9NV1246A-Coverage Strategy | 256 |  | 3954936 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954936/edit | Integration | Surendra nehra | 2025-09-13 00:00:00 | Minor |  | Concerns | 1 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | Internal |  | Closed | Port Matrix | Incorrect Port matrix-As per Site Configuration there are 3 RET’s per sector, but as per Port matrix there are two RET’s per sector. Required updated port Matrix for RET validation |  |  | 2025-09-13 00:00:00 | INTP |  |  |  |  | 37 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.85 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 100 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 227, 293, 361 | True | 5.1 | 0.39
WI03185A-Coverage Strategy | 340 | WI | 3923052 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3923052/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan |  |  | Incorrect site schedule .Site was not schedule for support in Ti, site came for Troubleshooting for support. | [8 empty] | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 69, 57, 62 | True | 8.5 | 0.95
MW04312A-Coverage Strategy | 250 | IN | 3712182 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712182/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan | Closed |  | Site not schedule in Ti for support. Site logged in for support. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight prepetitive offenders |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Nan | 10 | 🔴 REPEAT OFFENSE | 4 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 69, 62, 56 | True | 14.9 | 0.95
OK02639A-Coverage Strategy | 192 | OK | 3673570 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673570/edit | Design | Aqsa Sayed | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan |  | Port Matrix | 3 Antenna’s model as per proposed configuration but port matrix showing 2 Ret’s on AHLOB and 3 Ret’s having NA list. Updated Port was not attached, | [8 empty] | 38 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.75 | Minor | Nan | 10 | 🔴 REPEAT OFFENSE | 100 | 0.82 | 🔴 High Risk (>70%) | High | 5 | 91, 185, 293 | True | 5.1 | 0.39
MW08132A-Coverage Strategy | 250 | IN | 3712169 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712169/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan | Closed | Scheduling | Site not part of schedule for integration, FE logged in for IX support. |  | All unscheduled integrations are being escalated to TMO |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Nan | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 123, 205, 90 | True | 14.9 | 0.95
AR01594A-Coverage Strategy | 139 | AR | 3673585 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673585/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  | Closed | Scheduling | Site not schedule for support on 9/15, FE logged in for TS support. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight prepetitive offenders |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 4 | 0.86 | 🔴 High Risk (>70%) | High | 5 | 69, 223, 86 | True | 14.9 | 0.95
OK02294A-Coverage Strategy | 192 | OK | 3712190 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712190/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan | Closed | Scheduling | site schedule 9/16, but FE logged in for IX on 9/15. |  | FE completed CX work earlier than expected, and asked for IX support. Files were ready, so IX support was given |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.7 | Minor | Nan | 10 | 🔴 REPEAT OFFENSE | 40 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 110, 289, 102 | True | 11.1 | 0.95
AR02000A-Anchor | 139 | AR | 3871746 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3871746/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan | Closed | Scheduling | Site not schedule for support in TI |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Nan | 10 | 🔴 REPEAT OFFENSE | 4 | 0.84 | 🔴 High Risk (>70%) | High | 5 | 57, 241, 242 | True | 11.7 | 0.95
9NV4615B-Coverage Strategy | 256 |  | 3950248 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3950248/edit | PM | Surendra nehra | 2025-09-15 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  |  | Nadeem khan | Closed | Scheduling | Site was schedule without microwave/Transmission ready. Site got cancelled due to site not been ready |  |  | 2025-09-17 13:30:00 | GC |  |  |  |  | 38 | 2025 | Site Readiness | General | 0.95 | Minor | Nan | 15 | 🔴 REPEAT OFFENSE | 160 | 0.87 | 🔴 High Risk (>70%) | High | 5 | 157 (0d), 287 (0d), 146 (0d) | True | 5.4 | 0.3
9LV4120A-Coverage Strategy | 255 | LU | 3873359 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873359/edit | PM | Surendra nehra | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for IX , FE on site for IX | 2025-09-16 06:30:00 |  | 2025-09-16 06:30:00 | Surendra |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 87, 173, 133 | True | 14.9 | 0.95
A5C0072A-L600 | 347 | KC | 3676966 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3676966/edit | PM | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  | Closed | CIQ | We found Mismatch in Mismatch in Spectrum sheet and CIQ,SCF. There is no N2500 C1C2 tech in RFDS |  | Design deviation are now being checked a week before the actual IX day |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Configuration & Data Mismatch | CIQ/SCF Mismatch | 0.71 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.89 | 🔴 High Risk (>70%) | High | 4 | 76 (0d), 370, 368 | False | 4.1 | 0.3
A4J1572A-Coverage Strategy | 252 | PB | 3954929 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954929/edit | PM | Surendra nehra | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site schedule for IX on 9/15, and it was not integrated on 9/15, Site not schedule for 9/16 and FE logged for IX | 2025-09-16 08:00:00 |  | 2025-09-16 08:00:00 | Surendra |  |  |  |  | 38 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 90, 205, 134 | True | 7.5 | 0.95
9LV4914A-Coverage Strategy | 255 | LU | 3955249 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955249/edit | PM | Surendra nehra | 2025-09-15 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for integration in Ti. |  |  | 2025-09-15 14:30:00 | Surendra |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 238, 81 (0d), 79 | True | 11.7 | 0.95
OK01437A-Coverage Strategy | 192 | OK | 3423497 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3423497/edit | PM | Yashpal Hans | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Incorrect Schedule Site schedule for IX on 9/15, FE logged for IX on 9/16. |  | Irrelevant escalation. IX started on 9/15, put on hold due to back haul issue, continued on 09/16 |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.85 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 40 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 61, 357 (0d), 102 | True | 8.9 | 0.95
CH12447A-L600 | 169 | CHI | 3912088 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3912088/edit | PM | Daniel Lamas | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Incorrect schedule Site not schedule in Ti for support, FE logged in requesting for support. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 57, 56, 62 | True | 8.5 | 0.95
MW08132A-Coverage Strategy | 250 | IN | 3712169 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712169/edit | PM | Yashpal Hans | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Reporting | Pay point ticket not in correct bucket. Ticket was in preliminary design for integration site. |  | wrong PM tagged | [6 empty] | 38 | 2025 | Scheduling & Planning | General | 0.7 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 245, 367, 188 | True | 7.5 | 0.95
MO05254A-Anchor | 261 | STL | 3973481 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3973481/edit | Integration | Pankaj Sharma | 2025-09-10 00:00:00 | Minor |  | Lessons learned | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | Internal | PM | Closed | Implementation | Issue was escalated to NTAC while It was communicated earlier that For Heartland we need not to reach NTAC |  | Team has been instructed again not to reach NTAC for Heartland | 2025-09-17 00:00:00 |  | Process Gap |  | Low |  | 37 | 2025 | Process Compliance | Wrong Escalation | 0.95 | Minor | Internal | 0 | 🔴 REPEAT OFFENSE | 50 | 0.91 | 🔴 High Risk (>70%) | High | 1 | 78 | False | 6.5 | 0.3
OK02680A-Coverage Strategy | 192 | OK | 3673577 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673577/edit | Field | Yashpal Hans | 2025-09-15 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | 0 | Scheduling | Site was schedule for 9/15, FE logged on 9/16 for support. Not Following the schedule | [8 empty] | 38 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 120, 86, 289 | True | 9.9 | 0.95
WI02897A-Coverage Strategy | 340 | WI | 3770794 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770794/edit | Field | Yashpal Hans | 2025-09-17 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | 0 | Scheduling | Site scedule not followed , Back hual was not ready for integration, FE logged for support. | [8 empty] | 38 | 2025 | Site Readiness | General | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 160 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 82, 100, 108 | True | 5.4 | 0.3
ML89121A-Coverage Strategy | 181 | ML | 3531108 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531108/edit | PM | Daniel Lamas | 2025-09-17 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration, FE logged in for integration. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 135, 84, 109 | True | 14.9 | 0.95
CH99167B-Coverage Strategy | 169 | CHI | 3696613 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3696613/edit | PM | Daniel Lamas | 2025-09-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE on site, Site not schedule in Ti for integration |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 112, 132, 135 | True | 11.5 | 0.95
9NV4615B-Coverage Strategy | 256 |  | 3950248 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3950248/edit | PM | Surendra nehra | 2025-09-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | CIQ | CIQ and SCF provided not matching, count of cell for N600 1C and 2C in CIQ is 7 and 4 respectively. But SCF cell is 4 and 4. |  |  | 2025-09-15 13:30:00 | INTP |  |  |  |  | 38 | 2025 | Configuration & Data Mismatch | CIQ/SCF Mismatch | 0.75 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.93 | 🔴 High Risk (>70%) | High | 2 | 65, 137 | True | 5.0 | 0.38
WI02897A-Coverage Strategy | 340 | WI | 3770794 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770794/edit | PAG | Dinesh Kumar | 2025-09-17 00:00:00 | Major |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans |  | PAG QA | Integration pre-checks released, site not ready with backhaul. It was a IX No-Go, till the backhaul acceptance is not completed in MB |  | Team can have look on to MB tasks 5025 (for AAV), 5300 (for Microwave) acceptance, MOP already shared. Else IX PM can be consulted. | [5 empty] | Team is sharing BH reediness from MB | 38 | 2025 | Site Readiness | BH Not Ready | 0.95 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 350 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 82, 180, 182 | True | 3.2 | 0.3
MW04374A-Equipment Upgrade | 250 | IN | 3884893 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3884893/edit | Integration | Nadeem Khan | 2025-09-10 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | Implementation | Issue escalated to NTAC, while it was clearly communicated that no issue should be raised to NTAC |  |  |  |  | Process Gap | Loss of Project | Low |  | 37 | 2025 | Process Compliance | Wrong Escalation | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 125 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 71 (7d) | False | 6.5 | 0.3
DE91265A-Replacement | 257 | DE | 3930006 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3930006/edit | PM | Daniel Lamas | 2025-09-18 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 81 (0d), 238, 122 | True | 11.7 | 0.95
A4L1824A-Coverage Strategy | 252 | PB | 3873441 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873441/edit | PM | Surendra nehra | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration. |  |  | 2025-09-18 08:30:00 | Surendra |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 81 (0d), 238, 122 | True | 11.7 | 0.95
CL30170A-Anchor | 251 | CL | 3873270 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873270/edit | PM | Surendra nehra | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration. |  |  | 2025-09-18 08:30:00 | Surendra |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 80 (0d), 79, 122 | True | 11.7 | 0.95
MW07332A-Coverage Strategy | 250 | IN | 3989415 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989415/edit | PM | Yashpal Hans | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  | Closed | Scheduling | Backhaul was ready but ,Site not schedule in Ti for integration , FE logged in for support. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 100, 135, 75 | True | 8.5 | 0.95
CH96151A-Coverage Strategy | 169 | CHI | 3696642 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3696642/edit | PM | Daniel Lamas | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for integration in Ti.FE logged in for IX |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 133, 135, 99 (0d) | True | 14.9 | 0.95
ML80106A-Anchor | 181 | ML | 3929974 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3929974/edit | PM | Daniel Lamas | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for integration , FE logged in for integration |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 74, 135, 334 (0d) | True | 16.1 | 0.95
MW06771A-Replacement | 250 | IN | 3673551 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673551/edit | PM | Yashpal Hans | 2025-09-18 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was ready for integration with BH , but site was not schedule for integration. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 166, 334 (0d), 160 | True | 9.9 | 0.95
TU02775C-Coverage Strategy | 421 | TU | 3999478 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999478/edit | PM | Yashpal Hans | 2025-09-18 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Scheduling issue--Site was schedule for 9/17, but FE didn't login on 9/17, Site was not schedule for 9/18, but FE logged in for integration support. |  | Schedule inaccuracy notified to TMO |  |  | Non Amdocs |  |  |  | 38 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 90, 134, 205 | True | 7.5 | 0.95
DE01656A-Coverage Strategy | 257 | DE | 3784763 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3784763/edit | PM | Daniel Lamas | 2025-09-19 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for IX in Ti |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 38 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 173, 153, 64 (0d) | True | 11.7 | 0.95
MW06749A-Coverage Strategy | 250 | IN | 3673530 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673530/edit | PM | Yashpal Hans | 2025-09-19 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration, FE logged in for IX support. Site was checked for BH readiness after FE logged and site was schedule after FE logged in with IX. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 38 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 205, 123, 133 | True | 6.2 | 0.95
AR01732A-Anchor | 139 | AR | 3999381 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999381/edit | Integration | Yashpal Hans | 2025-09-19 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Site is ahving 4*3 Confuguration with ALOHA radio , but as per physical Connection Delta is having 3 RET. and not 2 . Need updated port matrix . |  | Updated PM was shared |  |  |  |  | Low |  | 38 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 91, 185, 158 | True | 5.3 | 0.41
MW14403A-Coverage Strategy | 250 | IN | 3770762 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770762/edit | PM | Yashpal Hans | 2025-09-21 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site Schedule for integration for 9/18 , but FE didn't login for IX , Site not schedule for 9/22 but FE logged in for integration. |  | Schedule inaccuracy being highlighted to TMO |  |  | Non Amdocs |  | Low |  | 39 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 134, 86, 59 | True | 7.5 | 0.95
IL03867C-Coverage Strategy | 261 | STL | 3423481 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3423481/edit | 0 | Yashpal Hans | 2025-09-22 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | 0 | Port Matrix | Need updated port matrix.Site is having 3x3 configuration with AHLOB radio but as per Port Matrix, each sector have 2x2 RETS | [8 empty] | 39 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 185, 361, 216 | True | 4.6 | 0.33
WI03199A-Coverage Strategy | 340 | WI | 3999487 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999487/edit | PM | Yashpal Hans | 2025-09-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Material missing, AMID not available on site . Site is cancelled for integration |  | Material management not under Amdocs SoW |  |  | Non Amdocs |  | Low |  | 39 | 2025 | Site Readiness | Material Missing | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 210 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 166, 334 (0d), 144 | True | 15.2 | 0.69
ML93792A-Anchor | 181 | ML | 3748884 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3748884/edit | PM | Daniel Lamas | 2025-09-22 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration on 9/22.. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 39 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 144, 125 (0d), 133 | True | 11.5 | 0.95
AR01877A-Coverage Strategy | 139 | AR | 3712126 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712126/edit | PM | Yashpal Hans | 2025-09-23 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for integration on 9/23, Site logged in for integration and Back office supported the site. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 39 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 84, 90, 125 (0d) | True | 8.5 | 0.95
AR01877A-Coverage Strategy | 139 | AR | 3712126 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712126/edit | Integration | Abhishek Kumar (IX BO) | 2025-09-23 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | IX supported without Backhaul acceptance in MB |  | MOP already shared with team to verify BH acceptance from MB in odd hours, Integration email draft is updated to mandatory check BH status. | [6 empty] | 39 | 2025 | Process Compliance | Process Violation | 0.95 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 200 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 182, 180, 96 | True | 11.7 | 0.3
AR01877A-Coverage Strategy | 139 | AR | 3712126 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712126/edit | PAG | Raghbir Singh | 2025-09-23 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | IX pre-checks released by PAG BO without backhaul acceptance in MB |  | MOP already shared with team to verify BH acceptance status in MB. Integration pre-checks not to be shared for pending BH acceptance cases Integration email draft is updated to mandatory check BH status. | [6 empty] | 39 | 2025 | Process Compliance | Process Violation | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 200 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 182, 180, 262 | True | 16.1 | 0.3
AR01899A-Coverage Strategy | 139 | AR | 3712125 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712125/edit | Integration | IX Backoffice | 2025-09-22 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  |  |  | Closed |  | Delay in reply to GC. GC query at 09/22 1:04PM CST, Replied back to IX BO 09/22 09:14PM CST, when PM asked whether it was replied back or not. |  | Leads ascertained again to accord top priority to such specific queries. | [6 empty] | 39 | 2025 | Communication & Response | Delayed Response | 0.95 | Major | Nan | 75 | 🔴 REPEAT OFFENSE | 17.5 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 98, 286, 257 | True | 7.5 | 0.95
TU01805A-Anchor | 421 | TU | 3945120 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945120/edit | Integration | IX Backoffice | 2025-09-18 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | Delayed reply to GC. GC put query 09/17 03:26PM CST, his query replied back 09/18 07:40AM CST |  | Ascertained the fact to shift leads again to accord priority to such queries. The team has been sensitized on this, and we will ensure compliance going forward. | [6 empty] | 38 | 2025 | Communication & Response | Delayed Response | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 17.5 | 0.99 | 🔴 High Risk (>70%) | High | 5 | 97, 286, 309 | True | 8.5 | 0.95
A4J0090A-L1900 Capacity | 252 | PB | 3954926 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954926/edit | PM | Surendra nehra | 2025-09-25 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in TI for integrtaion on 9/25, FE logged in for IX. |  |  | 2025-09-25 10:00:00 | Surendra |  |  |  |  | 39 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 123, 133, 135 | True | 10.7 | 0.95
MW06754A-Coverage Strategy | 250 | IN | 3673538 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673538/edit | PM | Yashpal Hans | 2025-09-25 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was ready with Backhaul for integration, but site was not schedule TI for integration. FE joined requesting for support , Site was schedule after FE logged in with IX. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 39 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 82, 88, 99 (0d) | True | 7.5 | 0.95
MO1122BA_21-Small Cell Strategy | 244 | MON | 3768384 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3768384/edit | PAG | Poonam Hooda | 2025-09-15 00:00:00 | Minor |  | Concerns | 1 | Sachindra Mohan (Sachindra.Mohan@amdocs.com) |  | 0 |  | Investigation | Nesting | Site was not Nested during the activity even FCI was done as no Node was OA on that BTS & it was not added in Nesting tool, but TMO was asking team did activity without Nesting the site. | [8 empty] | 38 | 2025 | Nesting & Tool Errors | Missing Nesting | 0.85 | Minor | 0 | 10 | 🟡 POSSIBLE REPEAT | 60 | 0.94 | 🔴 High Risk (>70%) | High | 4 | 21 (0d), 30 (0d), 233 | True | 7.1 | 0.3
AR01663A-Coverage Strategy | 139 | AR | 3999379 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999379/edit | Field | Yashpal Hans | 2025-09-25 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | Site was schedule for 9/26 , FE logged in on 9/25 asking for IX support. | [8 empty] | 39 | 2025 | Scheduling & Planning | General | 0.69 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.96 | 🔴 High Risk (>70%) | High | 5 | 61, 59, 60 | True | 9.5 | 0.95
A5D0165A-Anchor | 347 | KC | 3332906 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3332906/edit | 0 | Yashpal Hans | 2025-09-25 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Incorrect port matrix As per the RFDS, the RET/TMAs should be connected to the AHFII radios. However in the current Port Matrix they are shown connected to the AHLOB radio. At site the RET/TMAs are correctly detected from the AHFII radios, and we have validated the RET configuration based on the site configuration. . | [8 empty] | 39 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.75 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.92 | 🔴 High Risk (>70%) | High | 2 | 158, 91 | True | 6.1 | 0.48
TMPLI1BA-Small Cell Strategy-Small Cell Strategy | 76 | NY | 4111618 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4111618/edit | Integration | Anuj | 2025-09-24 00:00:00 | Critical |  | Escalations | 3 | Rameshnaik Jarupla (Rameshnaik.Jarupla@amdocs.com) |  | Internal | Barry | Closed | Parameter Baselines | - BWP missing TMPLI1BA,TMPLI02A,TMPLI03A that caused issues on the iPhone users - At meantime the scripts are available on the COW NYTP086A, we recently integrate. - TMO corrected the scripts on all sectors TMPLI1BA,TMPLI02A,TMPLI03A | 2025-09-25 20:00:00 | - We need to find out why the scripts were not present on these sites TMPLI1BA,TMPLI02A,TMPLI03A. - If there is an issue we our scripts we need to fix it - We need to add these BWP MO are present after each integration . | 2025-09-25 20:00:00 | TMO | Human Error | Network Impact | Low | <ul style="margin-top:0in;"><li data-list="0" data-level="1" style="margin-left:0in;">We need to find out why the scripts were not present on these sites TMPLI1BA,TMPLI02A,TMPLI03A.</li><li data-list="0" data-level="1" style="margin-left:0in;">If there is an issue we our scripts we need to fix it </li><li data-list="0" data-level="1" style="margin-left:0in;">We need to add these BWP MO are present after each integration .</li></ul> | 39 | 2025 | Site Readiness | General | 0.52 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 400 | 0.88 | 🔴 High Risk (>70%) | High | 1 | 105 | False | 3.2 | 0.3
TMPLI02A-COW | 75 | LI | 4045380 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4045380/edit | Integration | Sahil/Lupita | 2025-09-26 00:00:00 | Critical |  | Escalations | 2 | Vikas Kalra (vikas.kalra@amdocs.com) |  | External_issue | TMO | Closed | Implementation | BWP Scripts were not implemented on TMPL102A/103A |  | BWP Scripts were run by TMO |  |  | Human Error |  | Low | <div><table><tbody><tr><td><span style="background:yellow;">What actions will prevent that in the short term?</span><br /><ul style="margin-top:0in;" type="disc"><li style="margin-bottom:8.0pt;line-height:105%;tab-stops:list .5in;">BWP parameter will be incorporated into the Health Check report to validate that BWP profiles are created in alignment with established guidelines. </li><li style="margin-bottom:8.0pt;line-height:105%;tab-stops:list .5in;">A verification mechanism is being developed to ensure no scripts are missed. This will include cross-checking the successful implementation of all baseline scripts.</li><li style="margin-bottom:8.0pt;line-height:105%;tab-stops:list .5in;">An audit of the BWP parameter will be conducted for all sites integrated during September 2025 to ensure compliance and identify any deviations.</li><li style="margin-bottom:8.0pt;line-height:105%;tab-stops:list .5in;">The process, guidelines, and the importance of accurate i | 39 | 2025 | Configuration & Data Mismatch | Missing Config | 0.66 | Critical | External_Issue | 150 | 🟡 POSSIBLE REPEAT | 150 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 104 (1d) | False | 6.5 | 0.51
AR01777A-Coverage Strategy | 139 | AR | 3999382 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999382/edit | PM | Yashpal Hans | 2025-09-26 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not ready with Back haul in MB FE on site requesting for support, PM didn't scedule the site in Ti as there was email approval from TMO and same was not communicated to Back office . |  | Delay in MB update by MIT. TMO released approval mail, and IX started. It should be reverse escalation, why did ix not started despite having TMO approval. Why Nadeem is expecting TI update on weekend. |  |  | Non Amdocs |  |  |  | 39 | 2025 | Site Readiness | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 82, 73, 100 | True | 8.9 | 0.49
MW11439A-Coverage Strategy | 250 | IN | 3712230 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712230/edit | Field | Yashpal Hans | 2025-09-28 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | Material (SFP ) missing on site , Precheck was shared and initial check performed on site and later it was inform by FE material is missing on site and site got cancelled, |  | Material management not under Amdocs SoW in HL |  |  | Non Amdocs |  | Low |  | 40 | 2025 | Site Readiness | Material Missing | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 210 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 234, 121, 92 | True | 4.5 | 0.3
AR01678A-Coverage Strategy | 139 | AR | 3712229 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712229/edit | Field | Yashpal Hans | 2025-09-28 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | Site not schedule in Ti for integration and BH not ready , FE on site for integration . No information of schedule from PM to FE |  | Unscheduled IX escalated to TMO. Vendor apologized on mail for the mess. RFC testing was already passed, FE checked in before BH actualized in MB. Backhaul actualized in MB after one hour, and was good to proceed with IX. |  |  | Non Amdocs |  | Low |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 112, 124, 135 | True | 7.5 | 0.95
FT01047B-Replacement | 257 | DE | 3531086 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531086/edit | PM | Daniel Lamas | 2025-09-29 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration, FE on site for integration, |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 74, 79, 80 (0d) | True | 14.9 | 0.95
AR01678A-Coverage Strategy | 139 | AR | 3712229 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712229/edit | PM | Yashpal Hans | 2025-09-30 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for 9/30, FE check-in for IX and Site was later schedule in Ti for 9/30 |  | Unscheduled IX escalated to TMO. Vendor apologized on mail for the mess. RFC testing was already passed, FE checked in before BH actualized in MB. Backhaul actualized in MB after one hour, and was good to proceed with IX. |  |  | Non Amdocs |  | Low |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 61, 357 (0d), 99 (0d) | True | 6.7 | 0.95
A4J1905A-Coverage Strategy | 252 | PB | 3955123 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955123/edit | PM | Surendra nehra | 2025-10-01 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE on site on 10/1/2025 for integration Site not schedule in Ti . |  |  | 2025-10-01 11:30:00 | Surendra |  |  |  |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 112, 75, 115 (0d) | True | 14.9 | 0.95
ML94445A-Equipment Upgrade | 181 | ML | 4115355 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4115355/edit | PM | Daniel Lamas | 2025-10-01 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE on site for Integration on 10/1/2205, Site not schedule in Ti |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 75, 111 (0d), 132 | True | 14.9 | 0.95
A4H0811A-Anchor | 252 | PB | 3750374 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3750374/edit | PM | Surendra nehra | 2025-10-02 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE logged in for Integration, site not schedule for integration on 10/2/2025 |  |  | 2025-10-02 08:30:00 | Surendra |  |  |  |  | 40 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 132, 84, 112 | True | 14.9 | 0.95
SDH0003A-Venue ACS | 172 | SD | 3990322 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3990322/edit | Field | Shrishti Singh | 2025-10-01 00:00:00 | Major |  | Concerns | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | Internal | BO | Closed | FE | Fe unable to perform CT, Site already out of MW. |  | FE (Steven) was new and this was his first site. |  |  | Process Gap | Network Impact |  |  | 40 | 2025 | Site Readiness | General | 0.69 | Major | Internal | 50 | 🟡 POSSIBLE REPEAT | 280 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 63 (2d), 316, 314 (2d) | True | 6.7 | 0.34
9LV0758A-Coverage Strategy | 255 | LU | 3792967 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3792967/edit | PM | Surendra nehra | 2025-10-02 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE logged in for integration on 10/2/2025, Site was not schedule in Ti. TI entry was completed after FE logged in for Integration |  |  | 2025-10-02 10:00:00 | Surendra |  |  |  |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 132, 135, 112 | True | 7.5 | 0.95
NY05994B-Replacement | 76 | NY | 4020978 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4020978/edit | PM | Ramesh | 2025-10-02 00:00:00 | Minor |  | Concerns | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | Internal | BO | Open | Scheduling | Site not scheduled in TI, But came for support | [8 empty] | 40 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 4 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 62, 57, 223 | True | 11.5 | 0.95
CH67348G-Anchor | 169 | CHI | 3436350 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3436350/edit | PM | Daniel Lamas | 2025-10-02 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE check-in for integration SOW on 10/2/2025, Site not schedule in Ti for IX |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 40 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 99 (0d), 111 (0d), 112 | True | 10.7 | 0.95
MW04792A-Coverage Strategy | 250 | IN | 3945116 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945116/edit | Field | Yashpal Hans | 2025-10-02 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | FE on site without site been schedule and Back hual ready. Exceptional approval received without BH been ready to support the integration. Ti schedule record updated in real time , while FE on site. | [8 empty] | 40 | 2025 | Scheduling & Planning | General | 0.85 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 112, 108, 100 | True | 6.1 | 0.95
A4H0811A-Anchor | 252 | PB | 3750374 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3750374/edit | PM | Surendra nehra | 2025-10-02 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed |  | Mismatch of SCF,.SCF provided with AVHA radio, But Site doesn't have AVHA radio installed .SCF and RFDS mismatch for radio type. |  |  | 2025-10-02 17:30:00 | Surendra |  |  |  |  | 40 | 2025 | Configuration & Data Mismatch | RFDS Mismatch | 0.85 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.92 | 🔴 High Risk (>70%) | High | 3 | 370, 387, 214 | True | 3.0 | 0.3
MO05263A-Anchor | 261 | STL | 3999460 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999460/edit | PM | Yashpal Hans | 2025-10-02 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Schedule not followed , Site schedule on 10/2 , but FE didn't checking on 10/2. Site not schedule on 10/3 and fe logged in for IX on 10/3 |  | Schedule inaccuracy being highlighted to TMO on regular basis |  |  | Non Amdocs |  | Low |  | 40 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 72, 289, 110 | True | 7.5 | 0.95
MO12704A-Coverage Strategy | 261 | STL | 3770783 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770783/edit | PM | Yashpal Hans | 2025-10-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Site Couldn't be completed due to missing material on site .Site spill over to next day |  | Material management not under Amdocs SoW in HL |  |  | Non Amdocs |  | Low |  | 40 | 2025 | Site Readiness | Material Missing | 0.63 | Major | Internal | 75 | 🟢 Monitored | 210 | 0.89 | 🔴 High Risk (>70%) | High | 3 | 107, 234, 92 | False | 5.3 | 0.3
TO01148A-Replacement | 257 | DE | 3696599 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3696599/edit | PM | Daniel Lamas | 2025-10-06 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration.. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 238, 81 (0d), 240 (0d) | True | 11.7 | 0.95
BH05982A-Coverage Strategy | 257 | DE | 3798599 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3798599/edit | PM | Yashpal Hans | 2025-10-06 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule inTi for integration for 10/6. FE logged in for IX. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 41 | 2025 | Scheduling & Planning | General | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 133, 99 (0d), 125 (0d) | True | 14.9 | 0.95
MW03602A-Coverage Strategy | 250 | IN | 3999389 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999389/edit | PM | Yashpal Hans | 2025-10-06 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for integration in Ti due to no BH readiness information from PM.FE on site for IX., Site was Schedule in Ti and BH readiness was check after FE logged for IX. |  | Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 88, 108, 99 (0d) | True | 7.1 | 0.95
A4J1458A-Anchor | 252 | PB | 3954971 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954971/edit | PM | Surendra nehra | 2025-10-07 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration for 10/7.FE logged in for Integration. |  |  | 2025-10-07 09:00:00 | Surendra |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 135, 133, 144 | True | 14.9 | 0.95
AR01899A-Coverage Strategy | 139 | AR | 3712125 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712125/edit | PAG | ABHISHEK.DUBEY25@T-Mobile.com | 2025-09-06 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | 0 | Mike Moore | Open | Implementation | PAG BO releases IX Pre-checks for site, wherein BH was not actualized in MB. |  | MOP already shared with team/leads to verify BH actualized status in MB. |  |  | Human Error | Loss of Trust | Medium |  | 36 | 2025 | Site Readiness | General | 0.95 | Critical | 0 | 150 | 🔴 REPEAT OFFENSE | 200 | 0.96 | 🔴 High Risk (>70%) | High | 5 | 262, 96, 128 | True | 8.2 | 0.45
AR01899A-Coverage Strategy | 139 | AR | 3712125 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712125/edit | Integration | srilakss@amdocs.com | 2025-09-06 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | 0 | Mike Moore | Closed | Implementation | IX BO integrated site whose BH task was yet pending to be actualized in MB. | 2025-10-15 00:00:00 | MOP already shared with team to check BH acceptance status in MB over weekend and off hours. |  |  | Human Error | Loss of Trust | Medium | Check the BH readiness in MB and share the screenshot of BH readiness to start the site IX | 36 | 2025 | Site Readiness | General | 0.65 | Critical | 0 | 150 | 🟡 POSSIBLE REPEAT | 400 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 128, 181, 329 | True | 6.9 | 0.36
MO14427A-Coverage Strategy | 261 | STL | 3673561 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673561/edit | PAG | Amit.Jaswal4@T-Mobile.com | 2025-10-06 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | Implementation | IX pre-checks releases for site, whose BH acceptance was pending actualization in MB. | 2025-10-15 00:00:00 | MOP already shared with team how to check latest BH task actualized status in MB |  |  | Human Error | Loss of Trust |  |  | 41 | 2025 | Site Readiness | General | 0.75 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 400 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 37 (0d), 11 (0d), 262 | False | 8.9 | 0.48
AR01872A-Coverage Strategy | 139 | AR | 3712166 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712166/edit | Integration | IX Backoffice | 2025-10-06 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | External_issue | TMO Subcon Mercury | Closed | Implementation | IX support was denied, despite BH status reflected actualized/accepted in MB. However, PAG BO actively checked it, and having a look in MB, released IX pre-checks. IX BO dint support, just by citing the reason, TI record was not updated. Team could have reached out to PM on his phone to have clarification. It could have been avoided with a simple call. | 2025-10-15 00:00:00 | Shift leads/Manger ascertained the fact again. IX team will check with PM going forward to check such cases. |  |  | Process Gap | Loss of Trust |  |  | 41 | 2025 | Site Readiness | BH Status Issue | 0.61 | Critical | External_Issue | 150 | 🟡 POSSIBLE REPEAT | 250 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 371, 326, 37 (0d) | True | 3.8 | 0.3
MO05851A-Replacement | 261 | STL | 3712227 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712227/edit | Integration | IX Backoffice | 2025-10-04 00:00:00 | Major |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | FE waited for 3hrs to get EOD reports. FE mentioned the delay on mail while TMO in loop. | 2025-10-15 00:00:00 | Ascertained the fact again to shift leads/manager to pay special attention towards such delays. The team has been sensitized on this, and we will ensure compliance going forward. | 2025-10-15 00:00:00 |  | Human Error | Loss of Trust |  |  | 40 | 2025 | Communication & Response | Delayed Deliverable | 0.75 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 35 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 131 | False | 7.3 | 0.95
IL11610A-Coverage Strategy | 261 | STL | 3858471 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858471/edit | Integration | IX Backoffice | 2025-09-12 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | FE waiting for 4hrs to get EOD report | 2025-10-15 00:00:00 | The team has been sensitized on this, and we will ensure compliance going forward. |  |  |  | Loss of Trust |  |  | 37 | 2025 | Communication & Response | Delayed Deliverable | 0.64 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 35 | 0.97 | 🔴 High Risk (>70%) | High | 3 | 130 (11d), 264, 257 | True | 15.2 | 0.95
ML89115A-Coverage Strategy | 181 | ML | 3436339 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3436339/edit | PM | Daniel Lamas | 2025-10-07 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE logged in for integration on 10/8, Site not schedule in Ti . |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 135, 125 (0d), 115 (0d) | True | 14.9 | 0.95
GS02316A-Coverage Strategy | 257 | DE | 3784766 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3784766/edit | PM | Daniel Lamas | 2025-10-08 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration on 10/8 , FE logged in for IX. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 4 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 123, 99 (0d), 135 | True | 9.2 | 0.95
MO01397C-L600 | 261 | STL | 3999457 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999457/edit | PM | Yashpal Hans | 2025-10-08 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | SIte scedule for IX on 10/7, FE didnt log in for integation. SIte didn't schedule for Integration 10/8 and FE logged in for IX . |  | Schedule inaccuracy highlighted to TMO on regular basis |  |  | Non Amdocs |  | Low |  | 41 | 2025 | Scheduling & Planning | General | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 90, 123, 66 (0d) | True | 7.2 | 0.95
CH17306A-Anchor | 169 | CHI | 3989100 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989100/edit | PM | Daniel Lamas | 2025-10-09 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration , FE logged in for integration on 10/9. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 125 (0d), 133, 132 | True | 9.2 | 0.95
AR01999A-Replacement | 139 | AR | 3332940 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3332940/edit | Design | Aqsa Sayed | 2025-10-09 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open |  | RIOT was red on L700¦L1900¦L2100¦L600 - ABGD due to TAC mismatch between SCF and RIOT tool.Tool tool RF config was not set with correct TAC as 45952 | [8 empty] | 41 | 2025 | Configuration & Data Mismatch | TAC Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 247, 174, 373 | True | 5.3 | 0.41
MW15807A-Coverage Strategy | 250 | IN | 3673598 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673598/edit | Integration | Maria | 2025-10-10 00:00:00 | Minor |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | SCF | Cell naming was incorrect in SCF for N600 C2 – Gamma. Corrected during integration | [8 empty] | 41 | 2025 | Configuration & Data Mismatch | General | 0.77 | Minor | Internal | 10 | 🟡 POSSIBLE REPEAT | 80 | 0.84 | 🔴 High Risk (>70%) | High | 3 | 39, 76 (0d), 206 (0d) | True | 5.2 | 0.4
AR01769A-Coverage Strategy | 139 | AR | 3712165 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712165/edit | PM | Yashpal Hans | 2025-10-10 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in No-Go list for integration, and BH was not ready in MB,FE reach on site and started the RFC test and BH ready. |  | this is the usual process, a day before the actual IX date, site may be IX no-go, on the actual IX day, FE will complete the RFC testing, and once BH will appear actualize in MB, we are good to extend IX support. Site was scheduled in TI once FE confirmed BH actualized in MB. Prior to 10/25/2025, IX schedule were only updated after BH will appear actualized in MB. Else site won't be scheduled in TI. |  |  | Non Amdocs |  | Low |  | 41 | 2025 | Site Readiness | BH Not Ready | 0.95 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 200 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 168, 161, 160 | True | 4.0 | 0.3
A5S0133A-Coverage Strategy | 347 | KC | 3393318 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3393318/edit | PM | Yashpal Hans | 2025-10-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | BH was ready on 10/3 , but site was not schedule in Ti for Integration to perform on 10/10. Ti entry for schedule is missing. |  | happened while IX PM was on PTO, somebody else was taking care of other important issues in absence of IX PM |  |  |  |  | Low |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 140, 144, 124 | True | 7.5 | 0.95
A5C0702A-Coverage Strategy | 347 | KC | 3712157 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712157/edit | PM | Yashpal Hans | 2025-10-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | BH was ready on 10/8 for integration , site was not schedule for Integration in TI TI entry missing , team started the support. |  | happened while IX PM was on PTO, somebody else was taking care of other important issues in absence of IX PM |  |  |  |  | Low |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 139, 124, 144 | True | 7.5 | 0.95
A6C0157A-Anchor | 467 | CB | 4139124 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4139124/edit | PM | Surendra nehra | 2025-10-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ti entry missing ,. IX Schedule date missing , site started for IX on 10/10 |  |  | 2025-10-10 11:00:00 | Surendra |  |  |  |  | 41 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 153, 173, 87 | True | 9.2 | 0.95
AR02233A-Coverage Strategy | 139 | AR | 3770757 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770757/edit | PM | Yashpal Hans | 2025-10-11 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Incorrect Schedule. Site Schedule for integration 10/8, FE logged for integration on 10/11 |  | Schedule inaccuracy being highlighted to TMO in routine |  |  | Non Amdocs |  | Low |  | 41 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 113 (0d), 112, 90 | True | 9.2 | 0.95
AR01775B-Coverage Strategy | 139 | AR | 4040246 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040246/edit | PM | Yashpal Hans | 2025-10-11 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ti not updated with IX schedule for 10/11. |  | happened while IX PM was on PTO, somebody else was taking care of other important issues in absence of IX PM | [6 empty] | 41 | 2025 | Scheduling & Planning | General | 0.71 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 87, 153, 141 (0d) | True | 10.2 | 0.95
MW13141A-Coverage Strategy | 250 | IN | 3788494 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3788494/edit | PM | Yashpal Hans | 2025-10-13 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for integration for 10/13 .schedule missing in Ti . |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 42 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 125 (0d), 232 (0d), 93 | True | 14.9 | 0.95
CH89357A-Coverage Strategy | 169 | CHI | 3531100 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531100/edit | PM | Daniel Lamas | 2025-10-12 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site schedule missing in Ti.. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 42 | 2025 | Scheduling & Planning | No TI Entry | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 147, 122, 241 | True | 10.4 | 0.95
CL56097A-Replacement | 251 | CL | 3750344 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3750344/edit | PM | Surendra nehra | 2025-10-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Microwave link was not ready and site was schedule for Integration., site could not be completed because of MW readiness issue. |  |  | 2025-10-13 14:30:00 | Surendra |  |  |  |  | 42 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 314 (2d), 287 (0d), 217 (0d) | True | 7.5 | 0.95
BS02755C-Coverage Strategy | 257 | DE | 3930016 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3930016/edit | PM | Daniel Lamas | 2025-10-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site schedule missing in Ti. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 42 | 2025 | Scheduling & Planning | No TI Entry | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 145, 150, 122 | True | 10.4 | 0.95
9NV4617A-Coverage Strategy | 256 |  | 3873393 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873393/edit | PM | Surendra nehra | 2025-10-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was schedule for integration , back haul was not ready. After multiple troubleshooting and multiple checks site was cancelled and , Incident ticket (INC120531243 ) open by FE to check BH readiness. | 2025-10-29 00:00:00 | BH restored by IRIS(BH vendor) | 2025-10-29 00:00:00 | TMO | Non Amdocs |  |  |  | 42 | 2025 | Site Readiness | BH Check Error | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 82, 100, 77 | True | 10.1 | 0.54
AR01896A-Coverage Strategy | 139 | AR | 3945115 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945115/edit | Integration | Yashpal Hans | 2025-10-12 00:00:00 | Critical |  | Escalations | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | External_issue | TMO | Closed | Implementation | The RET was set to maximum tilt for RTWP issue verification. During reversion, a “RET Antenna control failure” alarm was encountered on beta, preventing tilt rollback. Despite multiple troubleshooting attempts, the alarm persisted, indicating a hardware fault. Support engineer informed FE and FE confirmed via email that the antenna will be replaced. Alpha and Gamma tilt were not reverted, even though no alarms were present on those RETs. |  | Tilts were reverted by TMO RF | 2025-10-14 00:00:00 |  | Human Error |  | Medium | <div><table><tbody><tr><td><span style="font-family:Symbol;">·<span style="font-variant-numeric:normal;font-variant-east-asian:normal;font-variant-alternates:normal;font-kerning:auto;font-optical-sizing:auto;font-feature-settings:normal;font-variation-settings:normal;font-variant-position:normal;font-variant-emoji:normal;font-size:7pt;line-height:normal;font-family:'Times New Roman';"> </span></span>Anomaly detection is now mandatory for all activities. <br /><span style="font-family:Symbol;">·<span style="font-variant-numeric:normal;font-variant-east-asian:normal;font-variant-alternates:normal;font-kerning:auto;font-optical-sizing:auto;font-feature-settings:normal;font-variation-settings:normal;font-variant-position:normal;font-variant-emoji:normal;font-size:7pt;line-height:normal;font-family:'Times New Roman';"> </span></span>Email templates have been updated to include screenshot evidence of anomaly detection.<br /><span style="font-family:Symbol;">·<span style="font-v | 42 | 2025 | Validation & QA | No Reversion | 0.44 | Critical | External_Issue | 150 | 🆕 New Issue | 100 | 0.27 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.6 | 0.3
OK02220B-Coverage Strategy | 192 | OK | 3770774 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770774/edit | PM | Yashpal Hans | 2025-10-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site Schedule date missing in TI. |  | happened while IX PM was on PTO, somebody else was taking care of other important issues in absence of IX PM |  |  |  |  | Low |  | 42 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.72 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 147, 145, 244 | True | 10.2 | 0.95
SE0036BA_41-Small cell strategy - N41 upgrade | 189 | SE | 3750805 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3750805/edit | Integration | IX team | 2025-10-15 00:00:00 | Major |  | Escalations | 1 | DEEPAK VERMA (Deepak.Verma2@amdocs.com) |  | Internal | Deepak Verma | Closed | BO Support Delays | IX team did Audit after 5days and sector went down, Requested for GC support for HW issue, but main concern is the delay in Audit |  | The team has been sensitized on this, and we will ensure compliance going forward. | [6 empty] | 42 | 2025 | Site Readiness | General | 0.6 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 280 | 0.96 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.0 | 0.3
ML89043A-Coverage Strategy | 181 | ML | 3696637 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3696637/edit | PM | Daniel Lamas | 2025-10-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Integration Schedule date missing in Ti |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 42 | 2025 | Scheduling & Planning | General | 0.72 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 147, 145, 122 | True | 10.2 | 0.95
BS01178A-Coverage Strategy | 257 | DE | 3748918 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3748918/edit | PM | Daniel Lamas | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site IX schedule missing in Ti. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 42 | 2025 | Scheduling & Planning | No TI Entry | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 173, 87, 64 (0d) | True | 10.4 | 0.95
MW07238A-Equipment Upgrade | 250 | IN | 3958682 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3958682/edit | Design | Yashpal Hans | 2025-10-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | E911 readiness | At the time of CIQ creation, the MB TAC was 42236. Now it has been updated to 42111 TAC 42236 was not updated in MB and RIOT tool causing RIOT red issue . |  | Design pre-checks now being validated a week before the actual IX day |  |  | Non Amdocs |  | Low |  | 42 | 2025 | Nesting & Tool Errors | General | 0.95 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.86 | 🔴 High Risk (>70%) | High | 3 | 136, 247, 372 | False | 5.4 | 0.3
MW07205B-Anchor | 250 | IN | 3989412 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989412/edit | PM | Yashpal Hans | 2025-10-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Site was integrated with GSM as per RFDS and CIQ on 10/8, Site came for TS and was found GSM deleted by TMO . Again SCF was revised and integrated with GSM increasing effort and integration of site. |  | this was one odd case, TMO design & Dev was notified in biweekly executive call about the additional efforts done by Amdocs |  |  | Non Amdocs |  | Low |  | 42 | 2025 | Configuration & Data Mismatch | RFDS Mismatch | 0.6 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.86 | 🔴 High Risk (>70%) | High | 2 | 172, 311 | True | 3.8 | 0.3
MW07205B-Anchor | 250 | IN | 3989412 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989412/edit | Field | Yashpal Hans | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | Delay field work due to non-availability of GC on site, Precheck was shared. And GC not available on site . Delay of 2.5 hr in field after precheck. |  | escalated to TMO/vendor |  |  | Non Amdocs |  | Low |  | 42 | 2025 | Communication & Response | General | 0.58 | Major | Internal | 75 | 🟢 Monitored | 70 | 0.35 | 🟡 Moderate (30-50%) | Medium | 0 |  | False | 4.5 | 0.95
A4J1662A-Coverage Strategy | 252 | PB | 3873431 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873431/edit | PM | Surendra nehra | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Microwave path was not ready for site integration, Site got cancelled after precheck and initial check by back office. |  |  | 2025-10-16 20:00:00 | Surendra |  |  |  |  | 42 | 2025 | Site Readiness | General | 0.72 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 63 (2d), 217 (0d), 146 (0d) | True | 3.1 | 0.3
TU01819A-L600 | 421 | TU | 3999475 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999475/edit | Design | Aqsa Sayed | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | As port matrix 2 RETs need to be detected on each AHLOA, but on site 3 RETs are detected for each radio | [8 empty] | 42 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.63 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 91, 185, 355 | True | 3.5 | 0.3
MW07357B-Anchor | 250 | IN | 3999403 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999403/edit | PM | Yashpal Hans | 2025-10-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for IX , But FE on site for IX .While FE on site PM requested for Revision of script adding to delay in support , |  | PM remarks: Unschduled IX by Nokia escalated to TMO same day. TMO has cognizance of the matter. IX BO team was asked to standby as we cannot go ahead with unscheduled IX without completing design pre-check validations. |  |  | Non Amdocs |  | Low |  | 42 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 357 (0d), 102, 120 | True | 7.5 | 0.95
MW12411A-Coverage Strategy | 250 | IN | 3673612 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673612/edit | Field | Yashpal Hans | 2025-10-21 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | FE | BH is not ready but FE on site for integration. | [8 empty] | 43 | 2025 | Scheduling & Planning | No TI Entry | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 161, 168, 85 | True | 10.0 | 0.95
IL17501B-Coverage Strategy | 261 | STL | 3770780 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770780/edit | Field | Yashpal Hans | 2025-10-21 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | FE | BH not ready , But FE on site for integration | [8 empty] | 43 | 2025 | Scheduling & Planning | No TI Entry | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.96 | 🔴 High Risk (>70%) | High | 5 | 160, 168, 85 | True | 10.0 | 0.95
DAY1F01A-Venue ACS NSD | 95 | DA | 3334862 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3334862/edit | PM | Yogiraj Jhala | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Site was integrated initially with N2500 C2 , Site LCR alarm and PM requested BO to delete the N2550 C2 to clear the alarm. on 10/17/2025 PM again requesting to add the N2500 C2 and asking BO why N2500 C2 was deleted,. Such issue or no clarity on PM side resulted in rework on site (SCF prep and IX work). | 2025-10-20 00:00:00 | With N2500C2 was original plan in 2024 with X PM, X PM with then TMO leadership deleted N2500C2 to resolve the LCR alarm. 2025 PM Y Joined go the site back to integrate N2500 C2 and seeked IX BO assistance on historic emails/ udpates on why the N2500C2 was not integrated, guess PM Y needs to re structure the ask which should sound more like info request then WHY, Also to note that There was quite a bit of gap between PM X and PM Y so PM Y relies on the Integration team to aprise them of historic data that is so much embedded in TI that it may not be well understood at time and PM Y seeks more clarity. | 2025-10-20 00:00:00 | YogirajRaj Jhala | Process Gap |  | Low | Lessons Learned: PM Y ( new PM) and PM leads to get on seprate emails to gather historic data that lead to current situation and understand eachother ask which should not sound like Questioning rather info query. | 42 | 2025 | Scheduling & Planning | General | 0.55 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 311 | False | 5.0 | 0.95
9LV4135A-Coverage Strategy | 255 | LU | 3955066 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955066/edit | PM | Surendra nehra | 2025-10-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | SIte schedule for Integration but iNTP still not completed .FE waiting on site. |  |  | 2025-10-22 09:30:00 | Surendra |  |  |  |  | 43 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.7 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 112, 125 (0d), 135 | True | 9.7 | 0.95
BA00363A-Cabinet Consolidation | 88 | SF | 4115707 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4115707/edit | Field | Ejaz Mehmood | 2025-10-15 00:00:00 | Minor |  | Lessons learned | 1 | Kevin Pelletier (kevinpe@amdocs.com) | Celnet | Internal |  | Closed |  | Crew identified that site was in the middle of a microwave chain and the downstream sites didn't have CRs and couldn't be Nested. Additionally, the site had a generator that they were unaware of, and didn't have time to retrieve necessary conduit to extend to the 6160 cabinet. The site had to be aborted and revisited later. |  | 1) PM is now pulling all active Technologies for the sites so that backhaul type, bands, etc. are identified during planning, and the proper CRs in place, 2) SubCon will be walking sites 1 week in advance to identify sites that have non-standard Construction guidelines where they can plan for needed equipment ahead of time. | 2025-10-25 22:00:00 | Project Team | Process Gap | Loss of Trust | Low |  | 42 | 2025 | Nesting & Tool Errors | General | 0.95 | Minor | Internal | 0 | 🟢 Monitored | 80 | 0.31 | 🟡 Moderate (30-50%) | Medium | 4 | 63 (2d), 146 (0d), 287 (0d) | True | 7.8 | 0.3
TU01043G-Equipment Upgrade | 421 | TU | 4215634 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4215634/edit | PM | Yashpal Hans | 2025-10-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not plan for integration and PM didnt create ticket in Ti .Created ticket when asked on team channel |  | It was an adhoc requirement from TMO |  |  | Non Amdocs |  | Low |  | 43 | 2025 | Scheduling & Planning | General | 0.76 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 330, 232 (0d), 135 | True | 5.6 | 0.95
CH89304A-Coverage Strategy | 169 | CHI | 3187771 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3187771/edit | PM | Daniel Lamas | 2025-10-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site BH was not ready and Site was planned for Integration, Site Couldn't get integration due to non-reediness of BH. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 43 | 2025 | Site Readiness | BH Not Ready | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 350 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 85, 334 (0d), 94 | True | 3.2 | 0.3
AR01770A-Coverage Strategy | 139 | AR | 3712224 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712224/edit | PM | Yashpal Hans | 2025-10-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Missing material. The ISP for backhaul did not install an SFP in the Ciena. Site couldn't be integrated . |  | Material management not under Amdocs SoW in HL |  |  | Non Amdocs |  | Low |  | 43 | 2025 | Site Readiness | Material Missing | 0.63 | Major | Internal | 75 | 🟢 Monitored | 210 | 0.85 | 🔴 High Risk (>70%) | High | 5 | 82, 77, 190 | True | 16.7 | 0.71
MO12447A-Coverage Strategy | 261 | STL | 3531048 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531048/edit | PM | Yashpal Hans | 2025-10-23 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | BH readiness pending on site , but FE on site for Integration. |  | IX schedule inaccuracy highlighted to TMO |  |  | Non Amdocs |  | Low |  | 43 | 2025 | Scheduling & Planning | No TI Entry | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.87 | 🔴 High Risk (>70%) | High | 5 | 160, 161, 85 | True | 9.6 | 0.95
A5S0160A-Coverage Strategy | 347 | KC | 3712259 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712259/edit | Design | Aqsa Sayed | 2025-10-23 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Tilt mention in port matrix is different than RFDS . | [8 empty] | 43 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.7 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 197, 187, 218 | True | 8.3 | 0.6
CI15183A-Anchor | 248 | CI | 3873259 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873259/edit | Field | Surendra nehra | 2025-10-22 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | Site was shut down before it can be locked before integration start. |  | Generally GC install or upgrade the eqpt before logging with Ix on site Mods. TMO was aware of this and allowed GC. | 2025-10-22 14:30:00 | [5 empty] | 43 | 2025 | Scheduling & Planning | General | 0.66 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.93 | 🔴 High Risk (>70%) | High | 4 | 171, 166, 84 | True | 6.7 | 0.95
A5C0103A-Anchor | 347 | KC | 3999413 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999413/edit | Field | Yashpal Hans | 2025-10-22 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | FE | Site was shut down before cell could be locked | [8 empty] | 43 | 2025 | Site Readiness | Site Down | 0.72 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 160 | 0.94 | 🔴 High Risk (>70%) | High | 3 | 170 (0d), 295, 1 (0d) | True | 4.5 | 0.3
TU01043G-Equipment Upgrade | 421 | TU | 4215634 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4215634/edit | PM | Yashpal Hans | 2025-10-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | As per RFDS & SCF we have the GSM both Exciting and proposed tech but there is no GSM in BSC also its not showing in monitor. During Integration it was requested to get SCF revised without GSM , which resulted in SCF and IX rework. |  | Yes, it was a mess, being last minute request asking for support from Amdocs, and we couldn't deny. |  |  | Non Amdocs |  |  |  | 43 | 2025 | Configuration & Data Mismatch | RFDS Mismatch | 0.6 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.87 | 🔴 High Risk (>70%) | High | 1 | 155 | False | 4.3 | 0.3
OK01827A-Coverage Strategy | 192 | OK | 3858491 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858491/edit | PM | Yashpal Hans | 2025-10-23 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site schedule missing in Ti for IX. |  | Notified to TMO |  |  | Non Amdocs |  | Low |  | 43 | 2025 | Scheduling & Planning | No TI Entry | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 153, 87, 64 (0d) | True | 10.4 | 0.95
A5L0066A-Coverage Strategy | 347 | KC | 3673558 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673558/edit | Design | Aqsa Sayed | 2025-10-24 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | E911 readiness | Site A5L0066A is having Riot red for all LTE Tech .TAC showing mismatched both RF Config and OSS part | [8 empty] | 43 | 2025 | Configuration & Data Mismatch | TAC Mismatch | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 373, 372, 247 | False | 4.6 | 0.33
TU01043G-Equipment Upgrade | 421 | TU | 4215634 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4215634/edit | PM | Yashpal Hans | 2025-10-24 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | KPI Monitoring | PAG ticket is not created for the site to move the ticket for 48 PAG monitoring. |  | Yes, it was a mess, being last minute request asking for support from Amdocs, and we couldn't deny. |  |  | Non Amdocs |  | Low |  | 43 | 2025 | Scheduling & Planning | General | 0.55 | Minor | Internal | 15 | 🟢 Monitored | 4 | 0.78 | 🔴 High Risk (>70%) | Medium | 4 | 42 (1d), 235, 245 | True | 8.3 | 0.95
MW03604A-Coverage Strategy | 250 | IN | 3712129 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712129/edit | Integration | Vikas Singh | 2025-10-24 00:00:00 | Minor |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Different site ID (A5C0103A) in mail body in E911 Go mail |  | Guidance to team to be more cautious while drafting E911 circulations |  |  | Human Error | Loss of Revenue |  |  | 43 | 2025 | Documentation & Reporting | Wrong Site ID | 0.85 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 40 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 263, 178, 177 | True | 11.0 | 0.3
MW03604A-Coverage Strategy | 250 | IN | 3712129 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712129/edit | Integration | Vikas Singh | 2025-10-24 00:00:00 | Minor |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Different mail ID (A5C0103A) in mail body while E911 Completion mail was sent |  | Guidance to team to be more cautious while sending out E911 circulations. |  |  | Human Error | Loss of Trust | Medium |  | 43 | 2025 | Documentation & Reporting | Wrong Site ID | 0.7 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 40 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 263, 381, 176 | True | 9.7 | 0.3
TU01819A-L600 | 421 | TU | 3999475 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999475/edit | Integration | Pankaj Sharma | 2025-10-16 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Site ID missing in subject line, while E911 Go mail was sent |  | Guidance to team to be more cautious while drafting E911 circulations Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 42 | 2025 | Documentation & Reporting | Wrong Site ID | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 40 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 176, 259, 263 | True | 14.9 | 0.3
MW14344A-Coverage Strategy | 250 | IN | 3945117 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945117/edit | Integration | Maharaja MM | 2025-10-21 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | Wrong summary table in E911 complete mail |  | Requested team to be more cautious while drafting E911 notifications. The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Human Error | Loss of Trust | Medium |  | 43 | 2025 | Documentation & Reporting | General | 0.85 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 40 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 381, 283, 304 | True | 10.4 | 0.3
AR01770A-Coverage Strategy | 139 | AR | 3712224 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712224/edit | PAG | Vangelis Dardoumas | 2025-10-20 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Investigation | Implementation | IX pre-checks released without backhaul actualized in MB |  | Additional fields added in IX Schedule Record in TI |  |  | Human Error | Loss of Trust | Medium |  | 43 | 2025 | Process Compliance | Process Violation | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 200 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 96, 95, 11 (0d) | True | 13.3 | 0.3
MW07357B-Anchor | 250 | IN | 3999403 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999403/edit | Integration | Kashish Kalia | 2025-10-16 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | Implementation | Integration support initiated by IX BO, without BH actualized in MB |  | Additional field added in IX Schedule record in TI to avoid these ambiguities |  |  | Human Error | Loss of Trust | Medium |  | 42 | 2025 | Process Compliance | General | 0.95 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 200 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 11 (0d), 127, 83 | True | 16.1 | 0.3
MW07357B-Anchor | 250 | IN | 3999403 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999403/edit | PAG | Amit Jaswal | 2025-10-16 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Investigation | Implementation | IX pre-checks released without backhaul actualized in MB |  | additional field added in IX Schedule record to avoid such mistakes |  |  | Human Error | Loss of Trust |  |  | 42 | 2025 | Process Compliance | Process Violation | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 200 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 96, 95, 11 (0d) | True | 13.3 | 0.3
OK01825A-Coverage Strategy | 192 | OK | 3999443 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999443/edit | Integration | Nadeem Khan | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | E911 completion mail circulated, without sending E911 Go mail |  | Leads/Managers requested to guide team to avoid such misses Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 42 | 2025 | Documentation & Reporting | Process Skip | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 381, 177, 178 | True | 9.8 | 0.3
A5S0160A-Coverage Strategy | 347 | KC | 3712259 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712259/edit | Integration | Nadeem Khan | 2025-10-24 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | 5 reminder mails sent to maintain uniformity in E911 circulations, but still not taken care |  | 5th request placed with Manager/Leads to take care of such mistakes. Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 43 | 2025 | Documentation & Reporting | General | 0.62 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 183, 178, 177 | True | 7.8 | 0.3
IL11711A-Coverage Strategy | 261 | STL | 3711631 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711631/edit | Design | Aqsa Sayed | 2025-10-24 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Port matrix mismatch .As per current antenna configuration 3 RET’s detected but in current port matrix Only 2 RET’s showing | [8 empty] | 43 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 160 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 361, 355, 91 | True | 4.6 | 0.33
A4J1636A-Coverage Strategy | 252 | PB | 3954985 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954985/edit | Integration | Surendra Nehara | 2025-10-27 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | Internal | Surendra Nehara | Closed | Implementation | IX EOD released with no issues, but RTT wasn't released. It was released later after internal escalation | 2025-10-27 01:00:00 |  | 2025-10-27 01:00:00 | Ravikanth | Process Gap |  | Low |  | 44 | 2025 | Scheduling & Planning | General | 0.67 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.94 | 🔴 High Risk (>70%) | High | 3 | 394 (1d), 338 (1d), 250 (1d) | True | 6.0 | 0.95
MW11442A-Coverage Strategy | 250 | IN | 3768537 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3768537/edit | PM | Yashpal Hans | 2025-10-27 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  | Closed | Port Matrix | RET validation pending due to Port matrix not available In TI |  | Design details/sheets being verified a week before actual IX day now |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.73 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 272 (0d), 215, 197 | True | 9.2 | 0.64
MW04374A-Equipment Upgrade | 250 | IN | 3884893 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3884893/edit | PM | Yashpal Hans | 2025-10-28 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ticket is in closeout bucket and ticket not moved to Troubleshooting for support and site was not scheduling for troubleshooting |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 282, 271, 211 | True | 6.7 | 0.95
MW04374A-Equipment Upgrade | 250 | IN | 3884893 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3884893/edit | Integration | Jeschel | 2025-10-27 00:00:00 | Major |  | Escalations | 1 | Venkata Tula (TULAV@amdocs.com) |  | Internal |  | Open | Reporting | Observed that the team is using AEHC swap report to determine that there is no swap no site; Kindly keep in mind that this Report Does Not Recognize Physical Swap on site. This tool will only flag swap issue using Radio serial numbers and does not verify physical sector swaps or fiber swaps. This site has physical sector swap, identified during SSV drive, but team utilized below tool and informed GC that there is no swap. If GC arrives at site to correct swap sectors, then please guide the team to physically check reported sectors for plumbing issues. ----Did the support team ask GC to check the reported sectors for swap? (N600 - Beta and Gamma - email attached) | [8 empty] | 44 | 2025 | Configuration & Data Mismatch | General | 0.52 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.27 | 🟢 Low (<30%) | Medium | 0 |  | False | 5.2 | 0.4
OK01546A-Coverage Strategy | 192 | OK | 3999437 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999437/edit | PM | Yashpal Hans | 2025-10-30 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE logged in for NSD IX. But Backhaul is not ready |  | There was MIT acceptance already on mail, but it took time same to reflect in MB. IX started, moment BH appeared actualized in MB |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Site Readiness | General | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 280 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 82, 77, 100 | True | 14.0 | 0.66
IL11610A-Coverage Strategy | 261 | STL | 3858471 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858471/edit | PM | Yashpal Hans | 2025-10-30 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | GC logged in for TSH. But IX Ticket is in Close -out . Site not schedule for troubleshooting in Ti . |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 213, 270, 271 | True | 6.7 | 0.95
MW03582A-Coverage Strategy | 250 | IN | 3858489 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858489/edit | Design | Design Team | 2025-10-16 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | CIQ | For site MW03582A, phyCellId for Lncell-1 and 2 are same which is causing error in SCF, |  |  | 2025-10-16 17:00:00 | [5 empty] | 42 | 2025 | Configuration & Data Mismatch | General | 0.58 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.9 | 🔴 High Risk (>70%) | High | 0 |  | False | 9.2 | 0.64
AU03339B-Coverage Strategy | 176 | AU | 3989143 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989143/edit | Design | IP CIQ Team | 2025-10-23 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | For site AU03339B, One-T is not yet updated result in missing IP’s in current IP CIQ, |  | no ETA provided | [6 empty] | 43 | 2025 | Configuration & Data Mismatch | One-T Mismatch | 0.57 | Major | Internal | 75 | 🟢 Monitored | 105 | 0.26 | 🟢 Low (<30%) | Medium | 0 |  | False | 9.2 | 0.64
AR02051B-Coverage Strategy | 139 | AR | 3770753 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770753/edit | Design | IP CIQ Team | 2025-10-30 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | For site AR02051B, as per the RFDS, the site configuration is listed as eSRAN, whereas in One-T it is currently shown as non-SRAN. |  | no ETA provided | [6 empty] | 44 | 2025 | Configuration & Data Mismatch | One-T Mismatch | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 196 | False | 7.0 | 0.54
MW08201A-Coverage Strategy | 250 | IN | 3531058 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531058/edit | Design | PMX Team | 2025-10-30 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | CIQ | The attached PMX in TI is from four months ago and does not reflect the current HW deployment configuration. |  |  | 2025-10-30 18:00:00 | [5 empty] | 44 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.75 | Major | Internal | 75 | 🟢 Monitored | 175 | 0.9 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.9 | 0.46
SA02406A-Coverage Strategy | 176 | AU | 4015819 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4015819/edit | Design | One-T/RFDS Team | 2025-10-30 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | For site SA02406A, as per the RFDS, the site configuration is listed as eSRAN, whereas in latest IP exports it is currently shown as non-SRAN. | [8 empty] | 44 | 2025 | Configuration & Data Mismatch | One-T Mismatch | 0.62 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.95 | 🔴 High Risk (>70%) | High | 1 | 194 | False | 4.4 | 0.31
CC02736A-Coverage Strategy | 176 | AU | 4062129 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4062129/edit | Design | PMX Team | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | RFDS & Port Matrix is missing in TI. |  | NO ETA | [6 empty] | 44 | 2025 | Configuration & Data Mismatch | Missing Documents | 0.71 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 1 | 🔴 High Risk (>70%) | High | 5 | 215, 169, 187 | True | 8.5 | 0.61
MW07238A-Equipment Upgrade | 250 | IN | 3958682 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3958682/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.92 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
MW08201A-Coverage Strategy | 250 | IN | 3531058 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531058/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 60 | 0.91 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
AR01680A-Coverage Strategy | 139 | AR | 3858456 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858456/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.92 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
AR01593B-Coverage Strategy | 139 | AR | 4040233 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040233/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.92 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
OK02711A-Coverage Strategy | 192 | OK | 3673564 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673564/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed |  | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing IX/TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.93 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
AR02238A-Coverage Strategy | 139 | AR | 3858463 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858463/edit | PM | Yashpal Hans | 2025-10-31 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed |  | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.93 | 🔴 High Risk (>70%) | High | 4 | 204, 219, 56 | True | 5.6 | 0.95
AR01896A-Coverage Strategy | 139 | AR | 3945115 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945115/edit | PM | Yashpal Hans | 2025-11-01 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM no site schedule over weekend , Site logged for support . Ti ticket was for schedule was updated later.. Ticket was in closout state, later when checked with PM , PM moved ticket to TS bucket, |  | PM remarks: Site not logged in for TS support on 11/01/2025 13:30 | [6 empty] | 44 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 199, 201, 198 | True | 7.1 | 0.95
MW06779A-Coverage Strategy | 250 | IN | 3712180 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712180/edit | PM | Yashpal Hans | 2025-11-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not in integration schedule or in Ti IX schedule , site was logged in for IX by FE . Site was schedule after FE logged with back office. |  | IX schedules will be updated a night before the actual IX date |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 88, 59, 123 | True | 7.5 | 0.95
9LV0821A-Coverage Strategy | 255 | LU | 3955036 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955036/edit | Integration | Surendra Nehara | 2025-10-31 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia RF | Closed | Implementation | RET naming issue, Extra "2" added in naming and later corrected after escalation | 2025-10-31 01:00:00 | Resolved | 2025-10-31 01:00:00 | [5 empty] | 44 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Minor | External_Issue | 15 | 🔴 REPEAT OFFENSE | 80 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 207 (0d), 20 (0d), 39 | True | 13.2 | 0.74
9NV0284A-Coverage Strategy | 256 |  | 3955170 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955170/edit | Integration | Surendra Nehara | 2025-10-28 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia RF | Closed | Implementation | E missing and BTS ID wrong in RET naming. Later resolved after internal escalation | 2025-10-28 00:00:00 | resolved | 2025-10-28 00:00:00 |  | Human Error |  |  |  | 44 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Minor | External_Issue | 15 | 🔴 REPEAT OFFENSE | 80 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 206 (0d), 20 (0d), 39 | True | 7.8 | 0.58
9LV0408A-Coverage Strategy | 255 | LU | 4205142 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4205142/edit | Integration | Surendra Nehara | 2025-11-01 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia RF | Closed | Port Matrix | I missing for N21 | 2025-11-01 01:00:00 |  | 2025-11-01 01:00:00 | [5 empty] | 44 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.71 | Minor | External_Issue | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.85 | 🔴 High Risk (>70%) | High | 1 | 209 (5d) | False | 5.9 | 0.46
9LV3122A-Coverage Strategy | 255 | LU | 3954967 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3954967/edit | Integration | Surendra Nehara | 2025-10-24 00:00:00 | Minor |  | Concerns | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia RF | Closed | Implementation | "I" missing for N21 | 2025-10-29 01:00:00 |  | 2025-10-29 01:00:00 |  | Process Gap |  |  |  | 43 | 2025 | Nesting & Tool Errors | General | 0.71 | Minor | External_Issue | 10 | 🟢 Monitored | 80 | 0.75 | 🔴 High Risk (>70%) | Medium | 1 | 208 (0d) | False | 6.7 | 0.3
CL45897A-L1900 Capacity | 251 | CL | 3792983 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3792983/edit | Integration | Surendra Nehara | 2025-10-16 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia OA team | Closed | Implementation | RET controllers BETA and GAMMA are swapped, Beta need to be 4,5,6 & Gamma need to be 7,8,9. Later corrected by PAG | 2025-10-16 01:00:00 |  | 2025-10-16 01:00:00 | PAG | Human Error |  | Low |  | 42 | 2025 | Configuration & Data Mismatch | RET Swap | 0.66 | Minor | External_Issue | 15 | 🟢 Monitored | 80 | 0.38 | 🟡 Moderate (30-50%) | Low | 0 |  | False | 6.0 | 0.47
MW13141A-Coverage Strategy | 250 | IN | 3788494 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3788494/edit | PM | Yashpal Hans | 2025-11-03 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ticket was found in closeout .Site was not schedule for TS on 11/3. Ticket moved from closeout to TS after FE logged in with BO for TS activity. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 271, 229, 213 | True | 7.5 | 0.95
LI12121B-Sector Add | 75 | LI | 3988150 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3988150/edit | Integration | shriwastwa, Jitesh | 2025-10-28 00:00:00 | Critical |  | Escalations | 1 | Rameshnaik Jarupla (Rameshnaik.Jarupla@amdocs.com) |  | External_issue |  | Closed | Inadequate Skillset | The PM received a call from TMO pm asking why we didn't lock the cells before removing the temporary baseband | 2025-11-03 19:00:00 | Temp N41 nodes connectivity restored and currently the cells are Locked/barred/reserved: Now we will remove the BBUs. |  |  | Process Gap |  | Medium | <p style="margin-left:.5in;"><span style="font-size:11.0pt;font-family:'Century Gothic',sans-serif;">Temp N41 nodes connectivity restored and currently the cells are Locked/barred/reserved:</span></p><p style="margin-left:.5in;"><span style="font-size:11.0pt;font-family:'Century Gothic',sans-serif;">Now we will remove the BBUs.</span></p> | 44 | 2025 | Validation & QA | General | 0.62 | Critical | External_Issue | 150 | 🆕 New Issue | 200 | 0.29 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.3 | 0.3
MO08726A-Coverage Strategy | 261 | STL | 3712236 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712236/edit | PM | Yashpal Hans | 2025-11-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in Closeout .FE logged in for TS no schedule provided for TS of site, Ticket was moved back.TS for support . |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 35 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 270, 229, 211 | True | 7.2 | 0.95
MW04003A-Equipment Upgrade | 250 | IN | 3999390 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999390/edit | Design | Yashpal Hans | 2025-11-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | RFDS | Design change . SCF was prepared based on available RFDS , at the site of Integration It was noticed HW available on site was ASIA and SCF was created based on RFDS with ASIB. |  | design change not notified by TMO to us. as FE reached at site, realized RFDS vs HW deviation. and matter taken up with TMO |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Configuration & Data Mismatch | Design Mismatch | 0.48 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.84 | 🔴 High Risk (>70%) | High | 2 | 370, 119 (0d) | False | 3.3 | 0.3
AU03348A-Coverage Strategy | 176 | AU | 4062082 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4062082/edit | Design | PMX Team | 2025-11-05 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | AU03348A — Port Matrix is missing in TI. Kindly provide the updated one. |  | No ETA for PMX file on TI | [6 empty] | 45 | 2025 | Configuration & Data Mismatch | Missing Documents | 0.7 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 197, 360, 187 | True | 8.1 | 0.59
AR01685A-Coverage Strategy | 139 | AR | 3712168 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712168/edit | Design | Aqsa Sayed | 2025-11-06 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Updated Port matrix required/we did RET configuration as per site configuration, naming is incorrect in port matrix | [8 empty] | 45 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 313, 361, 355 | True | 6.3 | 0.49
9LV0756A-Coverage Strategy | 255 | LU | 3955085 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955085/edit | PM | Surendra nehra | 2025-11-06 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Microwave is pathed and site not ready for integration due to incomplete microwave work |  |  | 2025-11-06 01:00:00 | Surendra |  |  |  |  | 45 | 2025 | Site Readiness | MW Not Ready | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 314 (2d), 287 (0d), 157 (0d) | False | 7.1 | 0.37
OK02632A-Coverage Strategy | 192 | OK | 3770775 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770775/edit | Design | Aqsa Sayed | 2025-11-07 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RFDS | RFDS not mention with tilt value .Need udpated RFDS with for NSD site to set tilt value, | [8 empty] | 45 | 2025 | Nesting & Tool Errors | General | 0.59 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 80 | 0.88 | 🔴 High Risk (>70%) | High | 3 | 169, 384, 370 | True | 7.8 | 0.3
OK02632A-Coverage Strategy | 192 | OK | 3770775 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770775/edit | PM | Yashpal Hans | 2025-11-07 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | As per PM not site schedule on weekend , Site logged in for TS , Site was not schedule in Ti |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 221, 220, 202 | False | 6.7 | 0.95
AR01771A-Coverage Strategy | 139 | AR | 4040243 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040243/edit | PM | Yashpal Hans | 2025-11-07 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for TS and no entry in Ti Schedule ,Site logged in for TS |  | Not any TS support was there to FE on 11/07 |  |  | Non Amdocs |  |  |  | 45 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 230, 233, 244 | False | 9.2 | 0.95
A5L0079A-Coverage Strategy | 347 | KC | 3770771 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770771/edit | PM | Yashpal Hans | 2025-11-08 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not scedule for TS on weekend in TI, Fe logged in for TS activity. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | Weekend Schedule Issue | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.86 | 🔴 High Risk (>70%) | High | 5 | 219, 233, 220 | False | 8.9 | 0.95
MW04003A-Equipment Upgrade | 250 | IN | 3999390 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999390/edit | PM | Yashpal Hans | 2025-11-08 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  | Closed | Scheduling | Site was not planned for IX continuation and TS activity for 11/9, site was logged be FE for support |  | Vendors not sharing their schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight repetitive offenders |  |  | Non Amdocs |  | Low |  | 45 | 2025 | Scheduling & Planning | General | 0.7 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 357 (0d), 102, 60 | True | 5.6 | 0.95
OK02567A-Coverage Strategy | 192 | OK | 4040181 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040181/edit | PM | Yashpal Hans | 2025-11-09 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not planned or schedule for TS support in Ti.FE logged in for TS support. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 241, 233, 230 | True | 9.9 | 0.95
BA00368A-Cabinet Consolidation | 88 | SF | 4115710 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4115710/edit | Field | Ejaz Mehmood | 2025-11-08 00:00:00 | Minor |  | Escalations | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | Internal | BO | Closed | FE | GC team missed reconnecting GPS SFP at Port 23 to IXRe, causing a PTP sync issue. Which required TS with NTAC team. |  | With NTAC team's help, GNSS port was configured for PTP sync, and the issue was resolved. | [6 empty] | 45 | 2025 | Scheduling & Planning | General | 0.52 | Minor | Internal | 15 | 🟢 Monitored | 4 | 0.27 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.7 | 0.95
MU01215A-Coverage Strategy | 257 | DE | 3798572 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3798572/edit | Design | Daniel Lamas | 2025-11-10 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | we have observed a RET naming mismatch in the current Port Matrix, and as per site configuration . as per site configuration , there is no “I” = 5G AWS (N66) present , but in port matrix RET naming “I” is included | [8 empty] | 46 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 248, 267 (0d), 268 (0d) | True | 6.3 | 0.49
MO12864A-Coverage Strategy | 261 | STL | 3711632 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711632/edit | Design | Yashpal Hans | 2025-11-10 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | updated port matrix required as shared port matrix naming is not correct,as per rfds L600 ¦ L700 ¦ L1900 ¦ L2100 ¦ N600c1c2 ¦ N1900 ¦ N2500c1c2-ABG |  | Design pre-checks now in place prior to actual IX date |  |  | Process Gap |  | Low |  | 46 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.58 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 313, 360, 327 (0d) | True | 3.3 | 0.3
WI03017A-Coverage Strategy | 340 | WI | 3332996 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3332996/edit | Design | Aqsa Sayed | 2025-11-10 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | As per site configuration, we have 3 RET defined per Sector. As per port matrix , 2 RET’s defined per sector Need updated port matrix | [8 empty] | 46 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 293, 55 (0d), 361 | True | 5.3 | 0.41
9LV0629A-Coverage Strategy | 255 | LU | 3873317 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873317/edit | PAG | Surendra Nehara | 2025-11-11 00:00:00 | Minor |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | External_issue | Nokia OA team | Closed | KPI Monitoring | RET name "I" was deleted accidently for N21. PAG Engineer was working on the 2-hour report for 9KX0408A and simultaneously checking connectivity on 9LV0629A. while doing this, he was removing "I" from RET naming for 9KX0408A site as this site does not have N2100. It appears that the same letter was unintentionally removed from 9LV0629A site as well. Later it was caught by Nokia during OA review and asked us for correction | 2025-11-11 01:00:00 |  | 2025-11-11 01:00:00 | PAG | Human Error |  |  |  | 46 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Minor | External_Issue | 15 | 🟢 Monitored | 80 | 0.83 | 🔴 High Risk (>70%) | High | 4 | 20 (0d), 206 (0d), 207 (0d) | True | 6.9 | 0.53
MW15807A-Coverage Strategy | 250 | IN | 3673598 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673598/edit | PM | Yashpal Hans | 2025-11-14 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ticket was in closeout , FE on site for TS .Site was not schedule for TS . Site supported after ticket moved to TS from closeout. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 213, 270, 211 | True | 7.5 | 0.95
AR01865A-Coverage Strategy | 139 | AR | 3673586 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673586/edit | PM | Yashpal Hans | 2025-11-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for TS , site was schedule in Ti after FE logged with BO. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 233, 220, 244 | True | 9.2 | 0.95
MW03606A-Coverage Strategy | 250 | IN | 3712213 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712213/edit | PM | Yashpal Hans | 2025-11-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Sit was schedule and BH ready , but TI entry missing for BH readiness. |  | PM remarks: Irrelevant escalation. Mail initiated | [6 empty] | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 139, 124, 140 | True | 10.7 | 0.95
9KX1013A-Coverage Strategy | 254 | KX | 3955248 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955248/edit | PM | Surendra nehra | 2025-11-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in TI for integration.. | 2025-11-14 13:30:00 |  | 2025-11-14 13:30:00 | Surendra |  |  |  |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 122, 238, 81 (0d) | True | 11.7 | 0.95
MO05814A-Coverage Strategy | 261 | STL | 3712225 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712225/edit | PM | Yashpal Hans | 2025-11-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for TS in TI, site was schedule after FE logged with BO. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight the problematic vendors. |  |  | Non Amdocs |  | Medium |  | 46 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 230, 220, 244 | True | 9.2 | 0.95
MO12864A-Coverage Strategy | 261 | STL | 3711632 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711632/edit | Field | Yashpal Hans | 2025-11-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | FE on site for TS but didn't had material require for TS . Site was cancelled for TS . |  | Material management not under Amdocs SoW in HL |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | General | 0.7 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 107, 233, 230 | True | 9.2 | 0.95
SLFR001A-COW | 261 | STL | 4527185 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4527185/edit | PM | Yashpal Hans | 2025-11-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Ticket is not created in pay point for monitoring and ticket movement in paypoint, |  | It was an adhoc requirement from TMO |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | General | 0.67 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.86 | 🔴 High Risk (>70%) | High | 4 | 245, 367, 70 | True | 7.8 | 0.95
AR02051B-Coverage Strategy | 139 | AR | 3770753 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770753/edit | PM | Yashpal Hans | 2025-11-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not Schedule for TS in Ti. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 244, 241, 242 | False | 11.7 | 0.95
MO12880B-Coverage Strategy | 261 | STL | 4040173 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040173/edit | Design | Yashpal Hans | 2025-11-14 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Naming wrong in port matric, require updated port matrix..and we have only 3 sectors on site but port matrix have 4 sec |  | PM now being verified a week before the actual IX date |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.71 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 361, 251, 327 (0d) | True | 3.4 | 0.3
CH89311A-Coverage Strategy | 169 | CHI | 3334793 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3334793/edit | PM | Daniel Lamas | 2025-11-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for Integration. |  | IX schedule was in a different location, but has been updated to correct location going forward. |  | Dan Lamas |  |  |  |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 80 (0d), 79, 122 | True | 11.7 | 0.95
CH89311A-Coverage Strategy | 169 | CHI | 3334793 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3334793/edit | Design | Daniel Lamas | 2025-11-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RF NTP | mismatch for N600 between the ARFCN and bandwidth (BW) values defined in the spectrum plan and those currently configured in the SCF | [8 empty] | 46 | 2025 | Configuration & Data Mismatch | Spectrum Mismatch | 0.62 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.87 | 🔴 High Risk (>70%) | High | 1 | 174 | False | 4.4 | 0.31
9LV0642A-Coverage Strategy | 255 | LU | 3955112 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955112/edit | PM | Surendra nehra | 2025-11-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for integration |  |  | 2025-11-15 14:30:00 | Surendra |  |  |  |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 122, 81 (0d), 238 | True | 11.7 | 0.95
MO12880B-Coverage Strategy | 261 | STL | 4040173 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040173/edit | PM | Yashpal Hans | 2025-11-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for TS . |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 46 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.86 | 🔴 High Risk (>70%) | High | 5 | 242, 244, 122 | True | 11.7 | 0.95
MO05814A-Coverage Strategy | 261 | STL | 3712225 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712225/edit | PM | Yashpal Hans | 2025-11-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in Ti for TS |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Medium |  | 47 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 241, 240 (0d), 122 | True | 11.7 | 0.95
9LV0642A-Coverage Strategy | 255 | LU | 3955112 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955112/edit | Design | Surendra nehra | 2025-11-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | As per the site configuration, the RET naming should be 12IJBL for mid-band and 11KED for low-band. However, in the current port matrix, N2100 and L600 are missing across all sectors |  |  | 2025-11-16 13:30:00 | Surendra |  |  |  |  | 47 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 294 (0d), 248, 225 | True | 5.3 | 0.41
MW07357B-Anchor | 250 | IN | 3999403 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999403/edit | PM | Yashpal Hans | 2025-11-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule n TI for TS. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 47 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.86 | 🔴 High Risk (>70%) | High | 5 | 241, 236, 220 | False | 11.7 | 0.95
MO12880B-Coverage Strategy | 261 | STL | 4040173 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040173/edit | Design | Aqsa Sayed | 2025-11-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Incomplete Scope | pay point ticket was in Design phase , ticket cant be moved for monitoring in pay point project | [8 empty] | 47 | 2025 | Scheduling & Planning | General | 0.69 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 367, 70, 235 | True | 7.5 | 0.95
OK01606A-L600 | 192 | OK | 4099141 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4099141/edit | Design | RFDS Team | 2025-11-17 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | Upon reviewing the RFDS for the given NR technology, we observed that only one SMOD(ASIL) given. However, based on our understanding, two ASILs are generally required . | [8 empty] | 47 | 2025 | Configuration & Data Mismatch | RFDS Mismatch | 0.56 | Major | Internal | 75 | 🟢 Monitored | 175 | 0.23 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.6 | 0.34
MW06780B-Coverage Strategy | 250 | IN | 3999398 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999398/edit | Design | Aqsa Sayed | 2025-11-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RIOT | Mismatch in TAC in RIOT and SCF. RIOT is RED (OSS & RF Config) for all LTE Technologies(L1900¦L600¦LAWS3¦L2100) due to TAC mismatch. In OSS TAC is 42112 but in RF Config TAC value is 47488.RIOT turn green after chnaged the TAC on site as per RIOT value, | [8 empty] | 47 | 2025 | Configuration & Data Mismatch | TAC Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 372, 373, 174 | True | 6.3 | 0.49
MW06780B-Coverage Strategy | 250 | IN | 3999398 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999398/edit | Design | Aqsa Sayed | 2025-11-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | we have observed a RET naming mismatch in the current Port Matrix, and as per site configuration . As per site configuration , there is no “I” = 5G AWS (N66) present , but in port matrix RET naming “I” is included | [8 empty] | 47 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 225, 267 (0d), 268 (0d) | False | 6.3 | 0.49
WI02988B-Coverage Strategy | 340 | WI | 3531062 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531062/edit | Design | Aqsa Sayed | 2025-11-19 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Need updated port matrix . node having three rets and port matrix having only 2 rets, | [8 empty] | 47 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 361, 216, 355 | True | 8.2 | 0.6
9LV0471A-Coverage Strategy | 255 | LU | 3955196 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955196/edit | Integration | Jatinder | 2025-11-19 00:00:00 | Major |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | Internal | Ix team | Closed | Implementation | The Ix team missed the AWS3 E911 call test during Ix and released full RTT. Later it was caught by Ix team during audit and they asked us to schedule FE for call test | 2025-11-20 01:00:00 | Requested GC to send FE again to complete missing call test and completed | 2025-11-20 01:00:00 | Surendra | Human Error |  | Low |  | 47 | 2025 | Validation & QA | Missed Call Test | 0.6 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 122.5 | 0.98 | 🔴 High Risk (>70%) | High | 3 | 338 (1d), 365, 186 (0d) | True | 2.9 | 0.3
MW03553C-Equipment Upgrade | 250 | IN | 3999388 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999388/edit | Design | Aqsa Sayed | 2025-11-19 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Incorrect naming in port matirx .Need updated port matrix. | [8 empty] | 47 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 237, 216, 339 (1d) | True | 6.1 | 0.48
IL17602A-Coverage Strategy | 261 | STL | 3858468 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858468/edit | Integration | Nadeem Khan | 2025-10-25 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Count of sectors mentioned different in summary as compared to captured in CBN |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 43 | 2025 | Documentation & Reporting | Data Mismatch | 0.7 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 40 | 0.89 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.2 | 0.3
AR01770A-Coverage Strategy | 139 | AR | 3712224 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712224/edit | Integration | Nadeem Khan | 2025-10-29 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | Different site MW12411 mentioned in spectrum validation remarks |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Human Error | Loss of Trust | Medium |  | 44 | 2025 | Nesting & Tool Errors | General | 0.68 | Minor | Internal | 10 | 🟢 Monitored | 80 | 0.22 | 🟢 Low (<30%) | Medium | 0 |  | False | 8.2 | 0.3
AR02057A-Replacement | 139 | AR | 3999385 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999385/edit | Integration | Nadeem Khan | 2025-10-30 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | Live CT CBN output snapshot missing in E911 complete mail |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Human Error | Loss of Trust | Medium |  | 44 | 2025 | Documentation & Reporting | Missing Snapshot | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 10 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 273, 319, 179 | True | 11.5 | 0.3
AR02083A-Coverage Strategy | 139 | AR | 3858462 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858462/edit | Integration | Nadeem Khan | 2025-11-03 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Live CT CBN output snapshot missing in E911 complete mail |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 45 | 2025 | Documentation & Reporting | Missing Snapshot | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 10 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 273, 319, 179 | True | 11.5 | 0.3
MW06779A-Coverage Strategy | 250 | IN | 3712180 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712180/edit | Integration | Nadeem Khan | 2025-11-03 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | Delayed reply to FE on PTP profile on IXRe configuration |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 45 | 2025 | Communication & Response | Delayed Response | 0.95 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 25 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 257 | False | 7.3 | 0.95
AR01593B-Coverage Strategy | 139 | AR | 4040233 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040233/edit | Integration | Nadeem Khan | 2025-11-04 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | Delayed reply to FE. Replied back, when PM asked for update. |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Project | Medium |  | 45 | 2025 | Communication & Response | Delayed Response | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 25 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 264, 97, 286 | True | 16.1 | 0.95
OK02627A-Coverage Strategy | 192 | OK | 3712134 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712134/edit | Integration | Nadeem Khan | 2025-11-12 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | Troubleshooting was going on. FE questioned why TS taking more than 3.5hrs. Amdocs should answer such queries pro-actively, rather getting questioned over delays with TMO in cc. |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 46 | 2025 | Communication & Response | No Proactive Update | 0.55 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 25 | 0.96 | 🔴 High Risk (>70%) | High | 1 | 330 | False | 4.5 | 0.95
MO05814A-Coverage Strategy | 261 | STL | 3712225 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712225/edit | Integration | Nadeem Khan | 2025-11-12 00:00:00 | Major |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Without E911 Go mail |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 46 | 2025 | Documentation & Reporting | Process Skip | 0.75 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 70 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 178, 283, 304 | True | 10.2 | 0.3
MO12880B-Coverage Strategy | 261 | STL | 4040173 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040173/edit | Integration | Nadeem Khan | 2025-11-15 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Subject should have been partial, in lieu of Complete |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 46 | 2025 | Documentation & Reporting | Wrong Subject | 0.67 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 10 | 0.9 | 🔴 High Risk (>70%) | High | 0 |  | False | 7.9 | 0.3
AR01896A-Coverage Strategy | 139 | AR | 3945115 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3945115/edit | Integration | Nadeem Khan | 2025-10-15 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | External_issue | Conniel Rey Cabalatungan | Closed |  | IX Team made changes to the tilt settings and did not revert them to the original values, the responsibility lies with the IX Team to ensure post status shouldn't have abnormal/unacceptable values. |  | Team will take going forward, Anamoly detection also deployed for RET to check pre-post RET tilt so that any changes can be capture timely. |  |  | Process Gap | Loss of Project | Medium |  | 42 | 2025 | Configuration & Data Mismatch | General | 0.55 | Critical | External_Issue | 150 | 🟢 Monitored | 200 | 0.28 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.3 | 0.31
AR01769A-Coverage Strategy | 139 | AR | 3712165 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712165/edit | PAG | Vangelis Dardoumas | 2025-10-10 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | PAG QA | PAG BO released IX pre-checks. BH not actualized in MB |  |  |  |  | Human Error | Loss of Project | Medium |  | 41 | 2025 | Site Readiness | BH Not Ready | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 200 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 126, 96, 11 (0d) | True | 9.3 | 0.51
A5D0398A-Coverage Strategy | 347 | KC | 3770766 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770766/edit | Integration | Nadeem Khan | 2025-10-03 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Different site ID in E911 completion mail |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 40 | 2025 | Documentation & Reporting | Wrong Site ID | 0.75 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 40 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 176, 177, 178 | True | 10.2 | 0.3
A5C0253A-Coverage Strategy | 347 | KC | 3770764 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770764/edit | Integration | Nadeem Khan | 2025-09-17 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | Delayed response to FE. Replied back when PM questioned. |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Project | Medium |  | 38 | 2025 | Communication & Response | Delayed Response | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 25 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 257, 97, 286 | True | 11.5 | 0.95
AR01879A-Coverage Strategy | 139 | AR | 3712173 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712173/edit | Integration | Nadeem Khan | 2025-09-13 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | IX BO could have informed FE to complete whitelisted in lieu of Live calls, if PSAP was busy. |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 37 | 2025 | Site Readiness | General | 0.56 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 400 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 5.8 | 0.3
MO05254A-Anchor | 261 | STL | 3973481 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3973481/edit | Integration | Nadeem Khan | 2025-09-16 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | NTAC contacted for support |  |  |  |  | Process Gap | Loss of Trust | Low |  | 38 | 2025 | Configuration & Data Mismatch | General | 0.7 | Critical | Internal | 150 | 🟢 Monitored | 200 | 0.96 | 🔴 High Risk (>70%) | High | 1 | 62 | False | 6.5 | 0.51
5TC3041A-Coverage Strategy | 254 | KX | 3955088 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955088/edit | Design | Surendra nehra | 2025-11-20 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Incorrect port matrix As per site configuration , there is no “I” = 5G AWS (N66) present , but in port matrix RET naming “I” is included |  |  | 2025-11-20 13:30:00 | Surendra |  |  |  |  | 47 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 268 (0d), 225, 248 | True | 5.3 | 0.41
A6C0952A-Coverage Strategy | 467 | CB | 3955039 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955039/edit | Design | Surendra nehra | 2025-11-20 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Incorrect port matrix. As per site configuration , there is no “I” = 5G AWS (N66) present , but in port matrix RET naming “I” is included |  |  | 2025-11-20 13:30:00 | Surendra |  |  |  |  | 47 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 267 (0d), 225, 248 | True | 5.3 | 0.41
MO06390A-L600 | 261 | STL | 3999465 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999465/edit | PM | Yashpal Hans | 2025-11-23 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site cancelled. Live site , TMO didnt want to continue IX of site citing Holiday week. |  | PM remarks: TMO discretion, Amdocs shouldn't intervene |  |  | Non Amdocs |  | Low |  | 48 | 2025 | Scheduling & Planning | General | 0.75 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 358 (0d), 357 (0d), 222 | True | 9.8 | 0.95
AR02051B-Coverage Strategy | 139 | AR | 3770753 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770753/edit | PM | Yashpal Hans | 2025-11-24 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in close out and not Scedule. FE logged in for TS activity and site was in closeout, ticket moved back to TS for support. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors. |  |  | Non Amdocs |  | Low |  | 48 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.85 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.85 | 🔴 High Risk (>70%) | High | 5 | 213, 229, 271 | True | 7.2 | 0.95
MW07352B-L1900 Capacity | 250 | IN | 3999401 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999401/edit | PM | Yashpal Hans | 2025-11-24 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site in closeout and not schedule for TS. FE logged in for TS and ticket was in closeout. Ticket moved back to TS requesting BO for Support. |  | PM remarks: Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Medium |  | 48 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 211, 270, 213 | True | 7.5 | 0.95
9LV0822A-Coverage Strategy | 255 | LU | 3955006 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955006/edit | PM | Surendra nehra | 2025-11-24 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Port matrix is missing in Ti. RET is currently configured, but validation is pending |  |  | 2025-11-24 14:00:00 | Surendra |  |  |  |  | 48 | 2025 | Configuration & Data Mismatch | Missing Documents | 0.73 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 105 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 187, 185, 197 | True | 8.1 | 0.59
MW05204A-Coverage Strategy | 250 | IN | 3999395 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999395/edit | Integration | Nadeem Khan | 2025-11-24 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Complete notification mail, Live CT CBN output snapshot missing for L700-ABGD |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Snapshot | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 10 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 254, 255, 183 | True | 17.4 | 0.35
A5J0075A-Coverage Strategy | 347 | KC | 3673600 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673600/edit | Integration | Nadeem Khan | 2025-11-24 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | SCF team already uploaded correct SCF with guidelined CAT-M configuration, in TI. but during integration some other file was used by IX BO. |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 48 | 2025 | Configuration & Data Mismatch | General | 0.67 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 200 | 0.92 | 🔴 High Risk (>70%) | High | 3 | 370, 83, 288 (0d) | True | 4.7 | 0.35
A5J0075A-Coverage Strategy | 347 | KC | 3673600 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673600/edit | Integration | Nadeem Khan | 2025-11-24 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
A5J0075A-Coverage Strategy | 347 | KC | 3673600 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673600/edit | Integration | Nadeem Khan | 2025-11-25 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MW03599A-Coverage Strategy | 250 | IN | 3712147 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712147/edit | Integration | Nadeem Khan | 2025-11-24 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MW07352B-L1900 Capacity | 250 | IN | 3999401 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999401/edit | Field | Yashpal Hans | 2025-11-24 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | FE Competency issue . FE doesn't know how to do the troubleshooting for RTWP and even after explaining the process |  | PM remarks: Escalated to TMO |  |  | Non Amdocs |  | Low |  | 48 | 2025 | Scheduling & Planning | General | 0.58 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.83 | 🔴 High Risk (>70%) | High | 0 |  | False | 4.8 | 0.95
AR02064A-Coverage Strategy | 139 | AR | 3712246 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712246/edit | Integration | Nadeem Khan | 2025-11-25 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO14444B-Coverage Strategy | 261 | STL | 3770786 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770786/edit | Integration | Nadeem Khan | 2025-11-25 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
IL03716A-Coverage Strategy | 261 | STL | 3712218 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712218/edit | Integration | Nadeem Khan | 2025-11-25 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
TC01003A-Coverage Strategy | 257 | DE | 3858440 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858440/edit | PM | Daniel Lamas | 2025-11-30 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ticket was in closeout , PM requested for TS support to FE , Ticket moved to TS |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 49 | 2025 | Scheduling & Planning | Ticket Status Issue | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 362, 271, 345 | True | 9.2 | 0.95
IL17820A-Coverage Strategy | 261 | STL | 3531041 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531041/edit | Integration | Nadeem Khan | 2025-11-26 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  |  |  |  | Process Gap | Loss of Trust | High |  | 48 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
IL17820A-Coverage Strategy | 261 | STL | 3531041 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531041/edit | Integration | Nadeem Khan | 2025-12-01 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | High |  | 49 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO10501A-Coverage Strategy | 261 | STL | 3712112 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712112/edit | Integration | Nadeem Khan | 2025-12-01 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | High |  | 49 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
A5H0103A-Coverage Strategy | 347 | KC | 4040223 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040223/edit | PAG | PAG BO | 2025-12-01 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open |  | Delayed reply to GC. GC followed up on his request 1.5hrs after on same mail. Reply sent to GC 15mins after his second follow-up |  |  |  |  | Process Gap | Loss of Trust | Low |  | 49 | 2025 | Communication & Response | Delayed Response | 0.95 | Critical | Internal | 150 | 🔴 REPEAT OFFENSE | 25 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 97, 98, 309 | True | 7.5 | 0.95
9LV4133A-Coverage Strategy | 255 | LU | 3955107 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955107/edit | PM | Surendra nehra | 2025-12-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Site integration went in hold due to Microwave was not ready . | 2025-12-03 17:00:00 |  | 2025-12-03 19:00:00 | Surendra |  |  |  |  | 49 | 2025 | Site Readiness | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 146 (0d), 314 (2d), 217 (0d) | False | 9.1 | 0.5
9LV2266A-Coverage Strategy | 255 | LU | 3873343 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873343/edit | PM | Surendra nehra | 2025-12-04 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | RF NTP | IP mismatch in One-T and SCF , revised SCF needed from TMO causing delay in IX |  |  | 2025-12-04 14:00:00 | Surendra |  |  |  |  | 49 | 2025 | Configuration & Data Mismatch | IP Mismatch | 0.69 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 60 | 0.8 | 🔴 High Risk (>70%) | High | 2 | 322, 274 | True | 4.5 | 0.33
MO07296A-Coverage Strategy | 261 | STL | 3712219 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712219/edit | PM | Yashpal Hans | 2025-12-07 00:00:00 | Major |  | Concerns | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | site Schedule for 7th Dec, but FE logged on 8th Dec for IX |  | site actually scheduled for Sunday 12/07, integrated on Sunday 12/07 |  |  | Non Amdocs |  |  |  | 50 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.74 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 70 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 61, 120, 86 | True | 9.6 | 0.95
9LV4117A-Coverage Strategy | 255 | LU | 4205156 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4205156/edit | PM | Surendra nehra | 2025-12-07 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | BH was not ready. MW link was not ready and site got cancelled for IX after precheck |  |  | 2025-12-07 13:30:00 | Surendra |  |  |  |  | 50 | 2025 | Site Readiness | MW Not Ready | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 280 | 0.96 | 🔴 High Risk (>70%) | High | 5 | 157 (0d), 148 (15d), 63 (2d) | True | 12.2 | 0.62
A6F1206A-Coverage Strategy | 467 | CB | 4205129 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4205129/edit | PM | Surendra nehra | 2025-12-06 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was schedule for IX and BH (Microwave was not ready) for IX |  |  | 2025-12-06 13:30:00 | Surendra |  |  |  |  | 49 | 2025 | Site Readiness | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 357 (0d), 287 (0d), 63 (2d) | True | 9.1 | 0.5
LAYH044A-Venue ACS | 56 | LA | 4564187 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4564187/edit | PM | PM | 2025-12-08 00:00:00 | Major |  | Escalations | 3 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | Last time scripting request - RE: LA ¦¦ Site Review ¦¦ TMO Integration Ericsson - LAY4402A/LAY4403A/LAY4404A/LAY4405A/LAY4406A/LAY4401A (LAYH044A) ¦¦ CSR and BBU Swap + IX (L to M conversion) ¦¦ 2025-12-09 ¦¦ COMBINED PRE-CHECK | [8 empty] | 50 | 2025 | Scheduling & Planning | General | 0.5 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.32 | 🟡 Moderate (30-50%) | Medium | 0 |  | False | 4.1 | 0.95
MO06390A-L600 | 261 | STL | 3999465 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999465/edit | Design | Yashpal Hans | 2025-12-09 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | As per port matrix we have 2 RET’s for each sectors but configuration showing 3 RET’s per sectors. Need updated port matirx |  | PM remarks: Design team has started validation of PM/PSAP details as per weekly IX schedule from IX PM |  |  | Process Gap |  | Low |  | 50 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 227, 55 (0d), 361 | True | 4.6 | 0.33
A4K1825A-Coverage Strategy | 252 | PB | 4205172 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4205172/edit | Design | Surendra nehra | 2025-12-09 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | we have observed a RET naming mismatch in the current Port Matrix, and as per site configuration . As per site configuration , there is no “F” = LTE AWS3 present , but in port matrix RET naming “F” is included. Currently RET naming done as per site configuration and updated port matrix required for validation |  |  | 2025-12-09 13:30:00 | Surendra |  |  |  |  | 50 | 2025 | Configuration & Data Mismatch | RET Naming | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 248, 225, 216 | True | 6.7 | 0.52
MO06390A-L600 | 261 | STL | 3999465 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999465/edit | Field | Yashpal Hans | 2025-12-08 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | FE | Site was down in precheck. Site installation started without informing BO and BO couldn't lock the live cells. |  | PM remarks: Escalated to TMO |  |  | Non Amdocs |  | Low |  | 50 | 2025 | Site Readiness | Site Down | 0.68 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 160 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 166, 2 (0d), 85 | True | 4.9 | 0.3
9LV1723A-Cell Split | 255 | LU | 3659215 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3659215/edit | Design | Surendra nehra | 2025-12-04 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Updated port matrix require. N2100 is dark and N1900 active in RFDS &amp; site |  |  | 2025-12-04 13:30:00 | Surendra |  |  |  |  | 49 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.67 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 337 (0d), 320 (0d), 226 | True | 7.8 | 0.58
NY5905BA_11-Troubleshooting Support | 76 | NY | 4573698 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4573698/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | Last time script request- RE: Crown HUB 20 Re home support | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | General | 0.65 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.92 | 🔴 High Risk (>70%) | High | 2 | 300, 299 | False | 5.9 | 0.46
BA31330A-New Build | 88 | SF | 4581661 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4581661/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: BA31330A - Scripting | [8 empty] | 50 | 2025 | Documentation & Reporting | General | 0.65 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 70 | 0.93 | 🔴 High Risk (>70%) | High | 0 |  | False | 7.9 | 0.3
NY5901BA_31-Troubleshooting Support-Troubleshooting Support | 76 | NY | 4573699 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4573699/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: Crown HUB 20 Re home support | [8 empty] | 50 | 2025 | Site Readiness | General | 0.64 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 297 | False | 5.8 | 0.3
NY5912BA_11-Troubleshooting Support-Troubleshooting Support | 76 | NY | 4573700 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4573700/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: Crown HUB 20 Re home support | [8 empty] | 50 | 2025 | Site Readiness | General | 0.64 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.93 | 🔴 High Risk (>70%) | High | 1 | 297 | False | 5.8 | 0.3
MWYH042A-DAS Remote Connectivity | 250 | IN | 4568161 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4568161/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | Re: Ericsson DOT Central ACS December venues - MWYH042A-0002496443 ¦ A1YH0C1A-0002509551 | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | General | 0.67 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.79 | 🔴 High Risk (>70%) | Medium | 0 |  | False | 12.2 | 0.72
ATYN901A-Venue ACS-Venue ACS | 185 | AT | 4573430 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4573430/edit | PM | PM | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | ATYN901A ¦¦ Chattanooga Veterans Affairs Govt Bldg ¦¦ Scripting ¦¦ IP Sec | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | General | 0.68 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.87 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.59
SDYH006A_Site Mod-Venue ACS | 172 | SD | 3830468 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3830468/edit | Integration | CIQ Team | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Open | CIQ | CIQ uploaded with NSDY0610A as the NR node, while in oneT and atnd file N node is NSDY0610A2. | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | One-T Mismatch | 0.61 | Major | Internal | 75 | 🟢 Monitored | 105 | 0.28 | 🟢 Low (<30%) | Medium | 0 |  | False | 6.4 | 0.5
MO07296A-Coverage Strategy | 261 | STL | 3712219 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712219/edit | Integration | Nadeem Khan | 2025-12-07 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | High |  | 50 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO15832A-Coverage Strategy | 261 | STL | 3999469 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999469/edit | Integration | Nadeem Khan | 2025-12-08 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | High |  | 50 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO16502B-Coverage Strategy | 261 | STL | 3770788 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770788/edit | Integration | Nadeem Khan | 2025-12-08 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | High |  | 50 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO06390A-L600 | 261 | STL | 3999465 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999465/edit | Integration | Nadeem Khan | 2025-12-09 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed |  | In E911 Go mail, Table with PSAP contact details missing |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | High |  | 50 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
MO14305A-Coverage Strategy | 261 | STL | 3712212 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712212/edit | Integration | Nadeem Khan | 2025-12-09 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | main summary table missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 50 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.83 | 🔴 High Risk (>70%) | High | 1 | 179 | False | 7.6 | 0.3
MW08131B-Coverage Strategy | 250 | IN | 3712124 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712124/edit | Integration | Nadeem Khan | 2025-12-10 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | delayed response to GC |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Human Error | Loss of Trust | Medium |  | 50 | 2025 | Communication & Response | Delayed Response | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 17.5 | 0.93 | 🔴 High Risk (>70%) | High | 4 | 286, 98, 97 | True | 8.5 | 0.95
MW04003A-Equipment Upgrade | 250 | IN | 3999390 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999390/edit | Optimization | Yashpal Hans | 2025-12-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Incomplete Scope | N19C1C2 was still pending with call test , but OA team unlocked the cells and change the cell status to UUU.Cell was found in UUU during TS steps and left as UUU after confirmation from PM/JJ | [8 empty] | 50 | 2025 | Site Readiness | General | 0.56 | Major | Internal | 75 | 🟢 Monitored | 280 | 0.26 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.3 | 0.3
CH89310B-Coverage Strategy | 169 | CHI | 3748917 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3748917/edit | Design | Daniel Lamas | 2025-12-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Parameter Baselines | Site had alarm after integration related to MOCN (feature was not activated), new SCF was requested from TMO causing re-integration and delay of site. | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | Missing Config | 0.56 | Major | Internal | 75 | 🟢 Monitored | 105 | 0.26 | 🟢 Low (<30%) | Medium | 5 | 287 (0d), 155, 146 (0d) | True | 3.3 | 0.3
MO05182A-Coverage Strategy | 261 | STL | 3712154 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712154/edit | Integration | Maria | 2025-12-10 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | SCF | NRPLMNSET not define in SCF , causing site KPI degration., issue reported by OPT team . |  | CBN Validator tool is modified to check MOCN setting in SCF so that engineer can easily check if MOCN is active or not. | [6 empty] | 50 | 2025 | Nesting & Tool Errors | General | 0.58 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.24 | 🟢 Low (<30%) | Medium | 0 |  | False | 10.0 | 0.39
MW08131B-Coverage Strategy | 250 | IN | 3712124 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712124/edit | Design | Aqsa Sayed | 2025-12-11 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Incorrect Port matrix. we have observed a RET naming mismatch in the current Port Matrix, and as per site configuration .. Site doenst have N66 , but port matrix inluded with "I" for N66 | [8 empty] | 50 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 80 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 267 (0d), 268 (0d), 216 | True | 5.3 | 0.41
9LV3322A-Coverage Strategy | 255 | LU | 3955220 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955220/edit | Field | Surendra nehra | 2025-12-11 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Microwave link was not ready . Site not integrated due to site readiness isse.MW was still not ready . |  | TMO schedules MW links and integration on the same day to meet the yearly NSD target. GC performs check-in for Ix/MW simultaneously. If Ix fails due to MW pathing, GC resumes the Ix from where they left off. There is no rework or pre-checks | 2025-12-13 01:00:00 | GC |  |  |  |  | 50 | 2025 | Site Readiness | MW Not Ready | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 146 (0d), 217 (0d), 287 (0d) | False | 3.2 | 0.3
MWYH042A-DAS Remote Connectivity | 250 | IN | 4568161 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4568161/edit | Integration | Ericsson Integration BO support | 2025-12-15 00:00:00 | Major |  | Escalations | 1 | Uttam Mishra (Uttam.Mishra@amdocs.com) |  | Internal | PM | Closed | BO Support Delays | CT and ST procedure for DOT sites were already shared with the IX BO leads, but each day new IX BO engg. will raise the same queries to PM's and FE causing unnecessary delays. MWYH042A |  | Leads to prepare a MOP for DOT integration and share with the IX BO support team to avoid confusions/doubts. The team has been sensitized on this, and we will ensure compliance going forward. | [6 empty] | 51 | 2025 | Site Readiness | General | 0.49 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 280 | 0.82 | 🔴 High Risk (>70%) | High | 0 |  | False | 3.9 | 0.3
MO15632A-Coverage Strategy | 261 | STL | 3712194 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712194/edit | PM | Yashpal Hans | 2025-12-13 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | E911 readiness | MO15632A/Live CT details not mentioned in MB |  | Wrong LoB tagging. To be taken care by Design team. Respective team has been notified. |  |  | Human Error |  | Low |  | 50 | 2025 | Configuration & Data Mismatch | General | 0.67 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 80 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 321, 114, 254 | True | 8.5 | 0.61
MO14444B-Coverage Strategy | 261 | STL | 3770786 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770786/edit | Integration | Nadeem Khan | 2025-12-02 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | Implementation | Different site ID in subject, but pre-checks were actually meant for some other site MO14444B |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Low |  | 49 | 2025 | Documentation & Reporting | Wrong Site ID | 0.66 | Minor | Internal | 10 | 🟢 Monitored | 40 | 0.87 | 🔴 High Risk (>70%) | High | 5 | 22 (0d), 166, 295 | True | 7.5 | 0.3
AR01971A-Coverage Strategy | 139 | AR | 3770751 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770751/edit | Integration | Nadeem Khan | 2025-12-02 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | In E911 Go mail, Table with PSAP contact details missing |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 49 | 2025 | Documentation & Reporting | Missing Information | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 20 | 0.86 | 🔴 High Risk (>70%) | High | 0 |  | False | 8.0 | 0.3
AR01971A-Coverage Strategy | 139 | AR | 3770751 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770751/edit | Integration | Nadeem Khan | 2025-12-02 00:00:00 | Minor |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | CBN output sheet/Validation snapshot missing in mail body |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Low |  | 49 | 2025 | Documentation & Reporting | Missing Snapshot | 0.95 | Minor | Internal | 10 | 🔴 REPEAT OFFENSE | 10 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 379, 380, 378 | True | 11.7 | 0.3
9KX0453A-Coverage Strategy | 254 | KX | 3873299 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873299/edit | Design | Surendra nehra | 2025-12-16 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Updated port matrix required as N2100 available on Only A sec B and C but NOT present on site but it mentioned in port matrix. |  |  | 2025-12-16 13:30:00 | Surendra |  |  |  |  | 51 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.54 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 360, 313, 388 | True | 3.6 | 0.3
MO10501A-Coverage Strategy | 261 | STL | 3712112 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712112/edit | Integration | Nadeem Khan | 2025-12-02 00:00:00 | Minor |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Live CT actually completed for N600-ABGD, but in summary box Live CT completion mentioned for N2500-ABD |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Medium |  | 49 | 2025 | Site Readiness | General | 0.6 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 160 | 0.87 | 🔴 High Risk (>70%) | High | 1 | 316 | False | 4.3 | 0.3
MO15632A-Coverage Strategy | 261 | STL | 3712194 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712194/edit | Integration | Maria Peponaki | 2025-12-13 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | SCF | Gateway IP different compared with SCF and One-T. Caused delay in integration on weekend. |  |  |  |  | Process Gap | Loss of Trust | Low |  | 50 | 2025 | Configuration & Data Mismatch | IP Mismatch | 0.68 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 150 | 0.94 | 🔴 High Risk (>70%) | High | 1 | 288 (0d) | False | 6.3 | 0.49
IL17836B-Coverage Strategy | 261 | STL | 4040175 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040175/edit | Design | Mandeep Singh | 2025-12-08 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | CIQ | Design pre-checks of site scheduled on Monday, not completed on Friday. Had to cancel the integration on the actual integration date Monday 12/08. Else could have communicated the same to TMO/vendor Friday 12/05, not to align their crew |  |  |  |  | Process Gap | Loss of Trust | Low |  | 50 | 2025 | Scheduling & Planning | Schedule Not Followed | 0.65 | Major | Internal | 75 | 🟢 Monitored | 70 | 0.87 | 🔴 High Risk (>70%) | High | 5 | 73, 86, 66 (0d) | True | 7.1 | 0.95
NY01165C-Temp Deployment | 76 | NY | 4632356 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4632356/edit | PM | PM | 2025-12-18 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | FW: NY01165C - Anchor/L600/ mmwave | [8 empty] | 51 | 2025 | Nesting & Tool Errors | General | 0.57 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.31 | 🟡 Moderate (30-50%) | Medium | 0 |  | False | 9.4 | 0.35
MO05337C-SCF Support | 261 | STL | 4567927 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4567927/edit | Design | Mandeep Singh | 2025-12-05 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | CIQ | Delay in reply from CIQ team. One of mail to have updated SCF/CIQ not replied back on Friday 12/05, despite two follow-ups on same mail same day and reminder on Teams group. Taken care by next shift after 48hrs |  |  |  |  | Process Gap | Loss of Trust | Low |  | 49 | 2025 | Communication & Response | Delayed Response | 0.95 | Major | Internal | 75 | 🟢 Monitored | 17.5 | 0.33 | 🟡 Moderate (30-50%) | Medium | 4 | 286, 257, 264 | True | 7.4 | 0.95
IL11605A-Coverage Strategy | 261 | STL | 3712191 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712191/edit | PAG | Sanal Paulose | 2025-12-10 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Investigation | PAG QA | BH readiness in MB for site IL11605A, was checked wrongly in MB on 12/10, by our PAG BO team. Maybe site was checked in MB with wrong method. Since snapshot said “No AAV/MW actualized”, our IX BO team initially denied IX support. However, couple of mins after, when I checked BH status in MB, I found BH was already actualized in MB on previous day itself. Realizing the mistake, it was declared IX-GO just minutes after, and integration happened same day. Had we taken in to consideration initial BH readiness snap as our final check, and had denied IX support to FE, citing same reason, this might had come back as an unjustified escalation from TMO, that despite BH actualized in MB, why Amdocs said BH is not actualized, and why Amdocs denied IX support. |  |  |  |  | Human Error | Loss of Trust | Low |  | 50 | 2025 | Documentation & Reporting | General | 0.95 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 200 | 0.95 | 🔴 High Risk (>70%) | High | 5 | 129, 329, 37 (0d) | True | 7.6 | 0.3
CL81689C-Coverage Strategy | 251 | CL | 3955105 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955105/edit | Design | Surendra nehra | 2025-12-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Naming incorrect in port matrix . L600 was not present on site but included in port matrix |  |  | 2025-12-17 13:30:00 | Surendra |  |  |  |  | 51 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.7 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 360, 313, 237 | True | 5.4 | 0.42
MW03553C-Equipment Upgrade | 250 | IN | 3999388 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999388/edit | PM | Yashpal Hans | 2025-12-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was schedule in TI for TS after Back office started the support on 18th Dec 2025. |  | Vendors not sharing TS/CT schedule in advance are being escalated to TMO. One PPT/slide added in Weekly executive report to highlight problematic vendors |  |  | Non Amdocs |  | Medium |  | 51 | 2025 | Scheduling & Planning | General | 0.61 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 230, 233, 223 | True | 11.1 | 0.95
MW12401B-Coverage Strategy | 250 | IN | 3712220 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712220/edit | PM | Yashpal Hans | 2025-12-18 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | FE on site , BH was not ready. We got email later from TMO/FE to proceed the IX without BH actualized . |  | PM remarks: FE clearly mentioned in his mail that BH task is yet not actualized in MB and he has TMO approval to go ahead with IX. We verified with TMO. Mike Moore gave approval on mail in next 10mins. In such cases whenever FE will check-in, site will never have BH actualized in MB, and we will go ahead with IX if we have exceptional approval from TMO, else we won't. |  |  | Non Amdocs |  | Low | In such cases whenever FE will check-in, site will never have BH actualized in MB, and we will go ahead with IX if we have exceptional approval from TMO (like we had in this case) else we won't. | 51 | 2025 | Process Compliance | General | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.88 | 🔴 High Risk (>70%) | High | 5 | 124, 161, 160 | True | 6.7 | 0.3
IL03434B-Troubleshooting Support | 261 | STL | 4634638 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4634638/edit | PM | Yashpal Hans | 2025-12-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not integrated by Amdocs, Site came to Amdocs for TS and ticket was not available in Ti . No schedule or email approval provided to back office before start of support. |  | No prior information shared by TMO Dev. Tarun Gupta from TMO approved the TS PO and support ticket was created. |  |  | Non Amdocs |  | Low |  | 51 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 165, 233, 230 | False | 6.2 | 0.95
MO14444B-Coverage Strategy | 261 | STL | 3770786 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3770786/edit | Field | Yashpal Hans | 2025-12-19 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | FE | Activity of sector swap started by GC with site nested in NSI . | [8 empty] | 51 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.75 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.26 | 🟢 Low (<30%) | Medium | 0 |  | False | 7.8 | 0.3
NY6045BA_41-Small Cell Strategy | 76 | NY | 4637069 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4637069/edit | PM | PM | 2025-12-19 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | Last time request on Saturday 12/20 - NY HUB BQ06038B Small cell CIQs ** URGENT** | [8 empty] | 51 | 2025 | Scheduling & Planning | General | 0.6 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.78 | 🔴 High Risk (>70%) | Medium | 0 |  | False | 10.1 | 0.95
NJ3077BA_31-Small Cell Strategy-Small Cell Strategy | 79 | NJ | 4637068 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4637068/edit | PM | PM | 2025-12-19 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: Staten Island Saturday 12/20 work **URGENT | [8 empty] | 51 | 2025 | Scheduling & Planning | General | 0.62 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.73 | 🔴 High Risk (>70%) | Medium | 0 |  | False | 8.6 | 0.95
9LV3412A-Coverage Strategy | 255 | LU | 3955155 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955155/edit | PM | Surendra nehra | 2025-12-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule in for Integration . |  |  | 2025-12-20 16:00:00 | Surendra |  |  |  |  | 51 | 2025 | Scheduling & Planning | General | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 232 (0d), 84, 238 | True | 11.7 | 0.95
9LV2224A-Coverage Strategy | 255 | LU | 3955201 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955201/edit | Design | Surendra nehra | 2025-12-20 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Port matrix attached on site is of 9LV3334A , need correct port matrix |  |  | 2025-12-20 13:30:00 | Surendra |  |  |  |  | 51 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.7 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 360, 215, 320 (0d) | True | 8.1 | 0.59
9LV3018A-Coverage Strategy | 255 | LU | 3873348 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873348/edit | PM | Surendra nehra | 2025-12-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site not schedule for integration in Ti |  |  | 2025-12-20 13:30:00 | Surendra |  |  |  |  | 51 | 2025 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 67 (0d), 240 (0d), 122 | True | 11.7 | 0.95
9LV3018A-Coverage Strategy | 255 | LU | 3873348 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3873348/edit | PM | Surendra nehra | 2025-12-21 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | port matrix required as N2100 is dark in RFDS but mention in port matrix for alpha and beta sector. And N1900 is present on site for ABG sectors but not mentioned in port matrix for ABG sectors |  |  | 2025-12-21 13:30:00 | Surendra |  |  |  |  | 52 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.69 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 296 (0d), 320 (0d), 237 | True | 6.1 | 0.47
9NV0322A-New Build | 256 |  | 3858512 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858512/edit | Integration | Nadeem | 2025-12-20 00:00:00 | Major |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | Internal | Surendra Nehara | Closed | Implementation | Site integrated with no issue but didn't release full RTT by Ix team. It was released Later after internal escalation |  |  | 2025-12-21 00:00:00 | Ix team |  |  |  |  | 51 | 2025 | Site Readiness | General | 0.67 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 280 | 1 | 🔴 High Risk (>70%) | High | 5 | 186 (0d), 250 (1d), 77 | True | 2.3 | 0.3
9NV0269A-Coverage Strategy | 256 |  | 4205158 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4205158/edit | Design | Surendra nehra | 2025-12-22 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Port Matrix | Updated port matrix require. As per PM, in naming we have AWS3 but, this tech is not available on site |  | Updated PM has been uploaded to TI | 2025-12-23 00:00:00 | INTP team |  |  |  |  | 52 | 2025 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.6 | Minor | Internal | 15 | 🟡 POSSIBLE REPEAT | 100 | 0.98 | 🔴 High Risk (>70%) | High | 5 | 268 (0d), 267 (0d), 251 | True | 3.1 | 0.3
MW12401B-Coverage Strategy | 250 | IN | 3712220 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712220/edit | Integration | Nadeem Khan | 2025-12-19 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | Query from vendor (Nokia) Fri 12/19 6:35PM, No reply from IX BO. Second follow-up from subcon next day on same mail Sat 12/20 7:47AM, Replied back within 10mins |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Project | Low |  | 51 | 2025 | Communication & Response | Delayed Response | 0.95 | Critical | Internal | 150 | 🟢 Monitored | 25 | 0.88 | 🔴 High Risk (>70%) | High | 1 | 97 | False | 6.4 | 0.95
MW12401B-Coverage Strategy | 250 | IN | 3712220 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712220/edit | Integration | Nadeem Khan | 2025-12-24 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | TS pre-check shared by IX BO Wed. 12/24 7:56AM CT. IX BO asked PM whether to support or not at 09:28AM CT. (almost 90 mins after) Verified from Mike Moore, and updated to IX BO after 30mins that despite site approved for outage, is not go ahead because of TMO freeze. When we denied TS support, FE questioned why Amdocs NESTed the site earlier, if it was a No-Go. |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | Low |  | 52 | 2025 | Nesting & Tool Errors | Rework | 0.75 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.92 | 🔴 High Risk (>70%) | High | 2 | 330, 129 | True | 6.7 | 0.3
Issues- Process Non Compliance-Escalation | 302 | Default Market | 4652610 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4652610/edit | Integration | Venkata Tula | 2025-12-29 00:00:00 | Major |  | Concerns | 1 | Venkata Tula (TULAV@amdocs.com) |  | External_issue | TMO Manager |  |  | Request for Alignment on Tool Request Submission Process - concern from TMO Manager We continue to receive inquiries from the TMO Manager requesting clarification on the purpose of several tool requests. As previously communicated, it is essential that all submissions adhere to the guidelines provided by the TMO team. To prevent delays or potential rejections, I respectfully request that all leads ensure the required details are included prior to submitting any new tool requests. Providing complete information upfront will enable us to brief the TMO Manager in advance and facilitate smoother, more efficient approvals. The guideline communication was shared on August 14, 2025, yet we have not received a final update nor observed consistent adherence to the revised process. At this time, we continue to receive weekly emails requesting the same clarifications. We urgently require alignment from the leads to ensure this process is followed correctly and to prevent further escalation. K | [8 empty] | 53 | 2025 | Nesting & Tool Errors | Wrong Nest Type | 0.8 | Major | External_Issue | 50 | 🆕 New Issue | 140 | 0.21 | 🟢 Low (<30%) | Medium | 0 |  | False | 8.4 | 0.3
AR01670A-Coverage Strategy | 139 | AR | 3712155 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712155/edit | Design | Mandeep Singh | 2026-01-05 00:00:00 | Critical |  | Escalations | 6 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | CIQ | 01/05/2026 8:30AM CT: CIQ inputs pending WK02 sites (1 site AR01670A in PM input, 5 sites OK02682A, MO05816A, OK02678A, MO12876A, OK02645A inputs pending from CIQ team). All CIQs of WK02 were supposed to be completed on Tuesday 12/30/2025. Sent reminder on mail in WK01. And 3 reminders were sent on Teams in last 2 weeks. |  |  |  |  | Process Gap | Loss of Trust | Low |  | 2 | 2026 | Communication & Response | General | 0.55 | Critical | Internal | 150 | 🟢 Monitored | 100 | 0.22 | 🟢 Low (<30%) | Medium | 0 |  | False | 5.1 | 0.95
BC05305A-Coverage Strategy | 257 | DE | 3334840 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3334840/edit | PM | Daniel Lamas | 2026-01-04 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in close out FE on site requesting for support. PM moved the ticket to TS in TI and asking for support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 2 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.8 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 345, 229, 282 | True | 7.2 | 0.95
DE03833M-Anchor | 257 | DE | 3748897 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3748897/edit | PM | Daniel Lamas | 2026-01-05 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in closeout , FE and PM requested for support . Ticket moved to TS for support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 2 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.68 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 344, 229, 375 | True | 10.5 | 0.95
A1YH0C1A-DAS Remote Connectivity | 258 | MN | 4568167 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4568167/edit | PM | PM | 2026-01-05 00:00:00 | Major |  | Escalations | 2 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | MA1YC101A_LTE_LTE_External_Relations: Error due to enbid-1076136. | [8 empty] | 2 | 2026 | Configuration & Data Mismatch | Config Error | 0.65 | Major | Internal | 75 | 🟢 Monitored | 140 | 0.75 | 🔴 High Risk (>70%) | Medium | 0 |  | False | 7.7 | 0.57
NY01413C-COW | 76 | NY | 4650239 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4650239/edit | PM | PM | 2026-01-11 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: **URGENT** mmW Add for Inauguration - AmDocs Integration Support (NEED CIQS) **URGENT REQUEST ** | [8 empty] | 3 | 2026 | Scheduling & Planning | General | 0.61 | Major | Internal | 75 | 🟢 Monitored | 7 | 0.26 | 🟢 Low (<30%) | Medium | 0 |  | False | 7.3 | 0.95
NYTP071A-COW | 76 | NY | 4646286 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4646286/edit | PM | PM | 2025-12-29 00:00:00 | Major |  | Escalations | 2 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: NYC Mayor Inauguration ¦¦ NYTP071A & NYTP072A - Term Point and GUtran Cell relation mapping | [8 empty] | 53 | 2025 | Configuration & Data Mismatch | General | 0.66 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.98 | 🔴 High Risk (>70%) | High | 0 |  | False | 6.6 | 0.51
NYTP072A-COW | 76 | NY | 4646379 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4646379/edit | PM | PM | 2025-12-29 00:00:00 | Major |  | Escalations | 2 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: NYC Mayor Inauguration ¦¦ NYTP071A & NYTP072A - Term Point and GUtran Cell relation mapping | [8 empty] | 53 | 2025 | Configuration & Data Mismatch | General | 0.66 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.98 | 🔴 High Risk (>70%) | High | 0 |  | False | 6.6 | 0.51
LAYH044A-Venue ACS | 56 | LA | 4564187 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4564187/edit | PM | PM | 2026-01-07 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | Last time request | [8 empty] | 2 | 2026 | Scheduling & Planning | General | 0.72 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.88 | 🔴 High Risk (>70%) | High | 0 |  | False | 6.6 | 0.95
BKYH023A-New Build | 76 | NY | 4662699 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4662699/edit | PM | PM | 2026-01-06 00:00:00 | Major |  | Escalations | 1 | Maria Peponaki (Maria.Peponaki@amdocs.com) |  | Internal |  | Closed | Last time request | RE: BKYH023A ¦¦ 12 Metrotech/330 Jay St., Brooklyn, NY 11201 | [8 empty] | 2 | 2026 | Configuration & Data Mismatch | General | 0.52 | Major | Internal | 75 | 🆕 New Issue | 140 | 0.26 | 🟢 Low (<30%) | Medium | 0 |  | False | 8.0 | 0.59
DE95002A-Equipment Upgrade | 257 | DE | 4636704 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4636704/edit | PM | Daniel Lamas | 2026-01-07 00:00:00 | Major |  | Concerns | 2 | Ankur Pandey (ankur.pandey@amdocs.com) |  | Internal | Ankur Pandey | Closed | Implementation | external neighbour relatios were not shared due to which MMW wave CT got delayed | 2026-01-08 06:00:00 |  | 2026-01-08 07:30:00 | BO team manually added relations |  |  |  |  | 2 | 2026 | Site Readiness | General | 0.63 | Major | Internal | 50 | 🆕 New Issue | 280 | 0.26 | 🟢 Low (<30%) | Medium | 1 | 114 | False | 4.0 | 0.3
SLYH0L6A-Venue ACS | 72 | SL | 4209331 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4209331/edit | Integration | IX team | 2026-01-11 00:00:00 | Major |  | Escalations | 1 | DEEPAK VERMA (Deepak.Verma2@amdocs.com) |  | External_issue | Pierson PM | Closed | CBN | As per Pierson: While on-site performing the 911 calls, we were told by Amdocs that all calls were completed and passed. However, Onboarding team found missing L21 Gamma and N25 Alpha VoNR testing. |  | The team has been sensitized on this, and we will ensure compliance going forward. | [6 empty] | 3 | 2026 | Documentation & Reporting | Missing Information | 0.95 | Major | External_Issue | 75 | 🟢 Monitored | 35 | 0.2 | 🟢 Low (<30%) | High | 0 |  | False | 6.7 | 0.3
RC01367A-Coverage Strategy | 257 | DE | 3798573 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3798573/edit | PM | Daniel Lamas | 2026-01-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was RTT on 19th Nov and ticket was in closeout bucket. FE on site requesting for support, ticket moved by PM to post check and requesting for Support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 3 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 35 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 375, 376, 362 | True | 7.5 | 0.95
OK02682A-Coverage Strategy | 192 | OK | 3999449 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999449/edit | Design | Vishwas jani | 2026-01-14 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Need Updated Port matrix Three Rets are detected on site but as per attached Port Matrix for site OK02682A only two rets have mentioned | [8 empty] | 3 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.85 | 🔴 High Risk (>70%) | High | 5 | 361, 185, 216 | True | 5.3 | 0.41
MW01495A-Coverage Strategy | 250 | IN | 3712138 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712138/edit | PM | Yashpal Hans | 2026-01-15 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | BH Actualization filled as pending. FE was on site for site IX , BH filled was showing pending .PM requested for support though BH pending in field. | [8 empty] | 3 | 2026 | Scheduling & Planning | General | 0.67 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 7 | 0.96 | 🔴 High Risk (>70%) | High | 5 | 329, 168, 161 | True | 7.2 | 0.95
9LV0820A-Coverage Strategy | 255 | LU | 3955267 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955267/edit | PM | Surendra nehra | 2026-01-14 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was not schedule for IX in TI. FE on site for IX , IX team supported the site and Site was schedule later in Ti |  |  | 2026-01-14 01:00:00 | Surendra |  |  |  |  | 3 | 2026 | Scheduling & Planning | No TI Entry | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.93 | 🔴 High Risk (>70%) | High | 5 | 64 (0d), 110, 87 | True | 7.5 | 0.95
9LV0820A-Coverage Strategy | 255 | LU | 3955267 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955267/edit | Field | Surendra nehra | 2026-01-14 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site IX was cancelled after start of IX due to missing material on site. |  |  | 2026-01-14 01:00:00 | Surendra |  |  |  |  | 3 | 2026 | Scheduling & Planning | General | 0.6 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 4 | 0.91 | 🔴 High Risk (>70%) | High | 3 | 269, 357 (0d), 291 (0d) | True | 7.3 | 0.95
A1YH0C1A-DAS Remote Connectivity | 258 | MN | 4568167 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4568167/edit | PM | PM | 2026-01-14 00:00:00 | Major |  | Concerns | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | Internal |  | Open | RFDS | 1. ix team was on a continuous 6 hour call with TMO bridge; 2. We explained the site issue multiple times (5–6 times) on the call, and despite providing continuous updates, messages were still raised in another Teams channel 3. The PM requested support for the router portion, which was entirely installed and integrated by a different vendor. We had no information or documentation related to that scope. 4. The IRUs are operating in mix mode configuration, but no such details are mentioned anywhere in the RFDS. Addressing these points will help streamline support for upcoming activities | [8 empty] | 3 | 2026 | Configuration & Data Mismatch | RFDS Mismatch | 0.51 | Major | Internal | 50 | 🟢 Monitored | 175 | 0.21 | 🟢 Low (<30%) | Medium | 0 |  | False | 4.9 | 0.37
A5B0095A-Coverage Strategy | 347 | KC | 4040213 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040213/edit | Design | Vishwas jani | 2026-01-17 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | L700 missing in port matrix , need updated port matrix with L700 . | [8 empty] | 3 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 327 (0d), 320 (0d), 215 | True | 13.2 | 0.74
A3M0394A-New Build | 96 | HN | 4014184 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4014184/edit | Design | Naveen Kumar | 2026-01-16 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Need updated Port matrix. Currently only one RET detected on site but in port matrix 2 RET’s are detecting on each sector | [8 empty] | 3 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.97 | 🔴 High Risk (>70%) | High | 5 | 55 (0d), 355, 293 | True | 4.6 | 0.33
RC01005A-Coverage Strategy | 257 | DE | 3798594 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3798594/edit | PM | Daniel Lamas | 2026-01-13 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Ticket in closeout . FE on site for TS , PM moved the ticket back to post check for support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 3 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 35 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 282, 344, 229 | True | 6.7 | 0.95
IL11611A-Coverage Strategy | 261 | STL | 3712226 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712226/edit | Integration | Nadeem Khan | 2026-01-14 00:00:00 | Major |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | CBN validation snapshot missing in mail body |  | Team has been sensitize for same, will take going forward. |  |  | Process Gap | Loss of Trust | Low |  | 3 | 2026 | Documentation & Reporting | Missing Snapshot | 0.95 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 17.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 319, 254, 255 | True | 13.3 | 0.3
IL11611A-Coverage Strategy | 261 | STL | 3712226 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712226/edit | Integration | Nadeem Khan | 2026-01-15 00:00:00 | Major |  | Concerns | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | CBN validation snapshot missing in mail body |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Low |  | 3 | 2026 | Documentation & Reporting | Missing Snapshot | 0.95 | Major | Internal | 50 | 🔴 REPEAT OFFENSE | 17.5 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 319, 254, 255 | True | 13.3 | 0.3
OK02377A-Coverage Strategy | 192 | OK | 3858498 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858498/edit | Integration | Nadeem Khan | 2026-01-19 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | E911 readiness | Only whitelisted calls completed during E911 testing, but "live CT completed" mentioned in summary table |  | Team has been sensitize for same, will take going forward. |  |  | Human Error | Loss of Trust | Low |  | 4 | 2026 | Documentation & Reporting | Incorrect Status | 0.64 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 87.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 381, 183, 254 | True | 8.2 | 0.3
A2G5058S-New Build | 100 | TP | 3989094 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3989094/edit | Integration | Integration | 2026-01-09 00:00:00 | Critical |  | Escalations | 1 | Vikas Kalra (vikas.kalra@amdocs.com) |  | External_issue | TMO | Closed | Implementation | N6 was missed to add, It was NSD site. FE has to revisit for CT. |  |  |  |  | Human Error |  |  |  | 2 | 2026 | Validation & QA | Missed Tech | 0.66 | Critical | External_Issue | 150 | 🟢 Monitored | 150 | 0.8 | 🔴 High Risk (>70%) | High | 0 |  | False | 6.7 | 0.3
MW06611A-Anchor | 250 | IN | 4640343 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4640343/edit | PM | Yashpal Hans | 2026-01-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Reporting | Pay point ticket was preliminary stage, to move ticket for KPI monitoring , ticket should have been in correct stage. | [8 empty] | 4 | 2026 | Scheduling & Planning | General | 0.69 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 7 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 245, 70, 235 | True | 5.6 | 0.95
IL03863A-Coverage Strategy | 261 | STL | 3999451 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999451/edit | Design | Vishwas jani | 2026-01-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RFDS | Mismatch in RFDS and CIQ. L700 is not available in RFDS but CIQ is having the L700 Details . need updated RFDS with L700. | [8 empty] | 4 | 2026 | Configuration & Data Mismatch | RFDS Mismatch | 0.75 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.94 | 🔴 High Risk (>70%) | High | 3 | 387, 370, 65 | True | 4.7 | 0.35
MW06611A-Anchor | 250 | IN | 4640343 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4640343/edit | PM | Yashpal Hans | 2026-01-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Reporting | Live call test details and PSAP Contact info not available | [8 empty] | 4 | 2026 | Documentation & Reporting | Incorrect Status | 0.73 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 87.5 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 365, 383, 304 | True | 9.8 | 0.3
ML84235A-Anchor | 181 | ML | 3929984 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3929984/edit | PM | Daniel Lamas | 2026-01-20 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | SCF | RFDS and SCF not matching. RFDS has L700 , but SCF missing with L700 , updated SCF was not attached in Ti. | [8 empty] | 4 | 2026 | Configuration & Data Mismatch | RFDS Mismatch | 0.8 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 119 (0d), 387, 368 | True | 3.4 | 0.3
AR01777A-Coverage Strategy | 139 | AR | 3999382 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999382/edit | Integration | Yashpal Hans | 2025-09-27 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Closed | BO Support Delays | IX support from our side for site AR01777A was denied, citing BH acceptance NA in MB. Saturday 09/27. However, TMO approved the exception, and another reminder almost an hour after, to begin with integration. IX BO dint check the approval mail from TMO and dint begin with integration despite having TMO approval. IX PM got call from TMO, why IX hasn't started. IX PM asked same to IX BO. Looks like approval mail from TMO was missed by IX BO. Integration started, once IX PM intervened. |  | The team has been sensitized on this, and we will ensure compliance going forward. |  |  | Process Gap | Loss of Trust | Medium |  | 39 | 2025 | Scheduling & Planning | General | 0.54 | Critical | Internal | 150 | 🟡 POSSIBLE REPEAT | 10 | 0.9 | 🔴 High Risk (>70%) | High | 4 | 129, 326, 329 | True | 6.0 | 0.95
WI02308A-Replacement | 340 | WI | 3858358 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858358/edit | Design | Vishwas jani | 2026-01-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RIOT | Site WI02308A is having Riot red for following technology L700¦L1900¦L2100-ABG. We have observed a TAC mismatch between the RF configuration and OSS. • In CIQ/SCF LTE TAC is 46469 • In the RF configuration LTE TAC is 46588 | [8 empty] | 4 | 2026 | Configuration & Data Mismatch | TAC Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.86 | 🔴 High Risk (>70%) | High | 5 | 373, 247, 174 | True | 6.3 | 0.49
AR01985B-Coverage Strategy | 139 | AR | 3711630 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711630/edit | Design | Vishwas jani | 2026-01-22 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RIOT | Site AR01985B is having Riot red for following technology L700¦L1900¦L2100-ABG . We have observed a TAC mismatch between the RF configuration and OSS. • In CIQ/SCF LTE TAC is 45953 • In the RF configuration LTE TAC is 46078 | [8 empty] | 4 | 2026 | Configuration & Data Mismatch | TAC Mismatch | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.92 | 🔴 High Risk (>70%) | High | 4 | 372, 174, 247 | False | 6.5 | 0.5
A5B0095A-Coverage Strategy | 347 | KC | 4040213 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040213/edit | Integration | Maria Peponaki | 2026-01-19 00:00:00 | Critical |  | Concerns | 1 | Amit Mishra (amit.mishra@amdocs.com) |  | Internal | Amit Mishra | Closed | SCF | Engineer missed to select the MOCN polygon area | 2026-01-20 12:30:00 | session scheduled with the IX Team for the MOCN and Spectrum Sheet Validation Tool | 2026-01-20 12:30:00 | Amit Mishra / Maria Peponaki | Human Error |  | Low |  | 4 | 2026 | Validation & QA | Missed Call Test | 0.75 | Critical | Internal | 100 | 🟡 POSSIBLE REPEAT | 175 | 0.91 | 🔴 High Risk (>70%) | High | 0 |  | False | 3.8 | 0.3
DE03833M-Anchor | 257 | DE | 3748897 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3748897/edit | PM | Daniel Lamas | 2026-01-27 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in closeout , FE and PM requested for support .SIte was RTT on 12/06 .Ticket moved to TS for support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 5 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.61 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.81 | 🔴 High Risk (>70%) | High | 5 | 376, 345, 354 | True | 5.2 | 0.95
TC02314A-Coverage Strategy | 257 | DE | 3798575 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3798575/edit | PM | Daniel Lamas | 2026-01-27 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Scheduling | Site was in closeout and RTT was shared on 11/26/2025. FE was site for RTWP support , ticket moved to post check for Support. |  | Site needed to be TS and I moved the ticket. I don't see the relevance in this escalation. |  | Dan Lamas |  |  |  |  | 5 | 2026 | Scheduling & Planning | Ticket Status Issue | 0.63 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 20 | 0.9 | 🔴 High Risk (>70%) | High | 5 | 375, 354, 345 | True | 5.7 | 0.95
TU03190A-Coverage Strategy | 421 | TU | 4040189 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4040189/edit | Design | Vishwas jani | 2026-01-28 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Incorrect Port matrix. Alpha has RET marked as TU03190A _A22LB instead of TU03190A_A12JLB. | [8 empty] | 5 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.6 | Major | Internal | 75 | 🟢 Monitored | 175 | 0.79 | 🔴 High Risk (>70%) | Medium | 2 | 313, 327 (0d) | True | 6.8 | 0.52
AR01985B-Coverage Strategy | 139 | AR | 3711630 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711630/edit | Integration | Nadeem Khan | 2026-01-23 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | CBN validation snapshot missing in mail body | [8 empty] | 4 | 2026 | Documentation & Reporting | Missing Snapshot | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 17.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 319, 254, 255 | True | 13.3 | 0.3
MW03612A-Coverage Strategy | 250 | IN | 4219382 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4219382/edit | Integration | Nadeem Khan | 2026-01-23 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | CBN validation snapshot missing in mail body | [8 empty] | 4 | 2026 | Documentation & Reporting | Missing Snapshot | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 17.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 319, 254, 255 | True | 13.3 | 0.3
A5S0142A-Coverage Strategy | 347 | KC | 3711649 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3711649/edit | Integration | Nadeem Khan | 2026-01-28 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | CBN validation snapshot missing in mail body | [8 empty] | 5 | 2026 | Documentation & Reporting | Missing Snapshot | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 17.5 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 319, 254, 255 | True | 13.3 | 0.3
OK02645A-Coverage Strategy | 192 | OK | 3712128 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712128/edit | Integration | Nadeem Khan | 2026-01-28 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | E911 completion mail has summary table copied from E911 Go mail | [8 empty] | 5 | 2026 | Documentation & Reporting | General | 0.85 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 183, 179, 177 | True | 11.0 | 0.3
WI03030A-Coverage Strategy | 340 | WI | 3673615 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3673615/edit | Integration | Nadeem Khan | 2026-01-29 00:00:00 | Minor |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | In E911 complete mail's summary table, 4 sectors (ABGD) has been mentioned, despite having 3 sectors (ABG) in actual | [8 empty] | 5 | 2026 | Documentation & Reporting | General | 0.85 | Minor | Internal | 15 | 🟢 Monitored | 40 | 0.79 | 🔴 High Risk (>70%) | Medium | 5 | 179, 381, 304 | True | 5.6 | 0.3
IL09105A-L600 | 261 | STL | 3712208 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712208/edit | Integration | Nadeem Khan | 2026-01-30 00:00:00 | Major |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | E911 readiness | PSAP contact info table missing in E911 GO mail | [8 empty] | 5 | 2026 | Documentation & Reporting | Missing Information | 0.95 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 35 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 280, 283, 304 | False | 11.5 | 0.3
IL09105A-L600 | 261 | STL | 3712208 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3712208/edit | Design | Vishwas jani | 2026-01-30 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | RFDS | E-tilt missing in RFDS Angle-E-Tilt is mentioned only for Delta sectors (both Mid and Low bands) in the proposed RFDS | [8 empty] | 5 | 2026 | Nesting & Tool Errors | General | 0.55 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.9 | 🔴 High Risk (>70%) | High | 1 | 218 | False | 5.0 | 0.3
A3M0142A-New Build | 96 | HN | 4014170 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4014170/edit | Design | Ramesh Naik | 2026-01-29 00:00:00 | Minor |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Site is having 1x1 (mid cell so it's 1×1 ) per sector RET configuration, but PM is designed 2x2 per sector configuration | [8 empty] | 5 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.63 | Minor | Internal | 15 | 🔴 REPEAT OFFENSE | 100 | 0.95 | 🔴 High Risk (>70%) | High | 3 | 293, 227, 91 | True | 3.0 | 0.3
OK02415A-Anchor | 192 | OK | 4649790 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4649790/edit | Design | Vishwas jani | 2026-01-30 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Site has GSM available and RFDS also but in Port Matrix not available GSM | [8 empty] | 5 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.75 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.94 | 🔴 High Risk (>70%) | High | 3 | 197, 91, 169 | True | 4.0 | 0.3
MO05816A-Coverage Strategy | 261 | STL | 3858473 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3858473/edit | Design | Vishwas jani | 2026-02-01 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal |  |  | RFDS | Mismatch in RFDS and CIQ. As per RFDS L700 not available on site.but its showing in CIQ & SCF | [8 empty] | 6 | 2026 | Configuration & Data Mismatch | RFDS Mismatch | 0.65 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 175 | 0.92 | 🔴 High Risk (>70%) | High | 4 | 368, 370, 119 (0d) | True | 4.6 | 0.34
A6A0993A-Coverage Strategy | 467 | CB | 4673266 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4673266/edit | Design | Vishwas jani | 2026-02-01 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Port Matrix | Mismatch in PORT matrix and RET. N2100 technology is included in the RET definition naming as per the port matrix. However, as per the current site configuration, N2100 is not available on Site | [8 empty] | 6 | 2026 | Configuration & Data Mismatch | Port Matrix Mismatch | 0.95 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 140 | 0.91 | 🔴 High Risk (>70%) | High | 5 | 320 (0d), 313, 243 (0d) | True | 5.3 | 0.41
WI01264A-Anchor | 192 | OK | 2988150 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/2988150/edit | PM | Yashpal Hans | 2026-02-03 00:00:00 | Critical |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Hardware missing on site, 1-ASIL and 2 ABIL card missing on site.SIte has to be revert due to missing HW. |  | Material management not SoW of Amdocs in HL |  |  | Non Amdocs |  | Low |  | 6 | 2026 | Site Readiness | General | 0.61 | Critical | Internal | 150 | 🟢 Monitored | 400 | 0.88 | 🔴 High Risk (>70%) | High | 0 |  | False | 3.8 | 0.3
A5C0458A-Anchor | 347 | KC | 4647605 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4647605/edit | PM | Yashpal Hans | 2026-02-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | Incorrect Schedule Site schedule for DT integration, site logged by FE for iX in MW. | [8 empty] | 6 | 2026 | Scheduling & Planning | Schedule Not Followed | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 123, 205, 66 (0d) | True | 9.8 | 0.95
A6C0136A-COW | 467 | CB | 4694064 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/4694064/edit | Design | Surendra nehra | 2026-02-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Closed | Incomplete Scope | Mismatch hardware. Site cancelled for IX due to material supplied on site not matching with RFDS or script. |  |  | 2026-02-03 01:00:00 | INTP |  |  |  |  | 6 | 2026 | Configuration & Data Mismatch | RFDS Mismatch | 0.75 | Major | Internal | 75 | 🟡 POSSIBLE REPEAT | 175 | 0.94 | 🔴 High Risk (>70%) | High | 5 | 63 (2d), 234, 107 | True | 4.2 | 0.3
OK02372B-Coverage Strategy | 192 | OK | 3531075 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3531075/edit | PM | Yashpal Hans | 2026-02-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | Site Schedule in TI for TS was FE logged and precheck shared by BO. | [8 empty] | 6 | 2026 | Scheduling & Planning | Schedule Not Followed | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 230, 233, 220 | True | 8.9 | 0.95
OK01582A-Coverage Strategy | 192 | OK | 3999439 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3999439/edit | PM | Yashpal Hans | 2026-02-03 00:00:00 | Major |  | Escalations | 1 | Nadeem Khan (nadeem.khan@amdocs.com) |  | Internal | Nadeem khan | Open | Scheduling | Site Schedule in TI after FE logged in with back office for IX support. | [8 empty] | 6 | 2026 | Scheduling & Planning | Schedule Not Followed | 0.8 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 70 | 0.92 | 🔴 High Risk (>70%) | High | 5 | 69, 88, 64 (0d) | True | 8.9 | 0.95
CI13142A-Coverage Strategy | 248 | CI | 3955063 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/3955063/edit | Integration | Nadeem Khan | 2026-02-03 00:00:00 | Major |  | Escalations | 0 | Surendra Nehara (Surendra.Nehara@amdocs.com) |  | Internal | Surendra Nehara | Closed | Implementation | EOD released with minor issues and didn't release the RTT. Later released upon internal communication | 2026-02-04 01:00:00 | RTT released | 2026-02-04 01:00:00 | Integration |  |  |  |  | 6 | 2026 | Configuration & Data Mismatch | General | 0.67 | Major | Internal | 75 | 🔴 REPEAT OFFENSE | 140 | 0.85 | 🔴 High Risk (>70%) | High | 2 | 186 (0d), 338 (1d) | True | 3.6 | 0.3
WI01264A-Anchor | 192 | OK | 2988150 | https://www.amdocs-ti.com/tmo/projects/intgr/tickets/2988150/edit | Integration | Nadeem Khan | 2026-02-04 00:00:00 | Critical |  | Escalations | 1 | Yashpal Hans (Yashpal.Hans@amdocs.com) |  | Internal | Yashpal Hans | Open | Reporting | No update over ongoing IX from last 14hrs from back-office, neither to TMO nor to PM | [8 empty] | 6 | 2026 | Scheduling & Planning | General | 0.65 | Critical | Internal | 150 | 🟢 Monitored | 10 | 0.89 | 🔴 High Risk (>70%) | High | 5 | 143, 329, 87 | True | 9.8 | 0.95

## Visual Analytics
VISUAL ANALYTICS
Strategic Visual Analysis - All Charts
📊 Risk Analysis
The chart illustrates the Friction Pareto Analysis of an 80/20 Rule Application, highlighting the distribution of friction points across various categories. ¦ Key: The most significant friction point is Scheduling & Planning, with a substantial 7,230 friction points, while Nesting & Tool Error has the lowest friction points at 845. ¦ Action: To optimize the application, it is essential to focus on reducing friction points in the Scheduling & Planning and Configuration & Data categories, as these areas have the greatest impact on the overall friction point count. | The chart illustrates the distribution of risk origin sources in a risk management context, categorized by internal and external factors. ¦ Key: The majority of risk origins (89.9%) are internal, while only 10.1% are external. ¦ Action: To effectively manage risk, it is crucial to focus on internal risk sources, as they account for the majority of risk origins. This requires a targeted approach to risk mitigation strategies, focusing on internal controls and processes to address these risks.
The chart displays a risk trend analysis for a 3-month moving average (MA) and target score, comparing historical performance to a target score. ¦ Key: The risk trend is below the target score for the 3-month MA, indicating a lower risk level compared to the target. ¦ Action: Based on the analysis, it is recommended to maintain the current risk management strategy, as it is performing below the target score, indicating a lower risk level. | The chart is a Severity-Impact Matrix Escalation Distribution Analysis, showing the distribution of business impact and severity levels for various events or incidents. ¦ Key: The majority of events have a significant business impact, with 30 events classified as Severe, and only 1 event classified as Critical. ¦ Action: Given the high number of events with significant business impact, it may be beneficial to prioritize resources and attention towards these events to mitigate their impact and prevent further escalation.
The chart displays a daily escalation count for breaches over a period of time, with a focus on the number of breaches and their corresponding escalation counts. ¦ Key: The chart shows a significant spike in the number of breaches in the first few days of the period, with a peak of 38 breaches on the first day. This is followed by a gradual decline in the number of breaches over the next few days. ¦ Action: Based on the chart, it appears that the number of breaches is decreasing over time, which could be a positive trend. However, the significant spike in the first few days suggests that there may be some underlying issues that need to be addressed to prevent future spikes. It may be worth investigatin | The chart shows a daily friction score with smart alert thresholds, indicating the number of breaches and daily friction score over time. ¦ Key: The chart shows a significant increase in daily friction score from 2025-09 to 2025-11, with a peak of around 800. ¦ Action: The chart suggests that the daily friction score is increasing, and it may be necessary to adjust the smart alert thresholds to account for this change.
👷 Engineer Performance
The chart displays a bar chart of friction scores for engineers, with scores ranging from 150 to 225. ¦ Key: The chart shows that most engineers have a friction score of 150, while only two engineers have a score above 200. ¦ Action: To improve overall performance, it is recommended to focus on the engineers with scores above 200, as they are likely to have the most impact on the team's overall performance. | The chart shows the Engineer Learning Progress for issue resolution and repeat patterns, comparing the number of issues resolved and repeated for each engineer. ¦ Key: Yashpal Hans has the highest number of issues resolved (11) and the highest number of issues repeated (96), indicating a significant difference in his performance. ¦ Action: Yashpal Hans' high number of repeated issues suggests that he may benefit from additional training or support to improve his performance in issue resolution.
🏢 Line of Business
The chart shows the LOB Friction Distribution Business Unit Performance, with an average score of 62.3. ¦ Key: The PAG unit has the highest score at 129.5, while the Optimization unit has the lowest score at 29.0. ¦ Action: The PAG unit's high score suggests that it is performing well and may be worth emulating by other units. However, the Optimization unit's low score may indicate areas for improvement. | The chart compares the performance of three metrics - Volume (normalized), Friction Score, and Resolution Time (normalized) - across different business areas. ¦ Key: The Friction Score is the lowest across all business areas, with a score of 29 in the Optimization area. ¦ Action: Focus on improving the Friction Score to enhance overall performance and reduce friction in business operations.
The chart shows the LOB (Line of Business) category breakdown of issue distribution by business unit. ¦ Key: The PM category has the highest number of issues, with over 150 issues, while the PAG category has the lowest number of issues, with around 10 issues. ¦ Action: Based on the chart, it appears that the PM category is experiencing the most issues, which may indicate a need for increased resources or attention to this area. It may be beneficial to investigate the causes of these issues and develop strategies to address them.
🔍 Root Cause Analysis
The chart shows the Root Cause Analysis of Top Escalation Drivers, highlighting the most common reasons for escalations. ¦ Key: Scheduling & Planning is the leading cause of escalations, accounting for 136 occurrences, followed by Configuration & Data Mismatch with 98. ¦ Action: Addressing Scheduling & Planning issues should be a priority to reduce the number of escalations. This could involve improving planning processes, increasing resources, or implementing better communication strategies. By addressing this top driver, organizations can reduce the number of escalations | The chart displays four pie charts representing different aspects of a system's performance, including data quality, learning system integrity, model accuracy, and feedback loop. ¦ Key: The data quality pie chart shows that 92% of data is high quality, indicating a strong foundation for the system. ¦ Action: Based on the high data quality and model accuracy, it is recommended to focus on improving the learning system's integrity and feedback loop to further enhance overall system performance.
The chart shows the distribution of escalations across various categories, providing a breakdown of the number of escalations for each category. ¦ Key: The category with the highest number of escalations is Scheduling & Planning, with 85 escalations, while Nesting & Tool Errors has the lowest number of escalations, with only 15. ¦ Action: Based on the chart, it appears that Scheduling & Planning is a critical area that requires more resources or attention to reduce the number of escalations. By focusing on this category, the company may be able to reduce the number of escalations and improve overall performance. | The chart compares the distribution of ticket volumes between categories and subcategories, providing insights into the volume of tickets across different categories. ¦ Key: The category with the highest ticket volume is Scheduling & Planning (43), while the subcategory with the highest ticket volume is Sub-Cat-2 (44). ¦ Action: Based on the chart, it appears that Scheduling & Planning is a critical category that requires more resources and attention, while Sub-Cat-2 is a high-priority subcategory that needs to be addressed. It is recommended to allocate more resources to these areas to improve overall ticket volume and res
The chart compares the baseline and recent periods for various categories, providing insights into their performance. ¦ Key: The chart highlights a significant improvement in "Nesting & Tool Errors" with a 198% increase, while "Scheduling & Planning" shows a notable 58% decline. ¦ Action: To address the decline in Scheduling & Planning, it is recommended to review and optimize the planning process to improve efficiency and reduce errors. This could involve re-evaluating resource allocation, and and to and to and to and to and to and to and to and to and to and to | The chart compares the distribution of categories between a "Baseline" (60% of the data) and a "Recent" (40% of the data) dataset. ¦ Key: The category with the largest difference between Baseline and Recent is "Scheduling & Planning" with a 58% increase from Baseline to Recent. ¦ Action: Given the significant increase in "Scheduling & Planning" from Baseline to Recent, it may be worth exploring this category further to understand why it has become so much more important in recent times.
🤖 Predictive Models
The chart shows a comparison of model performance trends over six weeks, focusing on predictive model accuracy, model performance trend analysis, and model performance. ¦ Key: The chart indicates that all three models (Predictive Model Accuracy, Model Performance Trend Analysis, and Model Performance) have seen an increase in performance over the six weeks. ¦ Action: Based on the chart, it appears that all three models are performing better over time, suggesting that they are likely to continue to improve. Therefore, it is recommended to continue monitoring and evaluating the performance of these models to ensure they maintain their high performance. | The chart compares AI Recurrence Prediction Predicted vs Actual Rates across various categories. ¦ Key: The chart shows that most categories have a predicted rate higher than the actual rate, with Process Complia. having the largest difference at 95% predicted vs 90% actual. ¦ Action: Based on the chart, it appears that the AI Recurrence Prediction model is overestimating the actual rates for most categories, suggesting that the model may need to be adjusted or retrained to better match actual results.
The chart shows a box plot of resolution time distribution for various categories, with target and actual values represented. ¦ Key: The actual values for most categories are higher than the target value of 2.5 days, indicating a general trend of longer-than-expected resolution times. ¦ Action: Based on the chart, it appears that resources or resources-optimization could be needed for categories like Process Complia., Scheduling & PI., and Site Readiness to improve actual values and align with the target value.
💰 Financial Impact
The chart provides a financial impact analysis of various categories, comparing direct, indirect, and potential savings. ¦ Key: The chart shows that "Configuration &." has the highest potential savings of $9K, while "Communication &." has the lowest potential savings of $0K. ¦ Action: Based on the chart, it appears that investing in "Configuration &." would be most beneficial, as it has the highest potential savings. However, it also has the highest direct cost, so it's essential to consider both costs and benefits when making decisions. | The chart displays the sub-category financial impact of top cost drivers, with a total financial impact of $810,000. ¦ Key: The chart highlights that Backhaul Issues have the most significant financial impact, accounting for $180,000 of the total, followed by MW/Transmission Issues at $160,000. ¦ Action: To address the most significant financial impact, it is recommended to focus on addressing Backhaul Issues and MW/Transmission Issues, which account for the majority of the financial impact.
🔗 Similarity Search Analysis
The chart shows a distribution of similar ticket counts for 396 tickets analyzed, with an average of 3.4 matches per ticket. ¦ Key: The chart reveals a skewed distribution, with a majority of tickets having few matches (0-2) and a few tickets having many matches (5-6). ¦ Action: Given the majority of tickets have few matches, it may be worth exploring ways to improve match quality or increase the number of matches per ticket. This could involve adjusting algorithms or increasing resources for match analysis. | The chart presents a bar chart comparing resolution consistency across various categories, with a focus on identifying areas for improvement. ¦ Key: The chart reveals that Scheduling & Planning has the highest number of Inconsistencies (122), while Nesting & Tool Errors have the lowest (9), indicating a significant difference in resolution consistency across categories. ¦ Action: To improve overall resolution consistency, it is recommended to focus on Scheduling & Planning, as it has the most Inconsistencies, and consider implementing strategies to reduce Inconsistenss in this category.
The chart displays a distribution of similarity scores for 321 matches, with a focus on high and medium confidence scores. ¦ Key: The chart shows that most matches have high confidence scores, with a peak at around 0.8-0.9, while medium confidence scores are less frequent and tend to be lower. ¦ Action: Based on the distribution of scores, it appears that most matches are highly similar, which could suggest that the algorithm is performing well in most cases. However, it also suggests that there may be some cases where the algorithm is not as accurate, which could be worth investigating further. | The chart compares the mean resolution time for similar ticket analysis between expected (similar tickets) and AI-predicted (AI Predicted) categories. ¦ Key: The mean difference in resolution time between expected and AI-predicted categories is 9.5 days, with expected categories having a longer mean resolution time. ¦ Action: Based on the chart, it appears that the expected categories have a longer mean resolution time, which may indicate that there are inefficiencies or processes that can be improved to reduce the mean resolution time. It may be worth investigating and addressing these ineffs to improve the mean resolut
The chart shows a comparison of similarity search effectiveness across various categories and origins, with a focus on match effectiveness. ¦ Key: The chart reveals that Site Readiness and Site Readiness-related categories (Site Readiness, Site Readiness Compli., Scheduling & PI) have the highest match effectiveness, with Site Readiness achieving 100% match effectiveness. ¦ Action: Based on the chart, it appears that Internal sources are more effective for similarity searches, and therefore, it is recommended to focus on Internal sources for optimal results.
📚 Lessons Learned Effectiveness
The chart shows learning effectiveness scores for various categories based on recurrence, lesson completion, and consistency. ¦ Key: The category with the lowest score is Process Compliancy with an F (2), while Nesting & Tool Error has the highest score with an F (12). ¦ Action: Based on the chart, it appears that there is room for improvement in all categories, especially Process Compliancy, which has the lowest score. It may be worth re-evaluating the lesson content and/or teaching methods to improve these scores. | The chart shows the lesson documentation and completion rate by category, with a focus on the percentage of lessons completed. ¦ Key: The chart reveals that all categories have a completion rate of 0%, indicating that no lessons have been completed in any category. ¦ Action: Given that no lessons have been completed in any category, it is recommended to review and adjust the lesson documentation and completion process to improve the overall completion rate. This could involve re-evaluating the lesson content, teaching methods, and/or providing more resources or support
The chart compares Recurrence Rate (Rec. Rate) to Lesson Completion Rate (L. C. Rate) for various learning processes. ¦ Key: The chart shows that Process Comp. and Config. have the highest Rec. Rate, while Process Comp. and Config. have the lowest L. C. Rate. ¦ Action: Based on the chart, it appears that Process Comp. and Config. are both high Rec. Rate and low L. C. Rate. This could be due to the nature of these processes, and it may be worth exploring why this is the case. | The chart presents a learning effectiveness score for various categories across different business/ market lines, with scores ranging from 0 to 100. ¦ Key: The category with the highest learning effectiveness score is "Optimization" with a score of 84, while "Communication &..." has the lowest score of 73. ¦ Action: Based on the chart, it appears that "Optimization" is a critical category for learning effectiveness, and it may be worth investing in resources or training programs to improve performance in this area.
The chart provides a visual representation of AI-generated improvement recommendations for various aspects of a process, including Process Compliance, Scheduling & Planning, Site Readiness, Documentation & Reporting, and Validation & Quality. ¦ Key: The chart highlights the criticality of each aspect, with Process Compliance and Scheduling & Planning being critical (C) and others being critical (C) or critical (C), indicating that these areas require immediate attention. ¦ Action: Based on the chart, it is recommended that resources and resources be directed towards improving Process Com RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM RECOM